## 1st qtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1st QUARTER, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
repair/improvement of Farmer's Pavillion | Sta. Barbara, Pangasinan | 2973554 | [5 empty] | 1/28/2015 | 6911 | PR# 0082
Proposed Perimerer Fence | Ketegan E/S., Brgy. Ketegan, Bautista, Pangasinan | 1405947 | [5 empty] | 2015-03-04 | 6911 | PR# 1202
Construction of Slope Protection | along Calarian Creek, Nursery, Tebag, Sta. Barbara, Pangasinan | 1446450 | [5 empty] | 2015-03-04 | 6911 | PR#0614
2-Storey Multi-purpose Bldg. (ABC Building) Phase II, | Alvear Street, Lingayen, Pangasinan | 1861017 | [5 empty] | 2015-03-04 | 6911 | PR#0312
Construction of 1 unit 2-Storey Multi-Purpose Bldg., (Brgy. Hall), | Poblacion East, Bautista, Pangasinan | 2305855 | [5 empty] | 2015-03-04 | 6911 | PR#0763
Additional works of various of various buildings at EPDH, | Tayug, Pangasinan | 2238748 | [5 empty] | 2015-03-04 | 6911 | PR#0059
Renovation/Improvement of Pangasinan Internal Affair Service (PIAS) Building, PNP Headquarters, | Lingayen, Pangasinan | 1146662 | [5 empty] | 2015-03-04 | 6911 | PR#1237
installation of Reinforced Concrete Culvert Pipes (RCCP)), Nursery Compound, | Tebag, Sta. Barbara, Pangasinan | 217442 | [5 empty] | 2015-03-04 | 6911 | PR#0378
Improvement of CT Scan Room | Pangasinan Provincial Hospital | 388107 | [5 empty] | 2015-03-04 | 6911 | PR#0630
Rehabilitation/Concreting of Basement flooring of Malong and Palaris Buildings, Capitol Compound, | Lingayen, Pangasinan | 221234 | [5 empty] | 2015-03-04 | 6911 | PR#1187
construction of Philippine Affairs Office (Pangasinan Chapter), Capitol Compound, | Lingayen, Pangasinan | 1979401 | [5 empty] | 2015-03-12 | 6911 | PR#2456
Repair/Rehab of Repair Bay 1 and Office Building, Motorpool Compound, | Lingayen, Pangasinan | 2593367 | [5 empty] | 2015-03-12 | 6911 | PR#1916
396 MT Asphalt Pre-mix and 17 drums Emulsified Asphalt for the improvement of Road Network and Parking Area @ Bayambang Dist. Hospital, | Bayambang, Pangasinan | 2422800 | [5 empty] | 2015-03-23 | 6911 | PR#2621
construction of Multi-Purpose Bldg., (Brgy. Hall), | Brgy Mapolopolo, Basista, Pangasinan | 1198627 | [5 empty] | 2015-03-23 | 6911 | PR#1319
construction of Stone Masonry with Barriers along Mabilao-Binday Prov'l Road, | San Fabian, Pangasinan | 555185 | [5 empty] | 2015-01-28 | 8917-1 | PR#0211
repainting of various concrete bridges | 1st-6th Pangasinan Engineering Districts | 266039 | [5 empty] | 2015-02-27 | 8917-1 | PR#1204
construction of Stone masonry with barrier and concreting of Road Shoulder along Mabilao-Binday Road, | San Fabian, Pangasinan | 1371178 | [5 empty] | 2015-03-04 | 8917-1 | PR#1034
repainting of various Provicial Steel Bridges | around the Province of Pangasinan | 190261 | [5 empty] | 2015-03-23 | 8917-1 | PR#1142
Mr. Bernabe Cabrera Salayog- Financial Assistance, cost of tiling works of Sodality Road | Manaoag, Pangasinan | 500000 | [5 empty] | Paid Jan., 2015
repair of Sison Auditorium (Vice-Governor's Room), | Lingayen, Pangasinan | 187485 | [5 empty] | 2015-02-11 | 3917 | PR#0311
furnishing materials, labor, equipment and others- for the completion of 2-storey Multi-Purpose building (Brgy. Hall), | San Guillermo, San Jacinto, Pangasinan | 1397805 | [5 empty] | 2015-03-19 | 3917 | PR#2921
Economic Development
Asphalting and blocktopping of RHU and Municipal Hall Compound, | Urbiztondo, Pangasinan | 1505900 | [5 empty] | 2015-03-04 | 6911 | PR#0036
Asphalting of Victorio-Pangascasan (Sual Coastal Road), Victoria Sec., | Alaminos City | 644000 | [5 empty] | 2015-01-28 | 8917-1 | PR#0157
concreting of Brgy. Esperanza Road, | Sison, Pangasinan | 158774 | [5 empty] | 2015-02-11 | 8917-1 | PR#0253
Asphalting of Frank's Canteen Compound, | Lingayen, Pangasinan | 314800 | [5 empty] | 2015-02-11 | 8917-1 | PR#0212
Asphalt materials for the Proposed Blocktopping of Brgy. Buenlag Road, | Bugallon, Pangasinan | 4058900 | [5 empty] | 2015-03-04 | 8917-1 | PR#0060
blocktopping of Cervantes Road, | Brgy. Salomague Norte, Bugallon, Pangasinan | 648200 | [5 empty] | 2015-03-04 | 8917-1 | PR#0212
414 MT Asphalt Pre-Mix and 18 drums Emulsified Asphalt in Asphalting of Balangobong Road, | Alaminos, Pangasinan | 2536200 | [5 empty] | 2015-03-04 | 8917-1 | PR#1223
concreting and construction of slope protection (stone masonry) | Brgy. Poponto, Bautista, Pangasinan | 4175839 | [5 empty] | 2015-03-04 | 8917-1 | PR#0754
construction of stone masonry | Brgy. Macalong, Asingan, Pangasinan | 3652065 | [5 empty] | 2015-03-04 | 8917-1 | PR#0398
concreting of Tombor Road, Phase II, | Binmaley, Pangasinan | 1794383 | [5 empty] | 2015-03-04 | 8917-1 | PR#0691
blocktopping/patching of various Poblacion Roads | Manaoag, Pangasinan | 925800 | [5 empty] | 2015-03-04 | 8917-1 | PR#0631
asphalting of By-pass Road, Poblacion, | Manaoag, Pangasinan | 340200 | [5 empty] | 2015-03-16 | 8917-1 | PR#2106
259 MT Asphalt in Asphalting of Pinmilapil Road | Sison, Pangasinan | 1582900 | [5 empty] | 2015-03-16 | 8917-1 | PR#1879
Asphalting of Amagbagan Road, | Sison, Pangasinan | 1972600 | [5 empty] | 2015-03-16 | 8917-1 | PR#1917
Asphalting of Poblacion road | Dama de Noche St. and Cemetery road, Mapandan, Pangasinan | 563600 | [5 empty] | 2015-03-16 | 8917-1 | PR#2184
Asphalting of Brgy. Macalong Road, | Asingan, Pangasinan | 861900 | [5 empty] | 2015-03-23 | 8917-1 | PR#1796
asphalting of Pantal Road, | Bugallon, Pangasinan | 2597500 | [5 empty] | 2015-03-23 | 8917-1 | PR#2261
Asphalting of various streets | Bayambang, Pangasinan | 4755300 | [5 empty] | 2015-03-23 | 8917-1 | PR#2807
Asphalting various streets at | Bayambang, Pangasinan | 3591400 | [5 empty] | 2015-03-23 | 8917-1 | PR#2730
construction of slope protection (Gabions) of the eroded riverbank along Shahani Road, | Brgy. Toboy, Asingan, Pangasinan | 4076795 | [5 empty] | 2015-04-10 | 8917-1 | PR#0903
Proposed Concrete paving along San Jacinto-Pozorrubio Road, Lobong Section, | San Jacinto, Pangasinan | 2692805 | [5 empty] | 2015-04-10 | 8917-1 | PR#0693
concreting of Sitio Cupang Road, | Brgy. Umanday, Bugallon, Pangasinan | 545054 | [5 empty] | 2015-03-19 | 3917 | PR#0704
100 units diesel engine water pump with complete accessories |  | 2400000
Loans Granted to various Multi-Purpose Cooperatives and Associations |  | 1000000 | [6 empty] | 8915
Tools needed for 2 drilling Team @ Waterworks Section, | PEO, Lingayen, Pangasinan | 173570.78 | [5 empty] | 2015-02-25 | 8919-2 | PR#0632
construction of 1 unit Deepwell Handpump at | Nalsian - Bacayao, Calasiao, Pangasinan | 113118 | [5 empty] | 2015-03-09 | 8919-2 | PR#0247
construction of one unit Artesian Well at | Brgy. Leet, Sta. Barbara, Pangasinan | 139921 | [5 empty] | 2015-03-09 |  | PR#0379
Environmental Development

## 2nd qtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE |  |  | REFERENCES
Social Development
Proposed Perimerer Fence | Ketegan E/S., Brgy. Ketegan, Bautista, Pangasinan | 1405947 |  |  | 100% | 1400624.67 |  | 60% paid 5/2015 40% paid 6/2015 | 6911 | Ranger Design & Constn PR#1202
Asphalting and blocktopping of RHU and Municipal Hall Compound | Urbiztondo, Pangasinan | 1505900 |  |  | 100% | 1504565 |  | Controlled 6-19-15 | 6911 | BET C/S PR#0036
Construction of Slope Protection | along Calarian Creek, Nursery, Tebag, Sta. Barbara, Pangasinan | 1446450 |  |  | 100% | 1444560 |  | Controlled 6-19-15 | 6911 | Goodvibe Builders PR#0614
construction of 2-Storey Multi-purpose Bldg. (ABC Building) Phase II, | Alvear Street, Lingayen, Pangasinan | 1861017 |  |  | 100% | 1676824.7 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | CAD Constn PR#0312
Construction of 1 unit 2-Storey Multi-Purpose Bldg., (Brgy. Hall) | Poblacion East, Bautista, Pangasinan | 2305855 |  |  | 100% | 2294562.38 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | Zota Trdg. & Constn PR#0763
Additional works of various of various buildings at EPDH | Tayug, Pangasinan | 2238748 |  |  | 100% | 2230830.79 |  | Paid 5/2015 | 6911 | BET Constn & Supply PR#0059
Renovation/Improvement of Pangasinan Internal Affair Service (PIAS) Building, PNP Headquarters | Lingayen, Pangasinan | 1146662 |  |  |  | 1142327.13 |  | 60% paid 5/2015 40% paid 6/2015 | 6911 | PR#1237
Improvement of CT Scan Room at Pangasinan Provincial Hospital | San Carlos City | 388107 |  |  | 100% | 385768.45 |  | Paid 6/2015 | 6911 | MCB C/S PR#0630
Construction of Philippine Affairs Office (Pangasinan Chapter), | Capitol Compound, Lingayen, Pangasinan | 1979401 |  |  | 100% | 1974587.28 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | CAD Constn PR#2456
Repair/Rehab of Repair Bay 1 and Office Building | Motorpool Compound, Lingayen, Pangasinan | 2593367.1 |  |  | 100% | 2587043.07 |  | 50% paid 5/2015 50% paid 6/2015 | 6911 | Ranger Design & Constn PR#1916
Concreting between Power house and Main Building @ Pozorrubio Community Hospital, | Pozorrubio, Pangasinan | 53873.5 |  |  |  | 53873.5 |  | Obligated | 6911 | PR#2234
Construction of materials Testing and Quality Control Bldg., | Motorpool Compound, Lingayen, Pangasinan | 1638590 |  |  |  | 1638590 |  | Obligated | 6911 | PR#0748
Completion of Senior Citizen Bldg., and Reconstruction of Perimeter Fence with Steel Gate and Concreting of Parking Space | Lingayen, Pangasinan | 1236108 |  |  |  | 1236108 |  | Obligated | 6911 | PR#4025
Concreting of Sitio Cristobal Farm to Market Road, | Brgy. Cabilocaan, Calasiao, Pangasinan | 3268546 |  |  |  | 3268546 |  | Obligated | 6911 | PR#2259
Concreting of Brgy, Auditorium (Floor Slab) | Brgy. Bolaoen, Bugallon, Pangasinan | 1222074 |  |  |  | 1222074 |  | Obligated | 6911 | PR#3266
Construction of Multi-purpose Gym (Phase 1) | Brgy. Camantiles, Urdaneta, Pangasinan | 500000 |  |  |  | 500000 |  | Obligated | 6911 | PR#4149
Repair/rehabilitation of Outpost | Brgy. Nacalobasaan, Urdaneta, Pangasinan | 200000 |  |  |  | 200000 |  | Obligated | 6911 | PR#4221
Repair/improvement of Day Care Center | Brgy. Pinmaludpod, Urdaneta City, Pangasinan | 300000 |  |  |  | 300000 |  | Obligated | 6911 | PR#4026
Repair/Restoration of Bengson-Yuson Bldg., Phase III | Lingayen, Pangasinan | 3751791 |  |  |  | 3751791 |  | Obligated | 6911 | PR#5360
Construction of Provincial Records and Archives Center | Capitol Compound, Lingayen, Pangasinan | 1999787 |  |  |  | 1999787 |  | Obligated | 6911 | PR#1793
Repair/rehabilitation and Construction of Deep Well Source | Namatucan,Agno, Pangasinan | 94205 |  |  |  | 94205 |  | Obligated | 8919-2 | PR#3335
Construction of 1 unit deepwell Handpump Level 1 (Sleeve converted) | Brgy. Bical Sur, Bayambang, Pangasinan | 53771 |  |  |  | 53771 |  | Obligated | 8919-2 | PR#4256
Construction of 1 unit deepwell Handpump (Level 1) | Maasin, Mangaldan, Pangasinan | 35805 |  |  |  | 35805 |  | Obligated | 8919-2 | PR#4253
Construction of 1 unit deepwell Source with Deepwell Motorpump at Manaoag Community Hospital | Manaoag, Pangasinan | 171928 |  |  |  | 171928 |  | Obligated | 8919-2 | PR#2857
Construction of 1 unit deepwell Handpump (Level 1) | Brgy. Banzal, Sta. Barbara, Pangasinan | 33622 |  |  |  | 33622 |  | Obligated | 8919-2 | PR#4255
Repair/replacement of Motorpump at Provincial Social Welfare Dev't Office | Poblacion, Lingayen, Pangasinan | 97283 |  |  |  | 97283 |  | Obligated | 8919-2 | PR#3333
Construction of 3 units deepwell (Level 1) Artesian Well | Brgy. Cabuloan, Urdaneta City | 399302 |  |  |  | 399302 |  | Obligated | 8919-2 | PR#4071
Installation of G.I. Pipes with cylinder brass Pump Assembly | Brgy. Linoc, Binmaley, Pangasinan | 40520 |  |  |  | 40520 |  | Obligated | 8919-2 | PR#4308
150 pcs. Jetmatic Pumps and GI Pipes | Distributed to different Barangays in Pangasinan | 1500750 |  |  |  | 1500300 |  | Obligated | 8919-2 | Jonemy Trdg. PR#5685
Jetmatic Pumps and GI Pipes | Distributed to different Barangays in Pangasinan | 1500000 |  |  |  | 1499520 |  | Obligated | 8919-2 | Lark Trdg. PR#5684
Jetmatic Pumps and GI Pipes | Distributed to different Barangays in Pangasinan | 1652550 |  |  |  | 1651950 |  | Obligated | 8919-2 | F & N C/S PR#5683
Equipment for various Community Hospitals |  | 10227000 |  |  |  | 10227000 |  | Obligated | 4918-1 | PR#6321
Equipment for various District Hospitals |  | 15000000 |  |  |  | 15000000 |  | Obligated | 4918-1 | PR#6787
Equipment for various District Hospitals |  | 9645000 |  |  |  | 9645000 |  | Obligated | 4918-1 | PR#6627
Equipment for various District Hospitals |  | 15115000 |  |  |  | 15115000 |  | Obligated | 4918-1 | PR#7025
Amortization of Principal and Interest |  | 55336869.38 |  |  |  | 55336869.38 |  | Obligated | 9921-1
Provision of Boulder Bank Protection along Marusay Bridge, Phase III | Brgy. Quesban, Calasiao, Pangasinan | 480303.98 |  |  |  | 480303.98 |  | Obligated | 8912-4 | PR#4560
Installation of 2 units airconditon and 1 set computer with printer at Lingayen Capital Senior Citizen Federation Bldg. | Lingayen, Pangasinan | 330891.11 |  |  |  | 330891.11 |  | Obligated | 3917 | PR#4009
Various materials for materials Testing and Quality Control Division (Tools and Equipments) | Province of Pangasinan | 1020320 |  |  |  | 1020320 |  | Obligated | 8917-3 | PR#3402
Brand New Water Well Drill Machine for Construction/Repair/Rehabilitation of various waterworks projects | Province of Pangasinan | 37000000 |  |  |  | 37000000 |  | Obligated | 8917-3 | PR#3576
Economic Development
Asphalting of Victorio-Pangascasan (Sual Coastal Road), Victoria Sec. | Alaminos City | 644000 |  |  | 100% | 643430 |  | Controlled 6-19-15 | 8917-1 | BET C/S PR#0157
Asphalting of Frank's Canteen Compound, | Lingayen, Pangasinan | 314800 |  |  | 100% | 314600 |  | Controlled 6-26-15 | 8917-1 | BET C/S PR#0212
Concreting and construction of slope protection (stone masonry) | Brgy. Poponto, Bautista, Pangasinan | 4175839 |  |  | 100% | 4170057.2 |  | 60% paid 5/2015 40% Paid-6/2015 | 8917-1 | Safeway C/S PR#0754
Construction of stone masonry | Brgy. Macalong, Asingan, Pangasinan | 3652065 |  |  | 60% | 2185596.72 |  | 60% paid 6/2015 | 8917-1 | Ranger Design PR#0398
Concreting of Tombor Road, Phase II | Binmaley, Pangasinan | 1794383 |  |  | 100% | 1786151.25 |  | 60% paid 5/2015 40% paid 6/2015 | 8917-1 | W.M. Salayog PR#0691
Construction of slope protection (Gabions) of the eroded riverbank | along Shahani Road, Brgy. Toboy, Asingan, Pangasinan | 4076795 |  |  |  | 4076795 |  | Obligated | 8917-1 | PR#0903
Proposed Concrete paving along San Jacinto-Pozorrubio Road, | Lobong Section, San Jacinto, Pangasinan | 2692805 |  |  |  | 2692805 |  | Obligated | 8917-1 | PR#0693
Concreting of Brgy. Bolaen, | Bugallon, Pangasinan | 1096696 |  |  |  | 1096696 |  | Obligated | 8917-1 | PR#3163
Improvement/blocktopping of Salingcaoet Road | Poblacion, Bugallon, Pangasinan | 2464200 |  |  |  | 2464200 |  | Obligated | 8917-1 | PR#3906
Improvement (Asphalting and blocktopping of Manambong-San Gabriell-Paragos Road | Bayambang, Pangasinan | 5274600 |  |  |  | 5274600 |  | Obligated | 8917-1 | PR#2473
Asphalting of Bantugan-Malasin Road, | Brgy. Bantugan, Pozorrubio, Pangasinan | 1762300 |  |  |  | 1762300 |  | Obligated | 8917-1 | PR#2094
Asphalting of Bical Sur Road, | Bayambang, Pangasinan | 1701800 |  |  |  | 1701800 |  | Obligated | 8917-1 | PR#3511
Asphalting of Access Road and Peripheral Area for Banca Parada 2015 | Brgy. Banaga, Bugallon, Pangasinan | 790400 |  |  |  | 790400 |  | Obligated | 8917-1 | PR#
Construction of CHB Open Canal with Concrete Barrier | Brgy. Tombor, Binmaley, Pangasinan | 1918704 |  |  |  | 1918704 |  | Obligated | 8917-1 | PR#3739
Asphalting/blocktopping of Namolan Road | Lingayen, Pangasinan | 2802300 |  |  |  | 2802300 |  | Obligated | 8917-1 | PR#4279
Asphalting Sitio Maburac Road, Brgy. Capulaan | Villasis, Pangasinan | 872900 |  |  |  | 872900 |  | Obligated | 8917-1 | PR#4965
Improvement/Asphalt repair of various farm to Market Roads | Mapandan, Pangasinan | 5932350 |  |  |  | 5932350 |  | Obligated | 8917-1 | PR#4010
Asphalting of Linmansangan-Santiago Brgy. Road | Binalonan, Pangasinan | 4876500 |  |  |  | 4876500 |  | Obligated | 8917-1 | PR#4230
Asphalting(blocktopping) of Cemetery Road, | Poblacion, Binalonan, Pangasinan | 957500 |  |  |  | 957500 |  | Obligated | 8917-1 | PR#5054
Blocktopping of Access Road going to Cemetery | Poblacion, San Nicolas, Pangasinan | 325800 |  |  |  | 325800 |  | Obligated | 8917-1 | PR#5034
Construction of Stone masonry for Protection Wall | Brgy. Caloocan Norte, Binmaley, Pangasinan | 1227040 |  |  |  | 1227040 |  | Obligated | 8917-1 | PR#5130
Reconstruction of Tumao Bridge | Bayambang, Pangasinan | 9226000 |  |  |  | 9226000 |  | Obligated | 8917-1 | PR#5757
Rehab/Improvement of Dupo Bridge | Brgy. Dupo, Binmaley, Pangasinan | 19409216 |  |  |  | 19409216 |  | Obligated | 8917-1 | PR#5564
Concreting of Sitio Cupang Road | Brgy. Umanday, Bugallon, Pangasinan | 545054 |  |  |  | 545054 |  | Paid 4-16-15 | 3917 | BET Constn PR#0704
Loans Granted to various Multi-Purpose Cooperatives and Associations |  | 1975000 |  |  |  | 1975000 |  |  | 8915
Environmental Development
Various spare parts of Dredging Machine at PEO | Lingayen, Pangasinan | 1126019.03 |  |  |  | 1126019.03 |  | Obligated | 8912-4 | PR#4558
Materials for the Extension/Improvement of Side Slope/Riverbank protection | Brgy. Talibaew, Calasiao, Pangasinan | 3137237 |  |  |  | 3137237 |  | Obligated | 8912-4 | PR#6583
Construction of drainage canal for the newly constructed nursery propagation structures | Sta. Barbara Provincial Nursery | 112187 |  |  |  | 112187 |  | Obligated | 8919 | PR#5310

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2015
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE |  |  | REFERENCES
Social Development
Repair/improvement of Farmer's Pavillion, | Sta. Barbara, Pangasinan | 2968065.38 | 10/17/2014 | 2015-05-29 | 100% | 2973554 |  | Obligated | 6911 | KJRS C/S PR#0082
Asphalting and blocktopping of RHU and Municipal Hall Compound, | Urbiztondo, Pangasinan | 1504565 | 2015-02-17 | 2015-02-18 | 100% | 1504565 |  | Obligated | 6911 | BET C/S PR#0036
Materials for use in Construction of Slope Protection along Calarian Creek, Nursery | Tebag, Sta. Barbara, Pangasinan | 1444560 | Materials Only |  | 100% | 1444560 |  | Obligated | 6911 | Goodvibe Builders PR#0614
Materials, labor, equipment and other incidentals necessary for the installation of Reinforced Concrete Culvert Pipes (RCCP)), Nursery Compound, | Tebag, Sta. Barbara, Pangasinan | 216995.8 | Labor and Materials Only |  | 100% | 216995.8 |  | Obligated | 6911 | W.M. Salayog PR#0378
396 MT Asphalt Pre-mix and 17 drums Emulsified Asphalt for the improvement of Road Network and Parking Area @ Bayambang Dist. Hospital, | Bayambang, Pangasinan | 2420650 | Materials Only |  | 100% | 2420650 |  | Obligated | 6911 | Exponetial Headway PR#2621
materials, labor, equipment and other- construction of Multi-Purpose Bldg., (Brgy. Hall), | Brgy Mapolopolo, Basista, Pangasinan | 1194505.82 | Labor and Materials Only |  | 100% | 1194505.82 |  | Obligated | 6911 | BET C/S PR#1319
Materials in concreting between Power house and Main Building @ Pozorrubio Community Hospital,an | Pozorrubio, Pangasin | 53666.5 | Materials Only |  | 100% | 53666.5 |  | Obligated | 6911 | Red Alpha PR#2234
Materials, equipment and other incidentals necessary for the construction of materials Testing and Quality Control Bldg., | Motorpool Compound, Lingayen, Pangasinan | 1633357.01 | Materials Only |  | 100% | 1633357.01 |  | Obligated | 6911 | Zota Trdg. PR#0748
Materials, labor,equipment and other incidentals, completion of Senior Citizen Bldg., and Reconstruction of Perimeter Fence with Steel Gate and Concreting of Parking Space, | Lingayen, Pangasinan | 1231834.03 | Labor and Materials Only |  | 100% | 1231834.03 |  | Obligated | 6911 | W.M. Salayog PR#4025
Materials, labor and other incidentals for the concreting of Brgy, Auditorium (Floor Slab) | Brgy. Bolaoen, Bugallon, Pangasinan | 1216521.92 | Labor and Materials Only |  | 100% | 1216521.92 |  | Obligated | 6911 | Safeway C/S PR#3266
Materials, labor, equipment and other incidentals - construction of Day Care Center | Brgy. Sawat, Urbiztondo, Pangasinan | 989621 | Materials Only |  |  | 989621 |  | Obligated | 6911 | PR#2472
Materials, labor, equipment and other incidentals - construction of Mini Grandstand with Concrete Bleachers @ Camp Tito Abat | Manaoag, Pangasinan | 1275446 | Materials Only |  |  | 1017503.25 |  | 80% as of October, 2015 | 6911 | MCB Constn PR#5785
Materials, labor, equipment and other incidentals - Rehabilitation of Repair Bay #2, Motorpool Compound | Capitol, Lingayen, Pangasinan | 6155643 | Materials Only |  |  | 6155643 |  | Obligated | 6911 | PR#1530
Materials, labor, equipment and other incidentals for the repair/rehabilitation of Maritime Bldg., | Dagupan City | 2528258 | Materials Only |  |  | 2528258 |  | Obligated | 6911 | PR#3325
10 drums E. Asphalt (SS-1), 225 MT Asphalt Pre-Mix - proposed Asphalting of Road Network & Parking Area @ OPAG Nursery | San Quintin, Pangasinan | 1381500 | Materials Only |  |  | 1381500 |  | Obligated | 6911 | PR#1792
Materials, labor and other incidentals - Construction of Storage Bldg., at Rehabilitation Center Phase 2 | Lingayen, Pangasinan | 2643052 | Materials Only |  |  | 2643052 |  | Controlled 10-14-15 | 6911 | Pangasinan New Wilson PR#1793
214 MT Asphalt Pre-mix, 10 drum E. Asphalt - Asphalting of Access Road and Parking Area at Camp Abat | Manaoag, Pangasinan | 1319830 |  |  |  | 1319830 |  | Obligated | 6911 | Exponential Headway PR#9019
Materials, labor, equipment and other incidentals for the construction of CHB Retaining Wall with Gabions @ Brgy. Tombor, | Binmaley, Pangasinan | 2310734.73 | Materials Only |  |  | 2310734.73 |  | Controlled in Oct., 2015, 100% | 6911 | PR#8339
Materials, labor, equipment and other incidentals for the construction of Reinforced Concrete Deck Girder (RCDG) Bridge in | Brgy. Bolo, San Jacinto, Pangasinan | 7046000 | Materials Only |  |  | 7046000 |  | Obligated | 6911 | PR#9252
Materials, labor, equipment and other incidentals for the construction of Slope protection and Installation of RCCP | Sitio Bogtong Silag, Brgy. Sta Cruz, San Jacinto, Pangasinan | 4106733 | Materials Only |  |  | 4106733 |  | Obligated | 6911 | PR#8978
Materials, labor, equipment and other incidentals- repair/improvement of Sison Auditorium Bldg., | Lingayen, Pangasinan | 3999989 | Materials Only |  |  | 3999989 |  | Obligated | 6911 | PR#9218
Materials, labor, equipment and other incidentals- construction of Diaz hanging footbridge | Brgy. Diaz, Bautista, Pangasinan | 5781936 | Materials Only |  |  | 5781936 |  | Obligated | 6911 | PR#10484
Materials, labor, equipment and other incidentals- completion of Brgy. Day Care Center | Brgy. Villanueva, Bautista, Pangasinan | 255014 | Materials Only |  |  | 255014 |  | Obligated | 6911 | PR#10485
Materials, labor, equipment and other incidentals- completion of Health Center Bldg. | Brgy. Anambongan, Basista, Pangasinan | 936324 | Materials Only |  |  | 936324 |  | Obligated | 6911 | PR#10991
Labor, materials, equipment and other incidentals - construction of 2-storey Building (Liga ng mga Barangay) | Poblacion, Bautista, Pangasinan | 4878209 | Materials Only |  |  | 4878209 |  | Obligated | 6911 | PR#11042
Labor, materials, equipment and other incidentals - repair/improvement of hanging bridge | NRSCC, Lingayen, Pangasinan | 1791900 | Materials Only |  |  | 1791900 |  | Obligated | 6911 | PR#11154
Labor, materials, equipment and other incidentals - proposed construction of kitchen/dining | Camp Lt. Tito Abat, Manaoag, Pangasinan | 1099372 | 2015-07-23 | 2015-07-30 | 100% | 1503159.34 |  | Obligated | 6911 | PR#11167
52 MT Asphalt Pre-Mix and 2 drums Emulsified Asphalt in Asphalting of Frank's Canteen Compound, | Lingayen, Pangasinan | 314600 | 2015-03-25 | 2015-03-25 | 100% | 314600 |  | Obligated | 8917-2 | Paid 7/2015
Materials in the repainting of various concrete bridges | 1st-6th Pangasinan Engineering Districts | 265739 | Materials Only |  | 100% | 265739 |  | Obligated | 8917-1 | PR#1204
683 MT and 21 drums Asphalt materials for the Proposed Blocktopping | Brgy. Buenlag Road, Bugallon, Pangasinan | 4055275 | 2015-05-07 | 2015-05-20 | 100% | 4129497.08 |  | Obligated | 8917-1 | BET C/S PR#0060
110 MT - Asphalt Pre-Mix, 3 drums Emulsified Asphalt for blocktopping of Cervantes Road | Brgy. Salomague Norte, Bugallon, Pangasinan | 647620 | 2015-04-08 | 2015-04-08 | 100% | 655947.7 |  | Obligated | 8917-1 | BET C/S PR#0212
150 MT Asphalt Pre-Mix, 7 drums Emulsified Asphalt in blocktopping/patching of various Poblacion Roads | Manaoag, Pangasinan | 924980 | Materials Only |  | 100% | 924980 |  | Obligated |  | BET C/S PR#0631
54 MT Asphalt Pre-mix and 3 drums Emulsified Asphalt for the asphalting of By-pass Road | Poblacion, Manaoag, Pangasinan | 339849 | Materials Only |  | 100% | 339849 |  | Obligated |  | BET C/S PR#2106
Materials for the repainting of various Provicial Steel Bridges | around the Province of Pangasinan | 189611 | Materials Only |  | 100% | 189611 |  | Obligated | 8917-1 | Red Alpha Trdg. PR#1142
141 MT Asphalt pre-mix, 6 drums emulsified Asphalt in the Asphalting | Brgy. Macalong Road, Asingan, Pangasinan | 861135 | Materials Only |  | 100% | 861135 |  | Obligated | 8917-1 | Exponential PR#1795
433 MT Asphalt Pre-mix and 15 drums Emulsified Asphalt in the asphalting | Pantal Road, Bugallon, Pangasinan | 2595185 | Materials Only |  | 100% | 2595185 |  | Obligated | 8917-1 | Exponential Headway PR#2261
807 MT Asphalt Pre-mix and 22 drums Emulsified Asphalt in the Asphalting of various streets | Bayambang, Pangasinan | 4751045 |  |  | 100% | 4751045 |  | Obligated | 8917-1 | Exponential Headway PR#2807
598 MT Asphalt Pre-mix and 21 drums Emulsified Asphalt for Asphalting various streets | Bayambang, Pangasinan | 3588200 |  |  | 100% | 3588200 |  | Obligated | 8917-1 | Exponential Headway PR#2730
Materials, labor, and other incidentals for the concreting | Brgy. Bolaen, Bugallon, Pangasinan | 1092938.85 | Labor and Materials Only |  | 100% | 1092938.85 |  | Obligated | 8917-1 | Safeway C/S PR#3163 | Paid 8/2015
414 MT Asphalt Pre-mix and 13 drums Emulsified Asphalt in the improvement/blocktopping | Salingcaoet Road, Poblacion, Bugallon, Pangasinan | 2462000 |  |  | 100% | 2462000 |  | Obligated | 8917-1 | Exponential PR#3906 | Paid 8/2015
870 MT Asphalt Pre-Mix and 34 drums Emulsified Asphalt in the improvement (Asphalting and blocktopping) | Manambong-San Gabriell-Paragos Road, Bayambang, Pangasinan | 5269910 |  |  | 100% | 5269910 |  | Obligated | 8917-1 | Exponential PR#2473 | Paid 8/2015
12 drums Emulsified Asphalt, 289 MT Asphalt Pre-Mix for asphalting | Bantugan-Malasin Road, Brgy. Bantugan, Pozorrubio, Pangasinan | 1760735 |  |  | 100% | 1760735 |  | Obligated | 8917-1 | Exponential PR#2094
278 MT Asphalt Pre-Mix and 2 drums Emulsified Asphalt in Asphalting | Bical Sur Road, Bayambang, Pangasinan | 1700290 | 2015-03-28 | 2015-03-30 | 100% | 1700290 |  | Obligated | 8917-1 | Exponential PR#3511
payment of 128 MT Asphalt Pre-Mix and 6 drums Emulsiied Asphalt in the Asphalting of Access Road and Peripheral Area for Banca Parada 2015 | Brgy. Banaga, Bugallon, Pangasinan | 789700 |  |  | 100% | 789700 |  | Obligated | 8917-1 | Exponential PR#4205
185f Asphalt Pre-Mix and 6 drums Emulsified Asphalt for use in the Asphalting/blocktopping/Patching of various barangay roads | Mapandan, Pangasinan | 1102915 |  |  | 100% | 1102915 |  | Obligated | 8917-1 | Exponential PR#3400 | Paid 8/2015
Materials, labor, equipment, and other incidentals for the construction of CHB Open Canal with Concrete Barrier | Brgy. Tombor, Binmaley, Pangasinan | 1531483.76 | Labor and Materials Only |  | 100% | 1531483.76 |  | Obligated | 8917-1 | Goodvibe Builders PR#3739 | Paid 8/2015
436 MT Asphalt Pre-Mix & 13 drums Emulsified Asphalt for Improvement/blocktopping | Sancagulis Road, Bayambang , Pangasinan | 2582890 | 2015-04-28 | 2015-04-30 | 100% | 2582890 |  | Obligated | 8917-1 | Exponential PR#5129 | Paid 8/2015
Materials, labor and other incidentals - construction of Stone masonry for Protection Wall | Brgy. Caloocan Norte, Binmaley, Pangasinan | 1223168.11 | Labor and Materials Only |  | 100% | 1223168.11 |  | Obligated |  | PR#5130 | @90%,Paid 8/2015,@100%, 9/2015
Labor, materials, equipment and other incidentals - for the coring test, ferroscanning program and structural analysis of various bridges in the | Around the Province | 682762.5 | Labor and Materials Only |  |  | 682762.5 |  | Obligated | 8917-1 | PR#7765
Materials for the construction and maintenance of Various provincial Roads and bridges | Around the Province | 85500 | Materials Only |  |  | 85500 |  | Obligated | 8917-1 | PR#5838
Materials, labor, equipment, and other incidentals for the construction of CHB Open Canal with Cross drainage | Brgy. Gayaman, Binmaley, Pangasinan | 2007116 | Labor and Materials Only |  |  | 2007116 |  | Obligated | 8917-1 | PR#8838
Materials, labor, equipment and other incidentals for the construction of concrete barrier at approach of Angalacan Brdg., | Baloling, Mapandan, Pangasinan | 142926 | Labor and Materials Only |  |  | 142926 |  | Obligated
283 MT Asphalt Pre-mix and 12 drums E. Asphalt - Asphalting/blocktopping of PAgO Road Network, Tebag Nursery | Sta. Barbara, Pangasinan | 1729300 |  |  |  | 1729300 |  | Obligated | 8917-1 | PR#9795
300 MT Asphalt Pre-mix and 18 drums E. Asphalt - Routinary Maintenance (Patching & blocktopping) of Capitol Cmpd. Road Network | Lingayen, Pangasinan | 1909200 |  |  |  | 1909200 |  | Obligated | 8917-1 | PR#9806
7 drums E. Asphalt, 162 MT Asphalt Pre-mix for the Asphalting of Road leading to PSWDO Bldg., LDH Cmpd., | Lingayen, Pangasinan | 5317800 | 8-18-2015 | 9-11-2015 |  | 5317800 |  | Obligated | 8917-1 | PR#9254
132 MT Asphalt Pre-mix, 6 drums E. Asphalt - Asphalting of Access Road at Mangaldan Dumpsite | Brgy. Banaoang, Mangaldan, Pangasinan | 812400 | [5 empty] | Obligated | 8917-1 | PR#9254
Materials, construction of various facilities for Pista'y Dayat 2015 (Tourism and Trade Fair Expo), | Stockyard Compound | 913885 |  |  | 100% | 913885 |  | Obligated |  | Red Alpha Trdg. PR#2407 | Paid 7-2015
216 sets of Heavy duty Padlock (Solex Brand) for use at Bugallon Public Market, | Bugallon, Pangasinan | 190728 |  |  | 100% | 190728 |  | Obligated |  | Red Alpha Trdg. PR#1619 | Paid 7-2015
Materials, labor and other incidentals- for the conversion of 1-Phase to 3-Phase Line and Installation of 3-15KVA DX Transformer and Electrical Service at ABC Bldg., | Alvear St., Lingayen, Pangasinan | 452080.33 | Labor and Materials Only |  | 100% | 452080.33 |  | Obligated |  |  | Paid 8-2015
Materials for construction of 3 units Housing for electric Motor Power System | San Gonzales, San Quintin | 845760 | Materials Only |  |  | 845760 |  | Obligated | PR#2122
Labor, materials, equipment and other incidentals- rehabilitation/construction of Tanggal Alola CIS | Brgy. San Roque, San Nicolas, Pangasinan | 850810.1 | Labor and Materials Only |  |  | 850810.1 |  | Obligated | 8911 | PR#8922
Labor, materials, equipment and other incidentals - Rehabilitation of Legaspi CIS, | Brgy. Legaspi, Tayug, Pangasinan | 1183100.31 | Labor and Materials Only |  |  | 1183100.31 |  | Obligated | 8911 | PR#8981
Labor, materials, equipment and other incidentals - Rehabilitation of Banding I CIS, | Brgy. Banding, Pozorrubio, Pangasinan | 1839681.54 | Labor and Materials Only |  |  | 1839681.54 |  | Obligated | 8911 | PR#9094
Labor, materials, equipment and other incidentals - Rehabilitation of Oltama SWIP, | Brgy. Oltama, Urdaneta, Pangasinan | 817681.18 | Labor and Materials Only |  |  | 817681.18 |  | Obligated | 8911 | PR#9041
Labor, materials, equipment and other incidentals - rehabilitation of San Roque CIP, | Brgy. San Jose, San Nicolas, Pangasinan | 2562370.33 | Labor and Materials Only |  |  | 2562370.33 |  | Obligated | 8911 | PR#9188
Labor, materials, equipment and other incidentals - rehabilitation of Nelintap PIS, | Brgy. Nelintap, San Carlos City | 2657590.65 | Labor and Materials Only |  |  | 2657590.65 |  | Obligated | 8911 | PR#9242
Labor, materials, equipment and other incidentals - Rehabilitation/construction of Tanggal LIS-UD Seconda, | Brgy. Salpad, San Nicolas, Pangasinan | 817457.76 | Labor and Materials Only |  |  | 817457.76 |  | Obligated | 8911 | PR#9293
Labor, materials, equipment and other incidentals - rehabilitation of Mantacdang CIS, | Brgy. Mantacdang, San Quintin, Pangasinan | 1622734.27 | Labor and Materials Only |  |  | 1622734.27 |  | Obligated | 8911 | PR#9291
Labor, materials, equipment and other incidentals - construction of Muelang CIS, | Brgy. Capulaan, Balungao, Pangasinan | 1436386.53 | Labor and Materials Only |  |  | 1436386.53 |  | Obligated | 8911 | PR#9355
Labor, materials, equipment and other incidentals - rehabilitation of Don Joaquin Dam, | Brgy. Capulaan, Balungao, Pangasinan | 766451.45 | Labor and Materials Only |  |  | 766451.45 |  | Obligated | 8911 | PR#9356
Labor, materials, equipment and other incidentals - construction/installation of 14 units STWIP | various barangays and munipalities of Pangasinan | 3846868.62 | Labor and Materials Only |  |  | 3846868.62 |  | Obligated | 8911 | PR#9437
Labor, materials, equipment and other incidentals - rehabilitatio of Ban-Ao CIS | Brgy. Bantocaling, Mangatarem, Pangasinan | 3562035.84 | Labor and Materials Only |  |  | 3562035.84 |  | Obligated | 8911 | PR#9438
Labor, materials, equipment and other incidentals - rehabilitation of Lobong-Mambog CIS, | Sitio Mambog, Brgy. Lobong, San Jacinto, Pangasinan | 662800.04 | Labor and Materials Only |  |  | 662800.04 |  | Obligated | 8911 | PR#9529
Labor, materials, equipment and other incidentals - construction of Torre-Niog II, | Brgy. CBN, Mangatarem, Pangasinan | 1314898.26 | Labor and Materials Only |  |  | 1314898.26 |  | Obligated | 8911 | PR#9530
Labor, materials, equipment and other incidentals - construction of Matico CIS, | Brgy. Sioasio West, Sual, Pangasinan | 2529946.77 | Labor and Materials Only |  |  | 2529946.77 |  | Obligated | 8911 | PR#9601
Labor, materials, equipment and other incidentals - rehabilitation of San Felipe CIS, | Brgy. Nangalisan, Infanta, Pangasinan | 2398248.87 | Labor and Materials Only |  |  | 2398248.87 |  | Obligated | 8911 | PR#9600
Labor, materials, equipment and other incidentals - construction of Nangalisan CIS, | Brgy. Flores, Umingan, Pangasinan | 2290776.86 | Labor and Materials Only |  |  | 2290776.86 |  | Obligated | 8911 | PR#9694
Labor, materials, equipment and other incidentals - construction of Tanggal Daldalayap, | Brgy. Sobol, San Nicolas, Pangasinan | 1722358.55 | Labor and Materials Only |  |  | 1722358.55 |  | Obligated | 8911 | PR#9769
Labor, materials, equipment and other incidentals - construction/installation of 11 units STWIP (Open Well) | various barangays and municipalites of Pangasinan | 2248093.2 | Labor and Materials Only |  |  | 2248093.2 |  | Obligated | 8911 | PR#9812
Labor, materials, equipment and other incidentals - rehabilitation of Lucero CIS | Brgy. Bogtong Bolo, Mangatarem, Pangasinan | 2516898.86 | Labor and Materials Only |  |  | 2516898.86 |  | Obligated | 8911 | PR#9813
Labor, materials, equipment and other incidentals - rehabilitation | Brgy. Esperanza , Sison, Pangasinan | 1550041.47 | Labor and Materials Only |  |  | 1550041.47 |  | Obligated | 8911 | PR#9948
Labor, materials, equipment and other incidentals - rehabilitation of Darawey PIS, | Brgy. Darawey, Bayambang, Pangasinan | 393259.11 | Labor and Materials Only |  |  | 393259.11 |  | Obligated | 8911 | PR#
Labor, materials, equipment and other incidentals - rehabilitation of Malimpued CIS, | Brgy. Binmeckeg, Sison, Pangasinan | 1776704.94 | Labor and Materials Only |  |  | 1776704.94 |  | Obligated | 8911 | PR#10112
Labor, materials, equipment and other incidentals - rehabilitation of Inmalog CIS, | Brgy. Inmalog Norte, San Fabian, Pangasinan | 851952.5 | Labor and Materials Only |  |  | 851952.5 |  | Obligated | 8911 | PR#10201
Labor, materials, equipment and other incidentals - rehabilitation of Malicdem CIS, | Brgy. Sapang, Sta. Barbara, Pangasinan | 1283146.68 | Labor and Materials Only |  |  | 1283146.68 |  | Obligated | 8911 | PR#10202
Labor, materials, equipment and other incidentals - rehabilitation of Sapang CIS, | Brgy. Sapang, Sta. Barbara, Pangasinan | 1988570.63 | Labor and Materials Only |  |  | 1988570.63 |  | Obligated | 8911 | PR#10288
Labor, materials, equipment and other incidentals - rehabilitation of Tanggal United Principal, | Brgy. Bachelor East, Natividad, Pangasinan | 813407.34 | Labor and Materials Only |  |  | 813407.34 |  | Obligated | 8911 | PR#10376
Labor, materials, equipment and other incidentals - rehabilitation/construction of Ancheta CIS, | Brgy. Coldit, Asingan, Pangasinan | 2772903.58 | Labor and Materials Only |  |  | 2772903.58 |  | Obligated | 8911 | PR#10366
Labor, materials, equipment and other incidentals - rehabilitation/construction of Masa Florenda SWIP, | Brgy. San Andres, Balungao, Pangasinan | 2705958.73 | Labor and Materials Only |  |  | 2705958.73 |  | Obligated | 8911 | PR#10351
Labor, materials, equipment and other incidentals - rehabilitation/construction of Pag-asa CIS, | Brgy. Arzadon, San Manuel, Pangasinan | 2612666.93 | Labor and Materials Only |  |  | 2612666.93 |  | Obligated | 8911 | PR#10367
Labor, materials, equipment and other incidentals - construction of Tanggal Cadaanan/Cabaruan, | Brgy. Sta. Maria East | 1137142.27 | Labor and Materials Only |  |  | 1137142.27 |  | Obligated | 8911 | PR#10377
Labor, materials, equipment and other incidentals - rehabilitation/construction of Lawak CIS, | Brgy. Lawak, Tayug, Pangasinan | 2887376.59 | Labor and Materials Only |  |  | 2887376.59 |  | Obligated | 8911 | PR#10401
Labor, materials, equipment and other incidentals - rehabilitation/construction of Carosalesan II CIS, | Brgy. Carosalesan, Umingan, Pangasinan | 2323991.03 | Labor and Materials Only |  |  | 2323991.03 |  | Obligated | 8911 | PR#10400
Various materials, construction/installation of 20 units STWIP in various barangays/municipalities/cities | San Carlos, Bugallon, and Aguilar, Pangasinan | 4762382 | Materials Only |  |  | 4762382 |  | Obligated | 8911 | PR#12244
Various materials, construction/installation of 17 units STWIP in various barangays/municipalities | Mangaldan, Manaoag, Sn. Fabian, San Jacinto, Laoac, Pangasinan | 4048024.7 | Materials Only |  |  | 4048024.7 |  | Obligated | 8911 | PR#12234
Various materials, construction/installation of 15 units STWIP | various barangays in Bautista, Pangasinan | 3571786.5 | Materials Only |  |  | 3571786.5 |  | Obligated | 8911 | PR#11262
Various materials, equipment and other incidentals for the construction/installation of 17 units STWIP | various barangays and municipalities of Urbiztondo and Basista, Pangasinanj | 4048024.7 | Materials Only |  |  | 4048024.7 |  | Obligated | 8911 | PR#11337
Various materials, construction/installation of 20 units STWIP in various barangays and municipalities | Bayambang, San Carlos City, and Malasiqui, Pangasinan | 4762382 | Materials Only |  |  | 4762382 |  | Obligated | 8911 | PR#11443
Various materials, equipment and other incidentals for the construction/installation of 18 units STWIP | various barangays of Urbiztondo and Basista, Pangasinan | 4286143.8 | Materials Only |  |  | 4286143.8 |  | Obligated | 8911 | PR#11684
Various materials, construction/installation of 19 units STWIP in various barangays and municipalities | Agno, Bolinao, Sual, Dasol and Alaminos, Pangasinan | 4524262.9 | Materials Only |  |  | 4524262.9 |  | Obligated | 8911 | PR#11840
Various materials, construction/installation of 16 units STWIP in various barangays and municipalities | Alcala, Binalonan and Pozorrubio, Pangasinan | 3809905.6 | Materials Only |  |  | 3809905.6 |  | Obligated | 8911 | PR#11905
Various materials, construction/installation of 16 units STWIP in various barangays and municipalities | Sison, Sto. Tomas, Villasis, Sta. Maria, San Quintin, Umingan, San Nicolas and Tayug, Pangasinan | 3809905.6 | Materials Only |  |  | 3809905.6 |  | Obligated | 8911 | PR#11758
Materials for construction of 2 units Artesian Well | Brgy. Pangangaan, Umingan, Pangasinan | 55478 | Materials Only |  | 100% | 55478 |  | Obligated | 8919-2 | Red Alpha Trdg PR#1514 | Paid 7-2015
Materials, labor, equipment and other necessary for the construction of 1 unit Deepwell Handpump | Nalsian - Bacayao, Calasiao, Pangasinan | 112777.19 | Labor and Materials Only |  | 100% | 112777.19 |  | Obligated | 8919-2 | Safeway C/S PR#0247 | Controlled 9-1-15
Materials in the construction of Water system @ Basilica de Manaoag, | Manaoag, Pangasinan | 64735 | Materials Only |  | 100% | 64735 |  | Obligated | 8919-2 | Legacy One Entp. PR#2447 | Controlled 7-2-15
Materials for the installation of G.I. Pipes with cylinder brass Pump Assembly | Brgy. Linoc, Binmaley, Pangasinan | 40445 | Materials Only |  | 100% | 40445 |  | Obligated | 8919-2 | Winmark PR#4308 | Paid 7-2015
150 pcs. Jetmatic Pumps and GI Pipes |  | 1500300 | Materials Only |  | 100% | 1500300 |  | Obligated | 8911 | Jonemy Trdg. PR#5685
Jetmatic Pumps and GI Pipes |  | 1499520 | Materials Only |  | 100% | 1499520 |  | Obligated |  | Lark Trdg. PR#5684
Jetmatic Pumps and GI Pipes |  | 1651950 | Materials Only |  | 100% | 1651950 |  | Obligated |  | F & N C/S PR#5683
Materials, labor and other incidentals - construction of 1 unit deepwell handpump (Level 1) with cylinder Brass Assembly | San Julian, Malasiqui, Pangasinan | 270347.24 | Labor and Materials Only |  |  | 270347.24 |  | Obligated | 8919-2 | PR#2569
Materials, labor and other incidentals - construction of 1 unit deepwell handpump Level 1 (sleeve converted) | Samangsur, Bolinao, Pangasinan | 200877.64 | Labor and Materials Only |  |  | 200877.64 |  | Obligated | 8919-2 | PR# 2626
Materials, labor and other incidentals - construction of 1 unit deepwell handpump with cylinder Brass (Level 1 - dugwell w/ culvert) | Brgy. Amagbagan, Sison, Pangasinan | 341028.41 | Labor and Materials Only |  |  | 341028.41 |  | Obligated | 8919-2 | PR# 2777
Materials, labor and other incidentals - construction of 1 unit deepwell handpump Level 1 (sleeve converted) | Brgy. Sapang, Manaoag, Pangasinan | 274456.56 | Labor and Materials Only |  |  | 274456.56 |  | Obligated | 8911 | PR# 2731
Materials, labor and other incidentals - construction of 1 unit deepwell handpump Level 1 with cylinder brass assembly | Brgy. Sugcong, Pozorrubio, Pangasinan | 341028.41 | Labor and Materials Only |  |  | 341028.41 |  | Obligated | 0 | PR#2664
Various materials for the Installation of Motorpump with Pressure tank At Regional Trial Court, | San Carlos City, Pangasinan | 39402 | Materials Only |  |  | 39402 |  | Obligated | 0 | PR# 3716
1000 pcs jetmatic pump |  | 3525000 | Materials Only |  |  | 3525000 |  | Obligated | 8919-2 | PR#9785
Materials for construction of Water System for 3rd, 4th floor of Capitol Resort Hotel | Lingayen, Pangasinan | 60119 | Materials Only |  |  | 60119 |  | Obligated | 8919-2 | PR#10062
various materials for the construction of 1 unit Artesian Well, | San Vicente, Calasiao, Pangasinan | 21500 | Materials Only |  |  | 21500 |  | Obligated | 8919-2 | PR#11640
Materials, labor and other incidentals for the upgrading/Improvement of PPH, | San Carlos City | 33870359 | Labor and Materials Only |  |  | 33870359 |  | Obligated | 4918-2 | PR#7206
Materials, labor and other incidentals for upgrading/improvement/rehabilitation of WPDH, | Alaminos City | 2812987.51 | Labor and Materials Only |  |  | 2812987.51 |  | Obligated | 4918-2 | PR#7059
Materials, labor and other incidentals for the construction of covered Pathway from Dietary building to Main Bldg. and Improvement of various Rooms/Area of Hospital Main Bldg for Level 2 @ EPDH, | Tayug, Pangasinan | 1872042 | Labor and Materials Only |  |  | 1872042 |  | Obligated | 4918-2 | PR#7273
Materials, labor and other incidentals for the Upgrading/Improvement/Rehabilitation of Lingayen Dist. Hosp | Lingayen, Pangasinan | 19862049.95 | Labor and Materials Only |  |  | 19862049.95 |  | Obligated | 4918-2 | PR#6889
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Urdaneta Dist. Hospital | Urdaneta, Pangasinan | 6244026 | Labor and Materials Only |  |  | 6244026 |  | Obligated | 4918-2 | PR#7279
Materials, labor, and other incidentals for the upgrading/ Imrprovement of Bayambang Dist. Hospital | Bayambang, Pangasinan | 3716574.12 | Labor and Materials Only |  |  | 3716574.12 |  | Obligated | 4918-2 | PR#7258
Materials, labor and other incidentals for the upgrading/improvement of Mangatarem District Hospital | Mangatarem, Pangasinan | 2618545 | Labor and Materials Only |  |  | 2618545 |  | Obligated | 4918-2 | PR#7060
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Bolinao Com. Hospital | Bolinao, Pangasinan | 3139977 | Labor and Materials Only |  |  | 3139977 |  | Obligated | 4918-2 | PR#6888
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Mapandan Com. Hospital | Mapandan, Pangasinan | 4050000 | Labor and Materials Only |  |  | 4050000 |  | Obligated | 4918-2 | PR#7148
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Manaoag Com. Hospital | Manaoag, Pangasinan | 6676330 | Labor and Materials Only |  |  | 6676330 |  | Obligated | 4918-2 | PR#7007
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Umingan Com. Hospital | Umingan, Pangasinan | 4154395 | Labor and Materials Only |  |  | 4154395 |  | Obligated | 4918-2 | PR#7084
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Asingan Com. Hospital | Asingan, Pangasinan | 1496167 | Labor and Materials Only |  |  | 1496167 |  | Obligated | 4918-2 | PR#7259
Materials, labor, and other incidentals for the upgrading/Improvement/rehabilitation of Dasol Com. Hospital | Dasol, Pangasinan | 3690431 | Labor and Materials Only |  |  | 3690431 |  | Obligated | 4918-2 | PR#6962
Materials, labor, and other incidentals for the upgrading/Improvement of Pozorrubio Com. Hospital | Pozorrubio, Pangasinan | 3219748 | Labor and Materials Only |  |  | 3219748 |  | Obligated | 4918-2 | PR#6963
Economic Development
Labor, equipment and other incidentals for the concreting of Sitio Cristobal Farm to Market Road, | Brgy. Cabilocaan, Calasiao, Pangasinan | 3262651.97 | Labor and Materials Only |  | 100% | 3262651.97 |  | Obligated | 6911 | MCB C/S PR#2259
Materials, labor, equipment, and other incidentals for the construction of Farm to Market Road (Bolo-Sta. Cruz Road), | Brgy. Bolo, San Jacinto, Pangasinan | 1635969 | Labor and Materials Only |  |  |  |  | Obligated | 6911 | PR#9018
104 MT Asphalt Pre-Mix and 5 drums Emulsified Asphalt for Asphalting of Victorio-Pangascasan (Sual Coastal Road), | Victoria Sec., Alaminos City | 643430 |  |  | 100% | 643430 |  | Obligated | 8917-1 | BET C/S PR#0157
Materials, labor and other incidentals for the concreting of Roadline Leading to Umbrella Rock, | Agno, Pangasinan | 1979620 | Labor and Materials Only |  |  | 295755.97 |  | Obligated | 8918 | Ranger Design PR#6308 | Paid 8/2015
Materials, labor and other incidentals for proposed concrete paving | Brgy. Balingasay Rd., Bolinao, Pangasinan | 12010567 | Labor and Materials Only |  |  | 1799861.68 |  | Obligated | 8918 | Alcel Constn PR#6093 | Paid 8/2015
Materials, labor and other incidentals for proposed concreting | Brgy. Tara, Bolinao, Pangasinan | 12509813 | Labor and Materials Only |  |  | 1871100 |  | Obligated | 8918 | Safeway C/S PR#6214 | Paid 8/2015
Various Construction equipment |  | 92470000 | Materials Only |  |  |  |  | Obligated | 8917-3 | PR#8283
327 MT Asphalt Pre-mix and 14 drums e. Asphalt - Asphalting of Road Network at OPAG Cmpd., | Sta. Barbara, Pangasinan | 2000000 | [5 empty] | Obligated | 8917-1 | PR#9237
Materials, labor, equipment and other incidentals for the construction of slope Protection, | Brgy. Bañaga, Bugallon, Pangasinan | 1594926 | Labor and Materials Only |  |  |  |  | Obligated | 8917-1 | PR#9183
Materials, labor, equipment and other incidentals- Improvement/Widening/Concreting of farm to market road, | Brgy. Anonang, San Fabian, Pangasinan | 4152556 | Labor and Materials Only |  |  |  |  | Obligated | 8917-1 | PR#0856
Asphalting/blocktopping of various roads, | Mangaldan, Pangasinan | 5037600 | [5 empty] | Obligated | 8917-1 | PR#10878
Materials, labor and other incidentals - New construction of ARAGAAG Bridge (to replace old existing Bridge) - 1, | Asingan, Pangasinan | 39288252 | Labor and Materials Only |  |  |  |  | Obligated | 8917-1 | PR#7920
Materials, labor and other incidentals - New Construction of 2 - BARREL RCBC (to replace old RCDG) , | San Manuel, Pangasinan | 2882674 | Labor and Materials Only |  |  |  |  | Obligated | 8917-1 | PR#7898
Materials, labor and other incidentals - New Construction of 2 - BARREL RCBC (to replace old CASANTIAGOAN RCDG) , | San Manuel, Pangasinan | 5993520 | Labor and Materials Only |  | 15% | 897606.72 |  | Obligated | 8917-1 | GoodVibe Builders PR#2418 | Paid 8/2015
Materials, labor, equipment and other incidentals for the improvement/rehabilitation of Bued-Ambonao Road, | Calasiao, Pangasinan | 2732634.1 | Labor and Materials Only |  | 70.09% | 1915303.24 |  | Obligated | 8917-1 | Ranger Design PR#2031 | Paid 8/2015, 70.090% Controlled 10-14-15
Materials, labor, equipment and other incidentals for the Improvement/rehabilitation of Mapandan - Urdaneta Road, | Mapandan, Pangasinan | 29926788 | Labor and Materials Only |  | 54.4% | 16281369.74 |  | Obligated
Materials, labor, equipment and other incidentals for the concreting of Parian - Bantocaling - Bantay Road, | Mangatarem, Pangasinan | 7428060.55 | Labor and Materials Only |  | 59.78% | 4440717.44 |  | Obligated |  | @15%, Paid 8-2015,@59.783% Controlled ,9-18-15
Materials, labor, equipment and other incidentals for the Improvement/rehabilitation of Mapandan - Banaoang Road, | Sta. Barbara, Pangasinan | 2215000 | Labor and Materials Only |  | 100% | 2215000 |  | Obligated |  | Ranger Design PR#2572
Materials, labor, and other incidentals for the concreting of Olo - Naguilayan Road, | Mangatarem, Pangasinan | 16078309.2 | Labor and Materials Only |  | 15% | 2411746.38 |  | Obligated | 8917-1 | Alcel Const'n PR#2734 | 15% Paid 8/2015,@50.98%, Controlled 10-6-15
Materials, labor, equipment and other incidentals for the concreting of Urdaneta - Asingan - Tayug Road, | Ariston East and West, Asingan, Pangasinan | 16274141 | Labor and Materials Only |  | 15% | 2438994.24 |  | Obligated |  | MCB C/S PR#1883 | 15% Paid 8/2015,@50%, Controlled 10-6-15
219 MT Asphalt Pre-mix 7 drums E. Asphalt - Asphalting of Dangley- Aloleng - Mamio Road, | Agno, Pangasinan | 1305300 | [5 empty] | Obligated
1524 MT Asphalt Pre-mix, 66 drums E. Asphalt - Asphalting of Rajal - Esmeralda Road, | Balungao, Pangasinan | 9332400 | 2014-11-21 | 2015-02-07 | 100% | 9332400 |  | Obligated |  | Exponential PR#8240
2547 MT Asphalt Pre-mix and 95 drums E. Asphalt - Improvement/Rehabilitation of Bani - Mabini Road, | Bani and Mabini, Pangasinan | 15376500 | [5 empty] | Obligated |  | Exponential Headway PR#8250
1642 MT Asphalt Pre-mix and 71 drums E. Asphalt - Improvement/Rehabilitation of Poponto - Villanueva Road, | Bautista, Pangasinan | 10053400 | [5 empty] | Obligated |  | Exponential Headway PR#8226
1150 MT Asphalt Pre-mix and 50 drums E. Asphalt - Improvement/rehabilitation of Bayambang - Urbiztondo Road, | Bayambang, Pangasinan | 7045000 | [5 empty] | Obligated |  | Exponential Headway PR#6890
1398 MT Asphalt Pre-mix and 61 drums E. Asphalt - Improvement/rehabilitation of Binalonan-San Manuel Road, | Binalonan, Pangasinan | 8567400 | [5 empty] | Obligated |  | Exponential PR#6891
1806 MT Asphalt Pre-mix, 79 drums E. Asphalt Asphalting of Burgos-Iliw-Iliw Road, | Burgos, Pangasinan | 11070600 | [5 empty] | Obligated |  | Exponential Headway PR#6965
690 MT Asphalt Pre-mix, 30 drums E. Asphalt - Asphalting of Patar - Capandanan Road, | Mabini, Pangasinan | 4227000 | [5 empty] | Obligated |  | Exponential Headway PR#7010
621 MT Asphalt Pre-mix, 27 drums E. Asphalt - Improvement/rehabilitation of Mapandan-Urdaneta Road, | Manaoag, Pangasinan | 3804300 | [5 empty] | Obligated
1518 MT Asphalt Pre-mix and 66 drums E. Asphalt - Improvement/rehabilitation of Pao-Pozorrubio Road, | Manaoag, Pangasinan | 9299400 | [5 empty] | Obligated |  | Exponential Headway PR#7062
621 MT Asphalt Pre-mix, and 19 drums E. asphalt - blocktopping of Licsi-Manaoag Sugar Central Road, | Manaoag, Pangasinan | 3689100 | [5 empty] | Obligated |  | Exponential Headway PR#7149
1719 MT Asphalt Pre-mix and 52 drums E. Asphalt - Improvement/rehabiitation (blocktopping) of Mapandan-Manaoag Road, | Mapandan, Pangasinan | 10203300 | [5 empty] | Obligated |  | Exponential Headway PR#7177
806 MT Asphalt Pre-mix and 35 drums E. Asphalt - Improvement/blocktopping of Mapandan-Urdaneta road, | Mapandan, Pangasinan | 4937000 | [5 empty] | Obligated |  | Exponential Headway PR#7207
1380 MT Pre-mix and 60 drums E. Asphalt - Improvement/rehabilitation of San Jacinto-Pozorrubio Road, | Pozorrubio, Pangasinan | 8454000 | [5 empty] | Obligated |  | Exponential Headway PR#7208
966 MT Asphalt Pre-mix and 42 drums E. Asphalt - Improvement/rehabilitation of Pozorrubio-Sogcong Road, | Pozorrubio, Pangasinan | 5917800 | [5 empty] | Obligated |  | Exponential Headway PR#7283
966 MT Asphalt Pre-mix and 42 drums E. Asphalt - Improvement/rehabilitation of Salvacion-San Vicente Road, | Rosales, Pangasinan | 5917800 | [5 empty] | Obligated |  | Exponential Headway PR#7283
1725 MT Asphalt Pre-mix and 75 drums E. Asphalt -Asphalting of Urbiztondo-San Carlos Road, | San Carlos City | 10567500 | [5 empty] | Obligated |  | Exponential Headway PR#7331
690 MT Asphalt Pre-mix, and 30 drums E. Asphalt - Improvement/rehabilitation of Asingan-San Manuel-Agno Gorge Road, | San Manuel, Pangasinan | 4227000 | [5 empty] | Obligated |  | Exponential Headway PR#7389
414 MT Asphalt and 14 drums E. Asphalt - Improvement/rehabilitation of Poblacion Natividad-Salud-Sta. Maria Road, | Natividad,Pangasinan | 2478600 | [5 empty] | Obligated |  | Exponential Headway PR#7390
380 MT Asphalt Pre-mix and 17 drums E. Asphalt - Improvement/rehabilitation of Batakil-Sison Road, | Sison, Pangasinan | 2334800 | [5 empty] | Obligated |  | Exponential PR#7434
828 MT Asphalt Pre-mix, 36 drums E. Asphalt - Asphalting of Cabatuan-Nampalcan Road, | Umingan, Pangasinan | 5072400 | [5 empty] | Obligated |  | Exponential Headway PR#7438
2422 MT Asphalt Pre-mix, 104 drums E. Asphalt - Asphalting of San Juan-Resurreccion Road, | Umingan, Pangasinan | 14818600 | [5 empty] | Obligated |  | Exponential Headway PR#7464
828 MT Asphalt Pre-mix, 36 drums E. Asphalt - Asphalting of Villabantog-Calitlitan Road, | Umingan, Pangasinan | 5072400 | [5 empty] | Obligated |  | Exponentia PR#7465
472 MT Asphalt Pre-mix, 21 drums E. Asphalt - Asphalting of Cadamortisan-Diket Road, | Umingan, Pangasinan | 2898400 | [5 empty] | Obligated |  | 472 MT Asphalt Pre-mix, 21 drums E. Asphalt - Asphalting of Cadamortisan-Diket Road, Umingan, Pangasinan
1472 MT Asphalt Pre-mix and 64 drums E. Asphalt - Improvement/rehabilitation of Nancalobasaan-Cabalitian Road, | Umingan, Pangasinan | 9017600 | [5 empty] | Obligated |  | Exponential Headway PR#7598
1035 MT Asphalt Pre-mix and 45 drums E. Asphalt - Improvement/rehabilitation of Urbiztondo-Bayambang Road, | Urbiztondo, Pangasinan | 6340500 | [5 empty] | Obligated |  | Exponential Headway PR#7667
1104 MT Asphalt Pre-mix and 48 drums E. Asphalt - Improvement/rehabilitation of Urdaneta-Manaoag Rd., San Vicente, | Urdaneta, Pangasinan | 6763200 | [5 empty] | Obligated |  | Exponential Headway PR#7668
621 MT Asphalt Pre-mix and 27 drums E. Asphalt - Improvement/rehabilitation of Urdaneta-Asingan Road, via Calepaan, | Urdaneta City, Pangasinan | 3804300 | [5 empty] | Obligated |  | Exponential PR#7709
690 MT Asphalt Pre-mix and 30 drums E. Asphalt - Improvement/rehabilitation of Urdaneta-Cili Jct. Road, | Urdaneta City, Pangasinan | 4227000 | [5 empty] | Obligated |  | PR#7710
1265 MT Asphalt Pre-mix, 39 drums E. Asphalt - blocktopping of Tayug - Natividad Road (with Exemptions), | Natividad, Pangasinan | 7519100 | [5 empty] | Obligated |  | Exponential Headway PR#7711
Materials, labor, equipment and other incidentals for the construction of concrete barrier at approach of Nilombot Bridge, | Nilombot, Mapandan, Pangasinan | 114425 | Labor and Materials Only |  |  |  |  | Obligated | 8917-1 | PR#8229
Materials, labor, equipment, and other incidentals for the concreting of Camanang Road, | Urdaneta City, Pangasinan | 1215459 | Labor and Materials Only |  |  |  |  | Obligated | 8917-1 | PR#8910
236 MT Asphalt Pre-mix and 7 drums E. Asphalt - blocktopping of Everlasting St., | Mapandan, Pangasinan | 1397550 | [5 empty] | Obligated |  |  | Controlled 10-16-15
Asphalting materials for Asphalting of Cabarangan Rd., | Umingan, Pangasinan | 861900 | [5 empty] | Obligated | 8917-1 | PR#0904
138 MT Asphalt Pre-mix and 6 drums E. Asphalt - Asphalting of Teacher's Village Road, | Brgy. Zone VIII, Bayambang, Pangasinan | 845400 | [5 empty] | Obligated | 8917-1 | PR#9219
Various materials for the construction of Stone Protection (Stone Masonry) and concrete pouring of road shoulder along Mapandan-Urdaneta Road, | Matulong Section, Manaoag, Pangasinan | 608350 | [5 empty] | Obligated | 8917-1 | PR#9253
483 MT Asphalt Pre-mix and 15 drums E. Asphalt - proposed Patching and blocktopping of Brgy. Road and Brgy. San Isidro Noter, | Binmaley, Pangasinan | 2869935 | 2015-08-06 | 2015-08-14 | 100% | 2869935 |  | Obligated | 8917-1 | Exponential PR#2146 | Controlled 10-16-15
329 MT - Asphalt Pre-mix, 101 drums E. Asphalt - Asphating/blocktopping/patching of Baligayan - | Labuan Rd., San Quintin, Pangasinan | 1953500 | [5 empty] | Obligated | 8917-1 | PR#3225
2 drums E. Asphalt and 75 MT Asphalt Pre-mix - Improvement(blocktopping) of Lokeb Sur Road, | Malasiqui, Pangasinan | 441300 | [5 empty] | Obligated | 8917-1 | PR#3167
115 MT Asphalt Pre-mix, 5 drums E. Asphalt - Asphalting of Poblacion - Cabaruan Rd., Burgos, Pangasinan |  | 704500 | [5 empty] | Obligated | 8917-1 | PR#3219
17 drums Emulsified asphalt and 465 MT Asphalt pre-mix in Asphalting/blocktopping of | Namolan Road, Lingayen, Pangasinan | 2799805 | 2015-04-23 | 2015-04-28 | 100% | 2799805 |  | Obligated | 8917-1 | Exponential PR#4279 | Paid 8/2015
143 MT Asphalt Pre-Mix & 6 drums Emulsified Asphalt in Asphalting Sitio Maburac Road, | Brgy. Capulaan, Villasis, Pangasinan | 872125 | 2015-04-01 | 2015-04-18 | 100% | 872125 |  | Obligated | 8917-1 | Exponential PR#4965 | Paid 8/2015
976.5 MT Emulsified Asphalt and 39 drums Asphalt Pre-Mix in the improvement/Asphalt repair of various farm to Market Roads | Municipality of Mapandan | 5927077.5 |  |  | 100% | 5927077.5 |  | Obligated | 8917-1 | Exponential Headway PR#4010 | Paid 8/2015
Materials, labor, equipment and other incidentals for the construction of Pototan Bridge, | Binmaley, Pangasinan | 5986845.9 | Labor and Materials Only |  | 90% | 5388161.31 |  | Obligated | 8917-1 | Zota Trdg. PR#3286 | Controlled 8-4-15,90% 9-18-15
Labor, materials, equipment and other incidentals- rehabilitation/construction of Carosalesan I CIS, | Brgy. Carosalesan, Umingan, Pangasinan | 1632331.08 | Labor and Materials Only |  |  |  |  | Obligated | 8911 | PR#8912
Amortization of Principal and Interest on Loan to LBP |  | 122003424.49 |  |  |  | 122003424.49 |  | Obligated
Environmental Development
40000 pcs. Mangrove propagules ( Bakawan Babae, Bakawan Lalaki, Baowan Bato) propagation of Mangrove, Bolinao Prov'l Mangrove Nursery, Arnedo, 3rd Qtr, CY 2015 | Bolinao, Pangasinan | 60000 | Materials Only |  |  |  |  | Obligated | PR#7698 | 8919
Various seeds and farm inputs for fruit and forest seedlings propagation at OPAG Field Station | Sta. Barbara, Pangasinan | 381300 | Materials Only |  |  |  |  | Obligated | PR#7699 | 8919
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO |  |  |  |  | AMADO T. ESPINO, JR.
Provincial Accountant |  |  |  |  | Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the Quarter JULY - SEPTEMBER, CY 2015
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 31714626.15 | 74000794.35 |  |  |  | 105715420.5
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 45024785.74 |  |  |  | 45024785.74
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 31714626.15 | 119025580.09 | 0 | 0 | 0 | 150740206.24
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies |  | 259400 |  |  |  | 259400
Office Supplies |  | 60550 |  |  |  | 60550
Repair of Evacuation Center | [5 empty] | 0
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses | 1176000 | 34430231 |  |  |  | 35606231
Traveling Expense |  | 76910.28 |  |  |  | 76910.28
Training Expense | [5 empty] | 0
IT Equipment & Software |  | 185302.5 |  |  |  | 185302.5
Motor Vehicles |  | 4894000 |  |  |  | 4894000
Other Machineries and Equipment |  | 2076000 |  |  |  | 2076000
Watercrafts |  | 6552920
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment | [5 empty] | 0
Gasoline, Oil, Lubricants |  | 606067.63 |  |  |  | 606067.63
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. |  | 22842547 |  |  |  | 22842547
Repair & Maintenance-Motor Vehicles |  | 67200 |  |  |  | 67200
Total Utilization | 1176000 | 72051128.41 | 0 | 0 | 0 | 73227128.41
Unutilized Balance | 30538626.15 | 46974451.68 | 0 | 0 | 0 | 77513077.83
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO, CPA
Provincial Accountant

## sef
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending September 30, 2015
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 141606203.89
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
83965041.97
Capital Outlay
42552178.28
Financial Expenses
-0-
Sub-total |  |  |  | 126517220.25
Balance |  |  |  | 15088983.64
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## SCF
FDP Form 9 - Statement of Cash Flow
(COA Form)
Province of Pangasinan
STATEMENT OF CASH FLOWS
General Fund
For the Third Quarter Ending September 30, 2015
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers | 19410660.93
|  | Share from Internal Revenue Collections | 607436973
|  | Receipts from sale of goods or services | 219981832.18
|  | Interest Income | 920347.69
|  | Other Receipts | 41240744.17
|  | Total Cash Inflow | 888990557.97
Cash Outflows:
Payments to -
|  | To suppliers/creditors | 423875166.53
|  | To employees | 204612850.21
|  | Interest Expenses | 7434614.9
|  | Other Disbursements | 625707
|  | Total Cash Outflow | 636548338.64
| Cash Provided by (Used In) |  |  | 252442219.33
Cash Flows from Investing Activities:
Cash Inflows:
Sale of Property, Plant and Equipment and Public
Infrastracture
Sale of Debt Securities of other Entities
|  | Collection of Principal on Loans to other Entities | 1723875
|  | Total Cash Inflow | 1723875
Cash Outflows:
|  | Purchase of Property, Plant and Equipment and Public | 126404482
Infrastracture
Grant/Loans to Other Entities
|  | Total Cash Outflow | 126404482
| Cash Provided by (Used In) |  |  | -124680607
Cash Flows from Financing Activities:
Cash Inflows:
Issuance of Debt Securities
|  | Acquisition of Loan | 123317156.14
|  | Total Cash Inflow | 123317156.14
Cash Outflows:
Retirement/.Redemption of Debt Securities
|  | Payment of Loan Amortization | 47598584.34
|  | Total Cash Outflow | 47598584.34
| Cash Provided by (Used In) |  |  | 75718571.8
Net Increase in Cash |  |  |  | 203480184.13
Cash at Beginning of the Period |  |  |  | 819067821.92
Cash at the End of the Period |  |  |  | 1022548006.05
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JULY - SEPTEMBER QUARTER, CY 2015
Province | : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
50% payment for construction & improvement/rehab of farm-to-market road at Brgy. Primicias, Bautista, Pangasinan | Brgy. Primicias, Bautista, Pangasinan | 2146025.63 |  |  |  | 2146025.63 |  | fund from the Department of Agriculture
50% payment for construction & improvement/rehab of farm-to-market road at Pogo-Diaz, Bautista, Pangasinan | Pogo-Diaz, Bautista, Pangasinan | 1473750 | 2015-07-22 | On-going |  | 1473750 |  | fund from the Department of Agriculture
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the Improvement/ Rehabilitation of Umingan Community Hospital at Umingan, Pangasinan | Umingan, Pangasinan | 299700 | Labor and Materials Only |  |  | 299700 |  | fund from the Department of Labor and Employment
payment of 1000 bags of Certified Seeds for the implementation of the Agricultural Technology Enhancement and Loan Assistance Program for rice in the province |  | 2035000 | Materials Only |  |  | 2035000 |  | fund from the Department of Agriculture
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Governor

## UnliquidatedCashAdv.
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of September 30, 2015
Province, City or Municipality:
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Marife Acerit | 79100 | 2015-09-03 | Expenses of the 16th Association of Tourism Officers of the Phils.(ATOP) National Convention which shall be held on Oct.1-4, 2015 | 79100
Dr.Anna Ma. Teresa S. De Guzman | 158500 | 2015-09-04 | Meals & Snacks served during the conduct of Municipal Program Implementation Review (MPIR) | 158500
Maria Luisa A. Elduayan | 84100 | 2015-09-04 | Expenses for the 1st Pangasinan Tourism Quiz Bee | 84100
Maria Luisa A. Elduayan | 82500 | 2015-09-04 | Expenses for the 2nd Pangasinan Tourism Skills Competition | 82500
Nestor P. Batalla | 77709 | 2015-09-07 | Expenses of participants to attend the KakaoKonek 2015 | 77709
Irmina B. Francisco | 70000 | 2015-09-07 | Miscellaneous Expenses | 70000
Irmina B. Francsico | 450000 | 2015-09-07 | Expenses to be incurred in the purchase of Postage Stamps for use in mailing Official Communications in the Office of the Governor | 450000
Jessieca A. Rosario | 66000 | 2015-09-07 | Expenses for Board & Lodging for the 2days Value Orientation & Team Bldg. of PPO Staff & League of Population Officers & Workers in the Phils.(LEPOWPHIL) Pang. Chapter on Sept.24-25, 2015 at the Teacher's Camp, Leonard Wood Road Baguio City | 66000
Edwin B. Sison | 180000 | 2015-09-07 | payment of Annual Reg.fees of various motor vehicles with Plate Nos.ending in (9) & (0) | 180000
Leonardo Cruz | 15550 | 2015-09-08 | Expenses for participants to attend the KakaoKonek 2015 - National Cacao Congress to be held at SMX Convention Center, Lanang, Davao City on Sept.11-13, 2015 | 15550
Rogelio D. Caronongan,Jr. | 25137 | 2015-09-08 | Traveling and registration fee expenses | 25137
Ildefonso C. Camba III | 25137 | 2015-09-08 | Traveling and registration fee expenses | 25137
Aurora L. Bacay | 25137 | 2015-09-08 | Traveling and registration fee expenses | 25137
Roderick E. Espiritu | 25137 | 2015-09-11 | Traveling and registration fee expenses | 25137
Merlyn Y. Adan | 40056 | 2015-09-11 | Miscellaneous and Registration fee Expenses | 40056
Atty. Verna T. Nava-Perez | 400000 | 2015-09-14 | Traveling Expenses | 400000
Ramon Morden | 200000 | 2015-09-22 | Financial Assistance | 200000
Romeo Oca | 25137 | 2015-09-22 | Traveling Expenses | 25137
Monika Aliguas Labaupa | 120000 | 2015-09-22 | Traveling Expenses | 120000
Nestor Quiambao | 10000 | 2015-09-28 | Traveling Expenses | 10000
Loida Q. Alamar | 40000 | 2015-09-28 | Traveling Expenses | 40000
Daisy Tomelden | 4600 | 2015-09-28 | Seminar Expenses | 4600
Imelda Jacinto | 6800 | 2015-09-28 | Seminar Expenses | 6800
Engr. Valeriano Mamaril | 9740 | 2015-09-28 | Seminar Expenses | 9740
Engr. Alberto Cabrera | 9740 | 2015-09-28 | Seminar Expenses | 9740
Mario Tiangson | 9740 | 2015-09-28 | Seminar Expenses | 9740
Aldrine Calamiong | 9740 | 2015-09-28 | Seminar Expenses | 9740
Bella B. De Quintos | 60000 | 2015-09-28 | Expenses for jobs and livelihood fair, rosales pang. | 60000
Richelle Ragundin | 30000 | 2015-09-28 | Expenses for jobs and livelihood fair, rosales pang. | 30000
Wilfreda Vicente | 29500 | 2015-09-28 | Expenses for jobs and livelihood fair, rosales pang. | 29500
Dr. Cielo E. Almoite | 26950 | 2015-08-11 | Training expenses | 26950
Irmina B. Francisco | 200000 | 2015-08-19 | Financial Assistance | 200000
Mr.Ramon M. Morden | 200000 | 2015-08-24 | Financial Assistance | 200000
Arturo V. Soriano | 24884 | 2015-08-25 | Traveling and registration fee expenses | 24884
Milagros F. Navarro | 24884 | 2015-08-25 | Traveling and registration fee expenses | 24884
Jamie T. Mendez | 24884 | 2015-08-25 | Traveling and registration fee expenses | 24884
Corazon L. Pantua | 24884 | 2015-08-25 | Traveling and registration fee expenses | 24884
Janine Alexis S. Fabia | 24884 | 2015-08-25 | Traveling and registration fee expenses | 24884
Cecilia V. Bautista | 24884 | 2015-08-25 | Traveling and registration fee expenses | 24884
Ramilyn N. Saumat | 40056 | 2015-08-25 | Training and Miscellaneous expenses | 40056
Rowena Brenda O. Guiang | 25900 | 07/1/2015 | Traveling and registration fee expenses | 25900
Mr.Ramon M. Morden | 200000 | 07/20/2015 | Financial Assistance | 200000
Jennifer D. Cruz | 7900 | 06/30/2015 | Traveling Expenses |  | 7900
Ferlynor M. Aranda | 7900 | 06/30/2015 | Traveling Expenses |  | 7900
Rowena U. Dela Cruz | 21150 | 2015-05-12 | Traveling Expenses |  | 21150
Rufo F. Aquino | 11000 | 2015-04-22 | Traveling Expenses |  | 11000
Mixon D. Flores | 11000 | 2015-04-22 | Traveling Expenses |  | 11000
Juliet F. Robina | 11000 | 2015-04-22 | Traveling Expenses |  | 11000
Hon.Mojamito R. Libunao,Jr. | 40000 | 2015-04-22 | Traveling Expenses |  | 40000
Hon.Napoleon C. Fontelera,Jr. | 40000 | 2015-04-22 | Traveling Expenses |  | 40000
Hon.Raul P. Sison | 40000 | 2015-04-22 | Traveling Expenses |  | 40000
Elmar Z. De Guzman | 11000 | 2015-04-22 | Traveling Expenses |  | 11000
Danilo G. Padulip | 11000 | 2015-04-22 | Traveling Expenses |  | 11000
Atty.Verna T. Nava-Perez | 154500 | 2015-04-08 | Miscellaneous Expenses |  | 154500
Atty.Verna T. Nava-Perez | 271500 | 2015-03-27 | Miscellaneous Expenses |  | 271500
Col.Fernando R. De Guzman | 30000 | 2015-03-02 | Traveling Expenses |  | 30000
Cristina J. Bumiltac | 350000 | 2015-01-21 | Various foodstuff & other operational expenses |  | 350000
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Total | 4346820 |  |  | 3211270 | 1017950 |  |  |  | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor