## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2016
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks (Date of Obligation)
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE |  |  | REFERENCES
Social Development
Labor, materials, equipment and other incidentals necessary for the completion/expansion of covered court at Brgy. Quibaol, Lingayen | Brgy. Quibaol,Ling. Pang. | 1572471.71 | 2016-02-22 | 2016-04-14 | 100% | 1572471.71 |  | Obligated |  | Alcel ConstnPR#0121
Labor, materials, equipment and other incidentals for the completion of covered court at Libsong East, Lingayen | Libsong East, Ling. Pang. | 1797848.99 | 2016-02-25 | 2016-03-21 | 100% | 1797848.99 |  | Obligated |  | CAD Constn PR#100
Materials, labor, equipment and other incidentals for the construction of Multi-purpose bldg., At Brgy. Mancup, Calasiao, Pangasinan | Brgy. Mancup, Calasiao, Pang. | 2307661 | 2016-04-01 | On-going | 35% | 806468.95 |  | Obligated |  | MCB C/S PR#0150
Labor, materials, equipment and other incidenatls for the construction of covered court (gymnsium) at Brgy. Bacabac, Bugallon | Brgy. Bacabac, Bugallon, Pang. | 2473530 | Labor and materials only |  | 75% | 1852206.16 |  | Obligated |  | BET Constn PR#0549
Labor, materials, equipment and other incidenatls for the construction of covered court (gymnsium) at Brgy. Buenlag, Bugallon | Brgy, Buenlag, Bugallon, Pang. | 2473530 | 2016-03-01 | On-going | 70% | 1728440.21 |  | Obligated
Labor, materials, equipment and other incidenatls for the construction of covered court (gymnsium) at Brgy. Buenlag, Bugallon | Brgy, Buenlag, Bugallon, Pang. | 2473530 | Labor and materials only |  | 70% | 1728440.21 |  | Obligated |  | Pang. New Wilson L/C PR#0278
Materials, labor, and other incidentals for the construction of standard 1 unit 3 classroom School Building at Pindangan Elem. Sch., Sison, Pangasinan | Pindangan, Sison, Pang. | 2430000 | Labor and materials only |  | 50% | 1213061.52 |  | Obligated |  | Lucky G18 PR#1789
Materials, labor, and other incidentals for the construction of drainage canal w/ cover and storm drainage at Brgy. San Miguel, Calasiao | Brgy. San Miguel, Calasiao, Pang. | 496775.31 | 2016-03-28 | 2016-06-10 | 100% | 496775.31 |  | Obligated |  | MCB Constn & Supply PR#2093
Labor, materials, equipment and other incidentals for the construction of Tribal hall, Brgy. San Jose, Labrador | Brgy, San Jose, Labrador, Pang. | 497226.86 | 2016-03-18 | 2016-04-29 | 100% | 497226.86 |  | Obligated |  | Pang. New Wilson PR#2669
Labor, materials, equipment and other incidentals for the repair of roofing anf painting of ceiling of Prov'l Jail |  | 124506.79 | Labor and materials only |  | 100% | 124506.79 |  | Obligated |  | Ahyok C/S PR#2841
Labor, materials, equipment and other incidentals for the repair/rehabilitation of Muliti-purpose Basketball court at Asan sur, Sison, Pangasinan | Asan Sur, Sison, Pang. | 432260.72 | Labor and materials only |  | 100% | 432260.72 |  | Obligated |  | Lucky G18 PR#3009
Materials, labor, equipment and other incidentals for the repair/rehabilitation of 2 units 3-classroom schoolbuildings at Flores E/S, Umingan, Pangasinan | Umingan, Pang. | 159396.99 | Labor and materials only |  | 100% | 159396.99 |  | Obligated
Materials, labor, equipment and other incidentals for the repair/improvement of 4-classroom schoolbuilding at Doyong NH/S, San Carlos City | Doyong, San Carlos, Pang. | 42937.94 | Labor and materials only |  | 100% | 42937.94 |  | Obligated |  | PR#3625
Materials, labor, equipment and other incidentals for the construction of concrete bleaches at Domalandan Center Gym at Lingayen, Pangasinan | Domalandan Center, Ling. Pang. | 151744.45 | Labor and materials only |  | 100% | 151744.45 |  | Obligated |  | PR#3624
Labor, materials, equipment and other incidentals, re: proposed fabrication/installation of 2 sets basketball board (complete) at Sitio IdolIdol, Brgy. Nagsaing, Calasiao, Pang. | Sitio Idolidol, Brgy. Nalsian, Calasiao, Pang. | 107803 | Labor and materials only |  | 100% | 107803 |  | Obligated |  | PR#8118
Materials, labor, equipment and other incidentals necessary for the repair of ceiling of PSWDO (Bahay Pag-asa), Lingayen, Pang. | Ling. Pang. | 396718.21 | Labor and materials only |  | 100% | 396718.21 |  | Obligated |  | MCB C/S PR# 1291
Materials, labor, equipment and other incidentals necessary for the proposed construction/ installation of 18 units streetlights at Capitol beachfront at Lingayen | Ling. Pang. | 632637.67 | Labor and materials only |  | 100% | 632637.67 |  | Obligated |  | CAD Constn PR# 1275
Labor, materials, equipment and other incidentals-application of reflective thermoplastic along Alvear, Artacho, Lingayen Extension and Diversion Road, Lingayen | Alvear Artacho, Pob. Ling. Pang. | 1081539 | Labor and materials only |  | 100% | 1081539 |  | Obligated |  | PR#8013
Economic Development
Labor, materials and other incidentals-concreting of Road in Brgy. Casilagan, Mangatarem, Pangasinan | Brgy. Casilagan, Mangatarem, Pang. | 1365973 | Labor and materials only |  | 100% | 1365973 |  | Obligated |  | PR#8015
100 MT Asphalt Pre-mix and 5 drums E. Asphalt for Asphalting of Callejon St., Poblacion, Binalonan, Pangasinan | Callejon St. Pob. Binalonan, Pang. | 622000 | Materials only |  | 100% | 622000 |  | Obligated |  | PR#8017
Labor, materials and other incidentals-concreting of Brgy. Road with RCCP at Sitio Tribon, Brgy. Mancup, Calasiao, Pangasinan | Brgy. Mancup, Calasiao, Pang. | 1014935 | Labor and materials only |  | 100% | 1014935 |  | Obligated |  | PR#8018
575 MT asphalt pre-mix and 25 drums emulsified asphalt for the asphalting of Mancasuy Rd. Binalonan, Pangasinan | Mancasuy Rd., Binalonan, Pang. | 3516625 | 2016-04-28 | 2016-05-04 | 15% | 3629433 |  | Obligated
Labor, materials, and other incidentals for rehabilitation/improvement/ upgrading of Burgos-Iliw-Iliw Rd., Burgos, Pangasinan | Burgos, Pang. | 11881142.96 | Labor and materials only |  | 15% | 5550286.58 |  | Obligated
Labor, materials, and other incidentals for rehabilitation/improvement/ upgrading of Urbiztondo-San Carlos Rd., Urbiztondo(part of P87,957,208.21) | Urbiztonod-San Carlos RD. Pang. | 23536109.26 | Materials only |  | 15% | 13193581.23 |  | Obligated
Labor, materials, equipment and other incidentals necessary for the widening of the road going to Palapad Seminary, San Fabian, Pangasinan | Palapad Seminary, San Fabian, Pang. | 5868850 | 2016-01-30 | 2016-04-25 | 90% | 5273963.1 |  | Obligated |  | Alcel Constn PR#0078
Materials. Labor, equipment and other incidentals necessary for the proposed concreting of Purok I Centro Rd. Brgy. Barlo, Mabini, Pangasinan | Brgy. Barlo, Mabini, Pang. | 1413467 | 2016-03-08 | 2016-03-28 | 100% | 1410857.6 |  | Obligated |  | Alcel Constn PR#0055
Labor, materials, equipment and other incidentals necessary for the concreting of Buer, Brgy. Rd. Aguilar, Pangasinan | Brgy. Buer Rd. Aguilar, Pang. | 1435950.75 | Labor and materials only |  | 100% | 1435950.75 |  | Obligated |  | MCB C/S PR#0037
Jetmatic pumps and G.I. Pipes (part of P 4,417,700.00, part charged to 2016-3917) |  | 2817700 | Materials only |  |  | 2817700 |  | Obligated |  | MVB Entp. PR#0378
Materials. Labor, equipment and other incidentals necessary for the concreting of Inmanduyan Rd. Laoac, Pangasinan | Laoac, Pangasinan | 1389999.21 | Labor and materials only |  | 100% | 1389999.21 |  | Obligated | 8917-01
Labor, materials, equipment and other incidentals necessary for the concreting of Polong West Rd. (Polong South Bd. Rd.) Bugallon, Pangasinan | Polong West, Bugallon, Pang. | 2915397.56 | 2016-03-01 | On going | 90% | 2473530 |  | Obligated |  | Pang. New Wilson L/C PR#0077
600 units water pump and engine sets |  | 4700000 | Materials only |  |  | 4700000 |  | Obligated | 8911 | PR#2891
1 unit Auxillary water pump and 1 unit 16 HP engine for the Lingayen Federation of Fisherfolk Org. |  | 112000 | Materials only |  |  | 112000 |  | Obligated | 8911 | PR#5845
Loans granted to various Associations and Multi-Purpose Cooperatives |  | 2120000 | Loans only |  |  | 2120000 |  | Obligated
Materials, labor, equipment and other incidentals necessary for the construction of Boy Scout of the Philippines Regional Off. Bldg., Lingayen | Ling. Pang. | 1396275.38 | Labor and materials only |  | 100% | 1396275.38 |  | Obligated |  | CAD Contn PR# 1276
Labor, materials, equipment and other incidentals for the repair/rehabilitation of 8 comfort rooms at NRSCC, Lingayen | Ling. Pang. | 464744.58 | Labor and materials only |  | 100% | 464744.58 |  | Obligated | 3917 | Ahyok C/S PR#2118
207 MT Asphalt Pre-mix and 6 drums E. Asphalt for the improvement/ blocktopping of Brgy. Camanang Road going to Urdaneta Fishport, Urdaneta City | Brgy. Camanang Rd. Urdaneta City | 1291441 | 2016-06-17 | 2016-06-17 | 100% | 1291441 |  | Obligated |  | Exponential Headway PR#3312
Jetmatic pumps and G.I. Pipes (part of P 4,417,700.00) |  | 1597636 | Materials only |  | 100% | 1597636 |  | Obligated |  | MVB Ent PR#0378
312 MT Asphalt Pre-mix and 14 drums E. Asphalt -blocktopping of Villa Road, Brgy. Villanueva and Primicias, Bautista, Pang. | Brgy. Villanueva and Primicias, Bautista, Pang. | 1914410 | Materials only |  | 100% | 1914410 |  | Obligated |  | Exponential PR#3314
Materials, labor, equipment and other incidentals - incidentals/construction of sideslope protection along San Jacinto - Pozorrubio Road, Pozorrubio | San Jacinto-San Manuel, Pang. | 1998584.2 | Labor and materials only |  | 100% | 1998584.2 |  | Obligated |  | MCB C/S PR#3008
Labor, materials, equipment, and other incidentals for the concreting along Sitio Casilagan Road, Brgy. San Juan, San Manuel, Pangasinan | Sitio Casilagan Rd. Brgy. San Juan, San Manuel, Pang. | 1073239 | 2016-03-24 | 2016-04-08 | 100% | 1073239 |  | Obligated |  | Lucky G18 PR#1766
19 drums Emulsified Asphalt and 619 MT Asphalt Pre-mix for the blocktopping of various Municipal Streets at Bautista | Municipality of Bautista, Pang. | 3671815 | Materials only |  | 100% | 3671815 |  | Obligated |  | Exponential PR#0086
8 drums Emulsified Asphalt and 181 MT Asphalt Pre-mix for the proposed asphalting of Brgy. Linoc Road, Binmaley | Brgy. Linoc Rd. Binmaley, Pang. | 1110700 | 2016-05-06 | 2016-05-07 | 100% | 1110700 |  | Obligated |  | Exponential PR#0026
7 drums emulsified Asphalt and 246 MT Asphalt Pre-mix for use in the blocktopping of Papagueyan Road, Binmaley, Pangasinan | Papagueyan Rd. Binmaley, Pang. | 1451305 | 2016-05-02 | 2016-05-05 | 100% | 1451305 |  | Obligated |  | Exponential PR#0051
736 MT Asphalt Pre-mix and 23 drums Emulsified Asphalt for the asphalting of Basing Road, Binmaley | Basing Rd. Binmaley, Pang. | 4371725 | Materials only |  | 100% | 4371725 |  | Obligated |  | Exponential PR#0083
138 MT Asphalt Pre-mix and 4 drums Emulsified Asphalt for the blocktopping of Brgy. Domalandan West Road, Lingayen | Domalandan West, Ling. Pang. | 815200 | Materials only |  | 100% | 815200 |  | Obligated |  | Exponential PR#0079
218 MT Asphalt Pre-mix and 10 drums Emulsified Asphalt for the asphalting of Sitio Pandel and Sitio Dr. De Vera Road, Brgy. Domalandan Center, Lingayen | Domalandan Center, Ling. Pang. | 1338535.49 | 2016-03-30 | 2016-04-01 | 100% | 1338535.49 |  | Obligated |  | Exponential PR#0052
Asphalt materials for the blocktopping of Brgy. Macarang Road, Mangatarem, Pangasinan | Brgy. Macarang Rd. Mangatarem, Pang. | 3200410 | Materials only |  | 100% | 3200410 |  | Obligated |  | Exponential PR#0019
339 MT Asphalt Pre-mix for the Asphalting of Palamis Road, Alaminos City | Palamis Rd., Alaminos City, Pang. | 1861110 | 2016-04-16 | 2016-04-21 | 100% | 1861110 |  | Obligated |  | Exponential PR#0109
670 MT Asphalt Pre-mix for the asphalting of Amandiego Road, Alaminos | Amandiego Rd., Alaminos City, Pang. | 3678300 | Materials only |  | 100% | 3678300 |  | Obligated | 6911 | Exponential PR#0120
233 MT Asphalt Pre-mix, 7 drums E. Asphalt for patching/blocktopping of Inmalog Sur Road, San Fabian, Pangasinan | Inmalog Sur Rd. San Fabian, Pang. | 1379935 | 2016-04-26 | 2016-04-29 | 100% | 1379935 |  | Obligated | 6911 | Exponential PR#0133
Amortization of Principal and Interest on Loan to LBP |  | 65057817.8 | Loans only |  |  | 65057817.8 |  | Obligated
Grand Total |  | 182035451.83 |  |  |  | 159605877.61
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the Quarter APRIL - JUNE , CY 2016
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 0 |  |  |  |  | 0
Continuing Appropriation | [5 empty] | 0
Previous Year's Appropriation transferred to the Special Trust Fund |  | 80015020.77 |  |  |  | 80015020.77
Transfers/Grants | [5 empty] | 0
Others ( Please specify) | [5 empty] | 0
Total Funds Available | 0 | 80015020.77 | 0 | 0 | 0 | 80015020.77
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies | [5 empty] | 0
Office Supplies | [5 empty] | 0
Repair of Evacuation Center | [5 empty] | 0
Institutional/Capacity Development ( Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses | [5 empty] | 0
Traveling Expense | [5 empty] | 0
Training Expense | [5 empty] | 0
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment | [5 empty] | 0
Gasoline, Oil, Lubricants | [5 empty] | 0
Donations | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. |  | 21450993.4 |  |  |  | 21450993.4
Repair & Maintenance-Motor Vehicles | [5 empty] | 0
Total Utilization | 0 | 21450993.4 | 0 | 0 | 0 | 21450993.4
Unutilized Balance | 0 | 58564027.37 | 0 | 0 | 0 | 58564027.37
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information containedin this document.
ARTURO V. SORIANO, CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending June 30, 2016
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 136328957.76
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
75745325.02
Capital Outlay
-0-
Financial Expenses
-0-
Sub-total |  |  |  | 75745325.02
Balance |  |  |  | 60583632.74
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
AMADO T. ESPINO, JR.
Governor

## CASHFLOW
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the Second Quarter Ending June 30,2016
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 48087428.29
|  | Share from Internal Revenue Allotment |  | 666390858
|  | Receipts from business/service income |  | 111943125.62
|  | Interest Income |  | 2485741.69
|  | Other Receipts |  | 87171528.36
|  | Total Cash Inflow |  | 916078681.96
Cash Outflows:
|  | Payment of expenses |  | 319345051.57
|  | Payment to suppliers and creditors |  | 126713450.78
|  | Payment to employees |  | 195628478.51
|  | Interest Expenses |  | 10462789.21
|  | Other Expenses |  | 106170370.27
|  | Total Cash Outflow |  | 758320140.34
| Net Cas Flows from Operating Activities |  |  | 157758541.62
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
|  | Collection of Principal on Loans to other Entities |  | 3162355
|  | Total Cash Inflow |  | 3162355
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 377123358.65
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 1500000
|  | Total Cash Outflow |  | 378623358.65
| Net Cash Flows from Investing Activities |  |  | -375461003.65
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 130942653.1
|  | Total Cash Inflow |  | 130942653.1
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 54985003.37
|  | Total Cash Outflow |  | 54985003.37
| Net Cash Flows from Financing Activities |  |  | 75957649.73
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | -141744812.3
Add:Cash at Beginning of the Quarter |  |  |  | 1096681245.64
Cash at the End of the Quarter |  |  |  | 954936433.34
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE APRIL - JUNE QUARTER, CY 2016
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
100% work accomplishment for the Construction of Seeds Storage Warehouse with Concrete Pavement at Sta. Barbara Provincial Agriculture Field Station | Provincial Agriculture Field Station, Sta. Barbara | 3737781.51 | Materials Only |  | 100% | 3737781.51 |  | fund from the Department of Agriculture
40% work accomplishment for the Improvement/Rehabilitation of Urdaneta-Cili Junction Road, Binalonan, Pangasinan | Urdaneta-Cili Junction Road, Binalonan, Pangasinan | 7035623.94 | Materials Only |  | 40% | 2814249.58 |  | fund from the Department of Interior and Local Government
70% mobilization for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Mangatarem-Urbiztondo Road, Mangatarem, Pangasinan | Mangatarem-Urbiztondo Road, Mangatarem, Pangasinan | 17950502.35 | On-Going |  | 70% | 12565351.64 |  | fund from the DPWH-SLRF
50% mobilization for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Malasiqui-Catablan Road, Malasiqui, Pangasinan | Malasiqui-Catablan Road, Malasiqui, Pangasinan | 8992893.4 | On-Going |  | 50% | 4496446.7 |  | fund from the DPWH-SLRF
65% mobilization for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Maniboc-Pangapisan-Sabangan Road, Lingayen, Pangasinan | Maniboc-Pangapisan-Sabangan Road, Lingayen, Pangasinan | 14986920.59 | On-Going |  | 40% | 9741498.38 |  | fund from the DPWH-SLRF
payment of 15% mobilization for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Asingan-San Manuel-Agno Gorge, Asingan, Pangasinan | Asingan-San Manuel-Agno Gorge | 4998307.3 | 2016-04-01 | 2016-04-01 | 15% | 749746.1 |  | fund from the DPWH-SLRF
payment of 50% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Tarlac Boundary-Bayambang Diversion Road, Bayambang, Pangasinan | Tarlac Boundary-Bayambang Diversion Road, Bayambang, Pangasinan | 8993910.67 | On-Going |  | 50% | 4496955.33 |  | fund from the DPWH-SLRF
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Ungib, San Quintin, Pangasinan | Brgy. San Miguel, Balungao, Pangasinan | 514104 | 2016-03-13 | 2016-03-17 | 100% | 514104 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Capital Tomas, Rosales, Pangasinan | Brgy. Capital Tomas, Rosales, Pangasinan | 514104 | Labor & Materials Only |  | 100% | 514104 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. La Paz, Umingan, Pangasinan | Brgy. La Paz, Umingan, Pangasinan | 514104 | Labor & Materials Only |  | 100% | 514104 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Lungao, San Nicolas, Pangasinan | Brgy. Lungao, San Nicolas, Pangasinan | 515300 | Labor & Materials Only |  | 100% | 515300 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. San Vicente, Sta. Maria, Pangasinan | Brgy. San Vicente, Sta. Maria, Pangasinan | 514776 | 2016-04-03 | 2016-04-07 | 100% | 514776 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Toboy, Asingan, Pangasinan | Brgy. Toboy, Asingan, Pangasinan | 514776 | 2016-03-28 | 2016-04-02 | 100% | 514776 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Bensican, San Nicolas, Pangasinan | Brgy. Bensican, San Nicolas, Pangasinan | 515300 | 2016-03-07 | 2016-03-13 | 100% | 515300 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Dupac, Asingan, Pangasinan | Brgy. Dupac, Asingan, Pangasinan | 514776 | Labor & Materials Only |  | 100% | 514776 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Dalayap, Sta. Maria, Pangasinan | Brgy. Dalayap, Sta. Maria Pangasinan | 514776 | 2016-04-01 | 2016-04-05 | 100% | 514776 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Labuan, San Quintin, Pangasinan | Brgy. Dalayap, Sta. Maria Pangasinan | 515140 | 2016-03-13 | 2016-03-17 | 100% | 515140 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. San Eugenio, Natividad, Pangasinan | Brgy. Dalayap, Sta. Maria Pangasinan | 515384 | Labor & Materials Only |  | 100% | 515384 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. San Isidro, Rosales, Pangasinan | Brgy. San Isidro, Rosales, Pangasinan | 514104 | Labor & Materials Only |  | 100% | 514104 |  | fund from the Tobacco Excise Tax
payment of 100% work accomplishment for furnishing labor, materials, equipment and other incidentals necessary for the CONCRETING of Farm-to-Market Road, Brgy. Angio San Fabian, Pangasinan | Brgy. Angio, San Fabian, Pangasinan | 515408 | 2016-02-25 | 2016-04-29 | 100% | 515408 |  | fund from the Tobacco Excise Tax
payment of 41,759 pcs. Roof sheets/corspan, 915, 0.40mm pre-painted BMT, for use as assistance to families affected by typhoon in Pangasinan | various families in Pangasinan | 23046792.1 | Materials Only |  | N/A | 23046792.1 |  | fund from National Housing Authority
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO T. ESPINO, JR.
Provincial Accountant | [5 empty] | Provincial Governor

## UNLIQUIDATED.CASH ADVANCES
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of June 30, 2016
Province, City or Municipality:
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Rommel Cardinoza | 0 | 2014-01-16
Cornel V. dela Cruz | 0 | 2014-01-16
Gerardo R. Santos | 0 | 2014-01-09
Aurora L. Bacay | 0 | 2014-01-09
Edwin B. Sison | 0 | 2014-01-08
Dr. Irmina B. Francisco | 117000 | 2016-06-29 | Misc.expenses, Joint Oath-Taking of New/ Re-Elected Prov'l Officials on June 30, 2016 at Sison Auditorium, Lingayen | 117000
Atty. Verna T. Nava-Perez | 115000 | 2016-06-27 | Inauguration of Incoming Elected Prov'l Officials for 2016-2019 on June 30, 2016 | 115000
Rodolfo M. Cortez | 6200 | 06/25/1997 | Traveling expenses | 6200
Wilma D. Quimosing | 200000 | 2016-06-24 | Immediate repair of various service vehicles & heavy equipment | 200000
Rachel Jose | 17200 | 2016-06-24 | Conduct of ISTIV Bayanihan & Green Productivity Enhancement Training on June 24, 2016 & Job's Fair on June 8 & 28, 2016 | 17200
Maria Luisa A. Elduayan | 190000 | 2016-06-22 | Expenses during Team Bldg./Lakbay Aral for All Chief of Offices & Hospitals in Subic Bay Metropolitan Authority, Olongapo City, Zambales on June 23-24, 2016 | 190000
Noemi C. Cabanisas | 8000 | 2016-06-21 | 2nd Youth Environmental Summit (YES) to be held on June 22-24, 2016, Baguio City | 8000
Benedict F. Ocampo | 8000 | 2016-06-21 | Official Travel, Baguio City, 2nd Youth Environmental Summit (YES), June 22-24, 2016 | 8000
Dr. Cielo E. Almoite | 150000 | 2016-06-17 | Logistics & other misc. expenses in the conduct of Buntis Congress Celebration | 150000
Maria Luisa A. Elduayan | 28350 | 2016-06-15 | 7th National Convention of Professional Tour Guides on June 18-20, 2016, Surigao City | 28350
Emilio P. Samson, Jr. RSW | 50000 | 2016-06-13 | Financial Assistance to indigents | 50000
Tyrone R. Pagsolingan | 17700 | 2016-06-13 | per diems & other incidental exps., Training on Strategic Planning & Management at the Dep't. of Health Policy & Admin., College of Public Health, UP Manila, June 20-22, 2016 | 17700
Monika Aliguas N. Labaupa | 313000 | 2016-06-08 | 7th National Convention of Professional Tour Guides, June 18-20, 2016, Surigao City | 313000
Jessieca A. Rosario | 36000 | 2016-06-07 | 1 Meal & 2 Snacks during the 2nd Qtr. Meeting of League of Population Officer & Workers in the Phils. Pangasinan Chapter (LEPOWPHIL) & Federation of Barangay Service Point Officers (BSPOs) | 36000
Janet S. De Vera | 9947 | 2016-06-06 | trav.exps. & per diems ,Seminar, June 16-18, 2016, Punta Villa Resort, Villa Arevalo, Iloilo City | 9947
Benita M. Pizarro | 9947 | 2016-06-06 | trav.exps. & per diems ,Seminar, June 16-18, 2016, Punta Villa Resort, Villa Arevalo, Iloilo City | 9947
Dr. Policarpio R. Manuel | 36115.83 | 2016-06-02 | Rerouting of Loadside Service Drop of Pangasinan Prov'l Hospital Radiology Bldg. | 36115.83
Norie S. Balan | 3600 | 2016-05-31 | per diems, "PLDT Road Show for ICT Telephony Solutions", June 2, 2016, Country Club Road, Baguio City |  | 3600
Edwin B. Sison | 150000 | 2016-05-30 | Annual reg.fees of various motor vehicles with plate numbers ending in (6) & (7) |  | 150000
Wilma R. Bravo | 26858 | 2016-05-26 | Upcoming Regional Seminar Workshop at Waterfront Insular Hotel Davao, Davao City on June 6-8, 2018 |  | 26858
Vida Myla Grace S. Bautista | 23000 | 2016-05-24 | per diems & Other Incidental Expenses, 2016 National Convention of the Philippine Pharmacists Association, Inc. ,Waterfront Hotel, Cebu City, May 25-28, 2017 |  | 23000
Dr. Cielo E. Almoite | 26858 | 2016-05-17 | Upcoming Regional Seminar Workshop at Waterfront Insular Hotel Davao, Davao City on June 6-8, 2018 |  | 26858
Teresita L. Viray | 23718.04 | 2016-05-17 | per diems & Other Incidental Expenses, 2016 National Convention of the Philippine Pharmacists Association, Inc. ,Waterfront Hotel, Cebu City, May 25-28, 2016 |  | 23718.04
Emilio P. Samson, Jr. | 26858 | 2016-05-11 | Upcoming Regional Seminar Workshop at Waterfront Insular Hotel Davao, Davao City on June 6-8, 2016 |  | 26858
Mona S. Alavazo | 26858 | 2016-05-11 | Upcoming Regional Seminar Workshop at Waterfront Insular Hotel Davao, Davao City on June 6-8, 2016 |  | 26858
Zenaida F. Alvendia | 26858 | 2016-05-11 | Upcoming Regional Seminar Workshop at Waterfront Insular Hotel Davao, Davao City on June 6-8, 2017 |  | 26858
Christine Joy Santos | 17850 | 2016-04-27 | per diems & Other Incidental Expenses, 2016 National Convention of the Philippine Pharmacists Association, Inc. ,Waterfront Hotel, Cebu City, May 25-28, 2016 |  | 17850
Karen Joyce Bautista | 17133 | 2016-04-25 | per diems & Other Incidental Expenses, 2016 National Convention of the Philippine Pharmacists Association, Inc. ,Waterfront Hotel, Cebu City, May 25-28, 2016 |  | 17133
Mary Cecile Q. Perez | 22489.72 | 2016-04-21 | per diems & Other Incidental Expenses, 2016 National Convention of the Philippine Pharmacists Association, Inc. ,Waterfront Hotel, Cebu City, May 25-28, 2016 |  | 22489.72
Jonathan L. Castro | 22000 | 2016-04-14 | per diems & traveling allow., "Luzon ICT Conference 2016",April 11 to 12, 2016, Balibago, Angeles City |  | 22000
Juliet F. Robina | 11300 | 2016-04-01 | 15th Regional Mining Summit,April 6-8, 2016 , Vigan City, Ilocos Sur |  | 11300
Ma. Catalina Judy G. Martin | 11300 | 2016-04-01 | 16th Regional Mining Summit,April 6-8, 2016 , Vigan City, Ilocos Sur |  | 11300
Mixon D. Flores | 11300 | 2016-04-01 | 17th Regional Mining Summit,April 6-8, 2016 , Vigan City, Ilocos Sur |  | 11300
Vivian U. Oamil | 11300 | 2016-04-01 | 18th Regional Mining Summit,April 6-8, 2016 , Vigan City, Ilocos Sur |  | 11300
Irmina B. Francisco | 404200 | 2016-03-16 | Cash advance to defray expenses for Gov. Amado T. Espino, Jr. Academic Excellence Award & Leadership Excellence Award for Academic Year 2015-2016 |  | 404200
Joenard E. Manuel - | 25688 | 2016-02-24 | payment of cash advance for Trav.exps., per diems, reg. fee, accomm. & other exps. to attend in the training on ISO 9001:2008 Quality Management Awareness on Mar.2, 2016, Internal Quality Audit on Mar.9-10, 2016 & Training on Effective IQA Report Writing on Mar.11, 2016 to be held at PTTC, Pasay City |  | 25688
Ramon M. Morden | 300000 | 2016-02-05 | Financial Assistance to be given to diff. constituents of Pangasinan |  | 300000
Cristina J. Bumiltac | 350000 | 2016-01-27 | Cash advance in payment of various foodtuff & other operational expenses for use at Capitol Resort Hotel |  | 350000
Antonieta C. Delos Santos | 200000 | 2016-01-20 | Cash advance to be used for the Immediate Repair of various Prov'l Bldgs., Service Vehicles & Equipment |  | 200000
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Total | 3169228.59 |  |  | 1312459.83 | 1739168.76 |  |  |  | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | AMADO T. ESPINO, JR
Provincial Accountant |  |  |  |  | Governor