## 1QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | TOTAL COST | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[6 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) Avenida Rizal, | 6111593 | Lingayen
Improvement/extension of Day Care Center at Brgy. Sto. Tomas, | 504156 | San Jacinto
Waterproofing of NRSCC Grandstand Bleachers at NRSCC Cmpd (Area-1867 sq.m.) | 4437467 | Lingayen
Construction of Senior Citizen Bldg. at | 900350 | Brgy. Bacag, Villasis
Improvement of Bautista Municipal Plaza, | 3000000 | Poblacion East, Bautista
Construction of Power house and Installation of MCB Panel, Main Feeder Line at Burgos Rehabilitation Center, | 950807.11 | Burgos, Pangasinan
Reconstruction of Gymnasium at PPH Bolingit, | 2233078 | San Carlos city
Extension of swimming pool warm up area w/ shade at NRSCC Cmpd, | 1131044 | Lingayen
Proposed construction of drainage canal at Pozorrubio Com. Hospital, | 729856 | Pozorrubio
Repair/rehabilitation of Multi-Purpose Hall | 162935 | Brgy. Ketegan, Bautista
Repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station, | 552931 | San Quintin
Repair/renovation of Old Female Cell Bldg. #1 & Fabrication of Steel Gate at Pang. Provincial Jail, | 448989 | Lingayen
Construction of Multi-Purpose Bldg. at | 2167431 | Brgy. Palma, Basista
Construction of Facilitators' Quarters | 1524013 | Brgy. San Vicente, Burgos
Completion of Senior Citizen Bldg., at | 706598 | Brgy. Nibaliw Norte, Bautista
Construction of Pathway infront of Brgy. Hall at Palaming, | 226814 | San Carlos City
Proposed construction of CR (Male & Female) | 253895 | Brgy. Nibaliw Norte, Bautista
Proposed street lights at Brgy. Burgos-Padlan, | 400217 | San Carlos City
Concreting of Multi-Purpose Pavement (Solar Dryer) Brgy. Cabalitian, | 363484 | Asingan
Construction of stage beside open court at | 396110 | Brgy. Galarin, Urbiztondo
Repainting of water Tank Bldg., Motor Pool Cmpd., | 94132 | Lingayen
Construction of Drainage Canal a tCasa Real Cmpd. (back of Prov'l Jai), | 260876 | Lingayen
Construction of Drainage Canal a tCasa Real Cmpd. (back of Prov'l Jai), | 234871 | Lingayen
Construction of concrete battery cages and replacement of solar streetlights battery at Capitol Beachfront, | 465409 | Lingayen
Construction/installation of Street lights | 219600 | Brgy. Turko, Laoac
Improvement/rehabilitation of Municipal Hall, , as per Extra Work Order No. 1 | 379886.96 | Bugallon
Labor, materials, equipment and other incidentals for the construction of New Water Sourc at Dasol Community Hosp., | 790700 | Dasol
Construction of 1 Artesian Well at Sitio Tebag, Brgy. Diaz, | 63559 | Umingan
Drilling/construction of well sourc (w/ pumpng machinery and elevated stell tank) at Baluyot, | 1818453.7 | Bautista
Construction of two (2) units Artesian Well (w/ excavation) at San Eugenio, | 183100 | Natividad
Provision of PE Pipe for connection of potable drinking water at Brgy. Babuyan, | 79500 | Infanta
Construction of Well Source (6" diam casing 120 M depth) (A) Drilling works and well development at Dasol Community Hospital | 54000 | Dasol
Construction of 10 Artesian Wells w/ jetmatic Pumphead at Brgy. Binabalian, | 133115 | Bolinao
Construction of drainage system at Don Canuto St., | 1077654 | Brgy. Domalandan West, Lingayen
Waterproofing of walls and floor topping of GSO Basement Area, Capitol Bldg., Lingayen | 1300000 | Lingayen
Retrofitting of Capitol Basement Area (double layer), Capitol Bldg., | 7000000 | Lingayen
Construction of Provincial Shuttle Bus Terminal, Motorpool Cmpd., Lingayen | 8200000 | Lingayen
Construction of Hall of Fame- Capitol | 2500000 | Lingayen
construction of Training Center #2, Capitol | 6300000 | Lingayen
Economic Development
Asphalting of Bonifacio St., Poblacion, | 525100 | Lingayen
Asphalting of Farm to Market Road, Brgy. Tebag, | 389700 | Mangaldan
Asphalting blocktopping of Soriano St., Poblacion, | 259800 | Lingayen
Blocktopping/patching of Brgy. Ingalagala, Brgy. Road, | 626200 | Malasiqui
locktopping of Nicanor St., | 499700 | Poblacion, Lingayen
Patching/blcoktopping of Dulag Road, | 1915000 | Binmaley
Asphalting of Abalos St., Brgy. Estanza, | 735400 | Lingayen
Concreting of Sitio Guillermo Lamsen Road at Domalandan East, | 371804 | Lingayen
Concreting of Sitio Senenche Extension Farm to Market Road at Brgy. Pogonsili, | 2218823 | Aguilar
blocktopping of Brgy. Luyan Road (Acacia Ave. & Chico Ave.), | 2541200 | Mapandan
Rehabilitation of Taculit Bridge II (Super Structure Only) , as per extra work #1 | 134438.05 | San Fabian,
Rehabilitation of Taculit Bridge I (Super Structure Only) at , as per extra work #1 | 134438.05 | San Fabian
Rehabilitation/construction of SIKLING DAM, | 1733459.53 | Brgy. Bongalon, Labrador
Concreting of Carmay West Brgy. Road, | 1082600 | Rosales
Retrofitting of Ramos Bridge, | 10000000 | Urbiztondo
Retrofitting of Zaragosa Bridge (L=18 mtrs.) | 5800000 | Bolinao
Asphalting of Angarian-Banaga Section, | 671500 | Bugallon
Asphalting of Sitio Nankumpapueyan Road at | 2041500 | Brgy. Laoag, Aguilar
blocktopping of Brgy. Road at Brgy. Matalava, | 811100 | Lingayen
Blocktopping of Municipal Cemetery Road, | 908000 | Bautista
Asphalting/blocktopping of Sitio IdolIdol Road, | 1131400 | Calasiao
blocktopping of Sitio Calay at | 957500 | Brgy. Lomboy, Binmaley
Asphalting of Brgy. Sumabnit, | 2676464 | Binalonan
Asphalting of Angela Valdez Ramos NH/S, | 889400 | Asingan
Constructuon of Hanging Bridge at , as per Extra Work #1 | 130135.43 | Brgy. Garrita, Bani
improvement/rehabilitation of Kinabalutan Bridge, Superstructure only (flat slab) | 1770551 | Brgy. Matulong, Manaoag
Costruction of CHB Drainage | 2360049 | Brgy. Poblacion, Binmaley
concreting of Sito Beros at | 2124109 | Brgy. Lokeb Este, Malasiqui
Repair/maintenance of Provincial Roads | 500000 | w/in the Province
Asphalting/blocktopping of Brgy. Mancasuy Rd., | 1411100 | Binalonan
Reconstruction of Baritao Bridge, | 6198991 | Brgy. Baritao, Manaoag
Asphalt of Brgy. Allabon Road, | 1972600 | Agno
Asphalting of Langka St., | 1268100 | Brgy. San Jose, Alaminos City
Concreting of Beleng Rd., Brgy. Beleng, | 1911221 | Bayambang
Concreting of Macayo-cayo, | 1810000 | Bayambang
Asphalting of Brgy. Catalina Rd., | 936820 | Binalonan
Blocktopping of Brgy. Cili Rd., | 1316300 | Binalonan
Asphalting of access road of Dasol Community Hospital and Dasol Breeding Station, | 925800 | Dasol
Blocktopping/patching of Brgy. Road, | 1774100 | Brgy. Butao, Malasiqui
Concreting of Sitio Bay-bay Rd. at | 2071229 | Brgy. Banaoang, Malasiqui
Blocktopping of Teofilo Visperas to Meliton Enriquez Rd., | 1892200 | Brgy. Banaoang, Mangaldan
10 drums E. Asphalt and 322 MT Asphalt Pre-mix for blocktopping of Siti Ragas at | 1915000 | Brgy. Andangin, Mangatarem
Blocktopping of Brgy. Magsaysay Rd., | 1742400 | San Jacinto
Concreting of Brgy. Barangobong Rd., | 610802 | Tayug
Concreting of Purok 1 Rd., | 487000 | Brgy. Trenchera, Tayug
Concreting of Purok 1 and 3 Road., | 542498 | Brgy. Libertad, Tayug
Concreting of Brgy. Amistad Rd., | 667800 | Brgy. Amistad, Tayug
Concreting of Brgy. Evangelista Rd., | 476766 | Tayug
Asphalting of Carosalesan-Aloo Road, | 2818000 | Umingan
Concreting of Sitio Valdez Rd., | 2047666 | Brgy. Dalanguiring, Urbiztondo
Concreting of Sitio Pinac-Bato Rd., | 1823233 | Brgy. Baug, Urbiztondo
Asphalting/blocktopping of Brgy. Dilan Paurino | 2229800 | Urdaneta City
Amortization of Principal and Interest on Loan to the LBP | 96683454.99
Loans Granted to Multi-Purpose Cooperative/ Livelihood Associations | 3730000
Environmental Development

## 2ndQTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) | Avenida Rizal, Lingayen | 6111593 | [6 empty] | 2441183.78 | 40% | Cont. 7/20/17
Improvement/extension of Day Care Center | Brgy. Sto. Tomas, San Jacinto | 504156 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the waterproofing of NRSCC Grandstand Bleachers | NRSCC Cmpd (Area-1867 sq.m.) Lingayen | 4437467 | [6 empty] | 2299212.73 | 51.89% | Cont. 7/3/17
Labor, materials, equipment and other incidentals for the construction of Senior Citizen Bldg. | Brgy. Bacag, Villasis | 900350 | [6 empty] | 754501.15 | 84.15% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the provision of fixed cover and manhole for drainage canal | Capitol Cmpd., Lingayen | 523163 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the concreting of as per Extra Work No. 2 | Malasiqui-Catablan Road, Malasiqui, Pangasinan | 20311.65 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the improvement of Bautista Municipal Plaza, | Poblacion East, Bautista | 3000000 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Power house and Installation of MCB Panel, Main Feeder Line at Burgos Rehabilitation Center, | Burgos, Pangasinan | 950807.11 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the reconstruction of Gymnasium at PPH Bolingit, | San Carlos city | 2233078 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the extension of swimming pool warm up area w/ shade at NRSCC Cmpd, | Lingayen | 1131044 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the the proposed construction of drainage canal at Pozorrubio Com. Hospital, | Pozorrubio | 729856 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the relocation of pole and installation 37.5 KVA of private distribution transformer | San Vicente, Burgos | 164799.84 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the additional work for the repair/rehabilitation of Multi-Purpose Hall | Brgy. Ketegan, Bautista | 162935 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station, | San Quintin | 552931 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Provincial Bus Terminal at , as per Extra Work Order No.1 | Motorpool Cmpd., Lingayen | 202528.47 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the repair/renovation of Old Female Cell Bldg. #1 & Fabrication of Steel Gate at | Pang. Provincial Jail, Lingayen | 448989 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the proposed Hall of Fame Bldg., , as per Extra Work #1 | Capitol Complex, Lingayen | 315472.79 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Multi-Purpose Bldg. | Brgy. Palma, Basista | 2167431 | [6 empty] | 865535.5 | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the construction of Facilitators' Quarters | Brgy. San Vicente, Burgos | 1524013 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the completion of Senior Citizen Bldg., | Brgy. Nibaliw Norte, Bautista | 706598 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of Pathway infront of Brgy. Hall | Palaming, San Carlos City | 226814 | [6 empty] | 224895.84 | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the proposed construction of CR (Male & Female) | Brgy. Nibaliw Norte, Bautista | 253895 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the proposed street lights | Brgy. Burgos-Padlan, San Carlos City | 400217 | [6 empty] | 397767.9 | 100% | Cont. 7/17/17
Labor, materials, equipment and other incidentals for the concreting of Multi-Purpose Pavement (Solar Dryer) | Brgy. Cabalitian, Asingan | 363484 |  |  | 100% | 360176.25 |  |  | 360176.25 | 100% | Cont. 6/6/17
Labor, materials, equipment and other incidentals for the construction of stage beside open court | Brgy. Galarin, Urbiztondo | 396110 | [6 empty] | 393699.75 | 100% | Cont. 7/17/17
Various materials for repainting of water Tank Bldg., | Motor Pool Cmpd., Lingayen | 94132 | [8 empty] | Obligated
Labor, materials, and other incidentals for the construction of Drainage Canal | Casa Real Cmpd. (back of Prov'l Jai), Lingayen | 260876 | [8 empty] | Obligated
Labor, materials, and other incidentals for the construction of Drainage Canal | Casa Real Cmpd. (back of Prov'l Jai), Lingayen | 234871 |  |  | 100% | 232892.59 |  |  | 232892.59 | 100% | Cont. 6/28/17
Labor, materials, equipment and other incidentals for the construction/installation of Street lights at | Brgy. Turko, Laoac | 219600 | [8 empty] | Obligated
Labor, materials, and other incidentals for the improvement/rehabilitation of Municipal Hall, , as per Extra Work Order No. 1 | Bugallon | 379886.96 | [8 empty] | Obligated
100 units 7 HP air cooled diesel engine couple w/ 3" diameter pump with accessories | Province of Pangasinan | 2400000 |  |  | 100% | 2398000 |  |  | 2398000 | 100% | Cont. 6/13/17
Engine pumpset and other incidentals for the installation of 20 units STWIP (Open Well) | Province of Pangasinan | 704550 | [6 empty] | 701736 | 100% | Cont. 7/13/17
Labor, materials, equipment and other incidentals for the installation of 57 units of STWIP of | various barangays and Municipality of Pangasinan, District I-IV | 4170996.09 |  |  | 100% | 4164429.69 |  |  | 4164429.69 | 100% | Cont. 5/26/17
3 sets of diesel engine | Province of Pangasinan | 159000 | [8 empty] | Obligated
rehabilitation/construction of SIKLING DAM, | Brgy. Bongalon, Labrador | 1733459.53 | [8 empty] | Obligated
construction of New Water Sourc | Dasol Community Hosp., Dasol | 790700
construction of 1 Artesian Well at | Sitio Tebag, Brgy. Diaz, Umingan | 63559
drilling/construction of well sourc (w/ pumpng machinery and elevated stell tank) | Baluyot, Bautista | 1818453.7
construction of two (2) units Artesian Well (w/ excavation) at | San Eugenio, Natividad | 183100
2 and 10 rolls 1" dia. PE Pipe SDR 11 and 3/4" dia. PE Pipe SDR 11, respectively, for the provision of PE Pipe for connection of potable drinking water at | Brgy. Babuyan, Infanta | 79500
construction of Well Source (6" diam casing 120 M depth) (A) Drilling works and well development at | Dasol Community Hospital | 54000
construction of 10 Artesian Wells w/ jetmatic Pumphead at | Brgy. Binabalian, Bolinao | 133115
concreting of Sitio Senenche Extension Farm to Market Road | Brgy. Pogonsili, Aguilar | 2218823 | [6 empty] | 2210648 | 100% | Cont. 6/20/17, 7/11/17
13 drums Emulsified Asphalt and 428 MT Asphalt Pre-mix in blocktopping | Brgy. Luyan Road (Acacia Ave. & Chico Ave.), Mapandan | 2541200 |  |  | 100% | 2534455 |  |  | 2534455 | 100% | Cont. 6/20/17
rehabilitation of Taculit Bridge II (Super Structure Only) at , as per extra work #1 | San Fabian | 134438.05 | [8 empty] | Obligated
rehabilitation of Taculit Bridge I (Super Structure Only) at , as per extra work #1 | San Fabian | 134438.05 | [8 empty] | Obligated
concreting of Carmay West Brgy. Road, | Rosales | 1082600 | [8 empty] | Obligated
retrofitting of Ramos Bridge, | Urbiztondo | 10000000 | [6 empty] | 5997142.39 | 60% | Cont. 7/18/17
retrofitting of Zaragosa Bridge (L=18 mtrs.) | Bolinao | 5800000 | [8 empty] | Obligated
asphalting of Angarian-Banaga Section, | Bugallon | 671500 | [6 empty] | 671173 | 100% | Cont. 7/18/17
asphalting of Sitio Nankumpapueyan Road at | Brgy. Laoag, Aguilar | 2041500 | [8 empty] | Obligated
blocktopping of Brgy. Road | Brgy. Matalava, Lingayen | 811100 | [6 empty] | 810689 | 100% | Cont. 7/18/17
blocktopping of Municipal Cemetery Road, | Bautista | 908000 | [8 empty] | Obligated
asphalting/blocktopping of | Sitio IdolIdol Road, Calasiao | 1131400 | [8 empty] | Obligated
blocktopping of Sitio Calay at | Brgy. Lomboy, Binmaley | 957500 | [6 empty] | 956856 | 100% | Cont. 7/18/17
Asphalting of Brgy. Sumabnit, | Binalonan | 2676464 | [8 empty] | Obligated
asphalting of Angela Valdez Ramos NH/S, | Asingan | 889400 | [8 empty] | Obligated
constructuon of Hanging Bridge, as per Extra Work #1 | Brgy. Garrita, Bani | 130135.43 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the construction of drainage system at Don Canuto St., | Brgy. Domalandan West, Lingayen | 1077654 | [8 empty] | Obligated
Labor, materials, equipment and other incidentals for the improvement/rehabilitation of Kinabalutan Bridge, Superstructure only (flat slab) at | Brgy. Matulong, Manaoag | 1770551 | [8 empty] | Obligated
costruction of CHB Drainage | Brgy. Poblacion, Binmaley | 2360049 | [6 empty] | 1177790.6 | 50% | Cont. 7/17/17
concreting of Sito Beros | Brgy. Lokeb Este, Malasiqui | 2124109 | [8 empty] | Obligated
repair/maintenance of Provincial Roads | w/in the Province | 500000 | [8 empty] | Obligated
reconstruction of Baritao Bridge, | Brgy. Baritao, Manaoag | 6198991 | [8 empty] | Obligated
Asphalt of Brgy. Allabon Road, | Agno | 1972600 | [8 empty] | Obligated
Asphalting of Langka St., | Brgy. San Jose, Alaminos City | 1268100 | [8 empty] | Obligated
concreting of Beleng Rd., | Brgy. Beleng, Bayambang | 1911221 | [8 empty] | Obligated
concreting of Macayo-cayo, | Bayambang | 1810000 | [8 empty] | Obligated
Asphalting/blocktopping of Brgy. Mancasuy Rd., | Binalonan | 1411100 | [8 empty] | Obligated
Asphalting of Brgy. Catalina Rd., | Binalonan | 936820 | [8 empty] | Obligated
blocktopping of Brgy. Cili Rd. | Binalonan | 1316300 | [8 empty] | Obligated
asphalting of access road of Dasol Community Hospital and Dasol Breeding Station, | Dasol | 925800 | [8 empty] | Obligated
blocktopping/patching of Brgy. Road, Brgy. Butao, | Malasiqui | 1774100 | [8 empty] | Obligated
concreting of Sitio Bay-bay Rd. | Brgy. Banaoang, Malasiqui | 2071229 | [8 empty] | Obligated
blocktopping of Teofilo Visperas to Meliton Enriquez Rd., | Brgy. Banaoang, Mangaldan | 1892200 | [8 empty] | Obligated
10 drums E. Asphalt and 322 MT Asphalt Pre-mix for blocktopping of Siti Ragas | Brgy. Andangin, Mangatarem | 1915000 | [8 empty] | Obligated
Blocktopping of Brgy. Magsaysay Rd., | San Jacinto | 1742400 | [8 empty] | Obligated
Concreting of Brgy. Barangobong Rd., | Tayug | 610802 | [8 empty] | Obligated
Concreting of Purok 1 Rd., | Brgy. Trenchera, Tayug | 487000 | [8 empty] | Obligated
Concreting of Purok 1 and 3 Road., | Brgy. Libertad, Tayug | 542498 | [8 empty] | Obligated
Concreting of Brgy. Amistad Rd., | Brgy. Amistad, Tayug | 667800 | [8 empty] | Obligated
Concreting of Brgy. Evangelista Rd., | Tayug | 476766 | [8 empty] | Obligated
Asphalting of Carosalesan-Aloo Road, | Umingan | 2818000 | [8 empty] | Obligated
Concreting of Sitio Valdez Rd., | Brgy. Dalanguiring, Urbiztondo | 2047666 | [8 empty] | Obligated
Concreting of Sitio Pinac-Bato Rd., | Brgy. Baug, Urbiztondo | 1823233 | [8 empty] | Obligated
Asphalting/blocktopping of Brgy. Dilan Paurino, | Urdaneta City | 2229800 | [8 empty] | Obligated
Economic Development
Environmental Development

## 3rdQTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of covered court Gymnasium w/ 0.4m Floor Elevation | Brgy. San Leon Umingan | 2523679
Improvement/interior design for Hall of Fame Building | Capitol Complex, Lingayen | 5866581 |  |  | 40% | 2342591.86
13000 bags cement |  | 3900000
Completion/improvement of Municipal Hall | Calasiao, Pangasinan | 2715184
Improvement/rehabilitation of OR/DR and OB Gyne Ward at WPDH | Alaminos City | 4386528 |  |  | 50% | 2162662.67
Construction of covered court | Brgy. Tombod, Villasis, Pangasinan | 2135007
Construction of covered court (Gymnasium, Concrete Post) Palisoc | Brgy. Palisoc, Bautista, Pangasinan | 2102206
Construction of Municipal Stage, Calasiao Municipal Plaza | Calasiao, Pangasinan | 2858490 |  |  | 80% | 2146790.85
Proposed construction of Multi-Purpose Bldg., | Brgy. San Jose, Alaminos City | 1609006 |  |  | 100% | 1565814.05
Construction of Multi-Purpose Hall with covered pathway at NBI Office | Dagupan City | 1169970
Construction and Rehabilitation of Drainage Canal at Mangaldan Public Market, | Mangaldan, Pangasinan | 1185322
Construction of Multi-purpoose Bldg. (covered court) at Sagud Bahley, San Fabian | San Fabian, Pangasinan | 2392170.94 |  |  | 100% | 2392170.94
Construction of Bleacher at the Municipal Plaza | Calasiao, Pangasinan | 4089571.2 |  |  | 100% | 4089571.2
Rehabilitation of Bleachers, shower rooms, comfort rooms and fence at swimming pool, NRSCC | Lingayen, Pangasinan | 1879825.97 |  |  | 100% | 1879825.97
Rehabilitation and repair of Drainage and elevation of concrete pavement at Zone 4, Pangapisan Sur | Lingayen, Pangasinan | 2344069.25 |  |  | 40% | 937627.7
Construction of cover court in Brgy. Plaza at Brgy. Carosuca Sur, | Asingan, Pangasinan | 2325964.11 |  |  | 100% | 2325964.11
Construction of Multi-purpose Hall 2-Storey Bldg. at Brgy. Labney | San Jacinto | 1543985.3 |  |  | 100% | 1543985.3
Improvement of 2-storey Multi-Purpose Bldg., (Brgy. Hall) at Brgy. Magallanes (Phase 1) | Tayug, Pangasinan | 2094367.42 |  |  | 60% | 1256620.45
Improvement/extension of Municipal Hall Bldg. | Bugallon, Pangasinan | 5799966.25 |  |  | 50% | 2613442.85
Labor, materials, equipment andother incidentals for the improvement/rehabilitation of existing Bachelor Officers Quarter (BOQ) into Senior Officers Quarter (SOQ) Avenida Rizal | Lingayen, Pangasinan | 6102959.46 |  |  | 70% | 4272071.62
Extension of swimming pool warm up area w/ shade at NRSCC Cmpd, Lingayen , @100%, part of 294,651.78 is charged to 3917, Revised CP:1195956.06 | Lingayen, Pangasinan | 1126630.36 |  |  | 100% | 1126630.36
Repair/rehabilitation of Goat Shed 7m x 18m at OPVET San Quintin Breeding Station | San Quintin, Pangasinan | 549779.26 |  |  | 100% | 549779.26
Construction/rehab of various facilities for Drug Rehabilitation Center | Brgy. San Vicente, Burgos, Pangasinan | 2274320.35 |  |  | 100% | 2274320.35
Construction of Multi-Purpose Bldg. | Brgy. Palma, Basista, Pangasinan | 2163838.76 |  |  | 100% | 2163838.76
Construction of Facilitators' Quarters at Brgy. San Vicente, | Burgos, Pangasinan | 1519183.56 |  |  | 100% | 1519183.56
Construction/installation of Street lights at Brgy. Turko, | Laoac, Pangasinan | 217492.87 |  |  | 100% | 217492.87
Construction of Day Care Center | San Bonifacio, San Manuel, Pangasinan | 737523.02 |  |  | 100% | 737523.02
Repair and rehabilitation of Building at OPAG Field Office | Brgy. Mamabobo, Mangatarem, Pangasinan | 306008.2 |  |  | 100% | 306008.2
Construction of 2 units deep well with jetmatic pumpheads | Brgy. Mantacdang, Umingan, Pangasinan | 113746.07 |  |  | 100% | 113746.07
Construction of stone masonry | Brgy. Guibel, San Jacinto | 674179.31 |  |  | 100% | 674179.31
Asphalting of Angela Valdez Ramos NH/S | Asingan, Pangasinan | 888962 |  |  | 100% | 888962
Costruction of CHB Drainage at Brgy. Poblacion, | Binmaley, Pangasinan | 2355581.2 |  |  | 100% | 2355581.2
Labor, materials, equipment and other incidentals for the construction of Drainage Canal (CHB) w/ RCCP | Brgy. Calit, Binmaley, Pangasinan | 1723800
Improvement (Raising and Concreting) of Brgy. Gayaman Road (L=200m;W=4.0) | Binmaley, Pangasinan | 2001600 |  |  | 60% | 1178596.79
6 units, 47-seaters, 12-meter bus |  | 39000000
2 units Coaster Bus |  | 8000000
1 unit Hospital Mobile Bus |  | 10000000
2 units Van |  | 4000000
3 units Ambulance |  | 6900000
1 unit Water Truck |  | 4000000
5 units Close Van |  | 10000000
2 units Mini Dump Truck |  | 8000000
1 unit Garbage Compactor |  | 4000000
1 unit plate compactor |  | 1350000
1 unit dredging machine |  | 70000000
3 units mini Vibratory Roller |  | 5700000
1 unit Man lift |  | 9000000
2 units pick-up Vehicle |  | 3200000
2 units Service Vehicle |  | 2000000
Waterproofing of walls and floor topping of GSO Basement Area, Capitol Bldg. | Lingayen, Pangasinan | 1296540 |  |  | 100% | 1296540
Construction of Provincial Shuttle Bus Terminal, Motorpool Cmpd., | Lingayen, Pangasinan | 8188336.39 |  |  | 90% | 7369502.75
Labor, materials, equipment and other incidentals for the construction of Training Center #2, Capitol | Lingayen, Pangasinan | 6294300.89 |  |  |  | 6294300.89
Economic Development
Asphalting of Abalos St., Brgy. Estanza | Lingayen, Pangasinan | 734928 |  |  | 100% | 734928
Construction of hanging bridge | Brgy. Garrita, Bani, Pangasinan | 2166649.13 |  |  | 100% | 2166649.13
Concreting of Brgy. Pita Road | Brgy. Pita Road, Infanta, Pangasinan | 1496568.25 |  |  | 100% | 1496568.25
Concreting of farm to market road, | Brgy. Dorongan Sawat, Mangatarem, Pangasinan | 2539924.54 |  |  | 100% | 2539924.54
Concreting of Maligaya-Sitio Banaolan Rd., Brgy. Palaming | San Carlos City | 2217194.75 |  |  | 100% | 2217194.75
Concreting of Brgy. Panakol Road | Aguilar, Pangasinan | 1917898.95 |  |  | 100% | 1917898.95
Asphalting of Baruan Road, Brgy. Baruan, | Agno, Pangasinan | 3931340 |  |  | 100% | 3931340
Concreting of Porok Ilang-ilang Road, Dahlia Road, Rosal Road at Brgy. Buer | Aguilar, Pangasinan | 2145847.44 |  |  | 100% | 2145847.44
Concreting of Farm to Market Road Sitio Guilig, Guevara Road, Brgy. Guesang | Mangaldan, Pangasinan | 1922337.75 |  |  | 100% | 1922337.75
Improvement (patching/blocktopping) of various provincial Roads | Pangasinan | 10009970 |  |  | 100% | 10009970
Improvement (concreting) of road at Mendoza St. | Brgy. Libsong West, Lingayen | 1924508.74 |  |  | 90% | 1571712.97
Concreting of Sitio Senenche Extension Farm to Market Road | Brgy. Pogonsili, Aguilar | 2210648 |  |  | 100% | 2210648
Retrofitting of Ramos Bridge | Urbiztondo, Pangasinan | 9995237.32 |  |  | 100% | 9995237.32
Retrofitting of Zaragosa Bridge (L=18 mtrs.) | Bolinao, Pangasinan | 5795773.79 |  |  | 100% | 5795773.79
Asphalting of Angarian-Banaga Section | Bugallon, Pangasinan | 671173 |  |  | 100% | 671173
Blocktopping of Brgy. Road at Brgy. Matalava, Lingayen | Lingayen, Pangasinan | 810689 |  |  | 100% | 810689
Blocktopping of Sitio Calay at Brgy. Lomboy | Binmaley, Pangasinan | 956856 |  |  | 100% | 956856
Concreting of Sitio Bay-bay Rd. | Brgy. Banaoang, Malasiqui, Pangasinan | 2067818.84 |  |  | 100% | 2067818.84
Concreting of Brgy. Barangobong Rd., | Tayug, Pangasinan | 608271.15 |  |  | 100% | 608271.15
Concreting of Brgy. Evangelista Rd., | Tayug, Pangasinan | 475666.07 |  |  | 100% | 475666.07
Blocktopping of Ignacio St., at Brgy. Poblacion West, | Asingan, Pangasinan | 576700 |  |  | 100% | 576409
Concreting of Farm to Market Road Located at Purok 7 Brgy. Bactad East | Urdaneta City | 1999054 |  |  | 100% | 1997883
Concreting of Joves Farm to Market Road w/ RCCP | Brgy. Macabito, Calasiao | 1878336
Asphalting/blocktopping of Road (Circumferential Area) | Brgy. Poblacion, Anda, Pangasinan | 2541700
Construction of Sitio Don Juan Extension Farm to Market Road w/ RCCP | Brgy. Cabiocaan Calasiao, Pangasinan | 1931720
Asphalting of Rose Street and Caimito St., | Mapandan, Pangasinan | 2807800
Concreting of Sitio Centro-Sitio Talsi Road, Brgy. Antipangol | San Carlos City | 2247008
Patching/blocktopping of Anda Tori-Tori Road | Anda, Pangasinan | 1837200
Asphalting of Access Road at NRSCC, Lingayen | Lingayen, Pangasinan | 270800 |  |  | 100% | 270624
500 MT Asphalt Pre-mix and 25 drums E. Asphalt 9(SS-1) for use in the maintenance/repair of various provincial roads and bridges | Pangasinan | 3110000
Asphalting/blocktopping of Duyala St. | Mangaldan, Pangasinan | 2130000
Environmental Development

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th Quarter, CY 2017
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Construction of Multi-purpoose Bldg. (covered court) | Sagud Bahley, San Fabian | 2392170.94 | 2017-03-19 | 2017-05-08 | 100% | 2392170.94
Construction of Bleacher at the Municipal Plaza | Calasiao | 4089571.2 | 2017-03-19 | 2017-07-13 | 100% | 4089571.2
Rehabilitation and repair of Drainage and elevation of concrete pavement at | Zone 4, Pangapisan Sur, Lingayen | 2344069.25 | 2017-04-06 | 2017-08-18 | 100% | 2344069.25
Construction of cover court in Brgy. Plaza | Brgy. Carosuca Sur, Asingan | 2325964.11 | 2017-04-06 | 2017-07-13 | 100% | 2325964.11
Construction of Multi-purpose Hall 2-Storey Bldg. | Brgy. Labney, San Jacinto | 1543985.3 | 2017-05-14 | 2017-08-14 | 100% | 1543985.3
Improvement/extension of Municipal Hall Bldg., | Bugallon | 2613442.85 | 2017-05-14 | On-going | 72% | 2899983.13
Waterproofing of NRSCC Grandstand Bleachers at NRSCC Cmpd (Area-1867 sq.m.) | Lingayen | 4430936.07 | 2017-06-05 | 2017-08-01 | 100% | 4430936.07
Provision of fixed cover and manhole for drainage canal | Capitol Cmpd., Lingayen | 519968.15 | 2017-06-21 | 2017-08-10 | 100% | 519968.15
Improvement of Bautista Municipal Plaza, | Poblacion East, Bautista | 2995486.96 | 2017-07-27 | 2017-09-30 | 100% | 2995486.96
Proposed construction of drainage canal at Pozorrubio Com. Hospital, | Pozorrubio | 726728.42 | 2017-07-25 | 2017-09-07 | 100% | 726728.42
Construction of covered court Gymnasium w/ 0.4m Floor Elevation | Brgy. San Leon Umingan | 2517276.19 | 2017-08-29 | On-going | 75% | 1887957.14
Improvement/interior design for Hall of Fame Building at Capitol Complex, | Lingayen | 5856479.66 | 2017-08-24 | On-going | 90% | 5270831.69
Improvement/rehabilitation of OR/DR and OB Gyne Ward at WPDH, | Alaminos City | 4325325.34 | 2017-08-24 | On-going | 90% | 3460260.27
Construction of Municipal Stage at Calasiao Municipal Plaza, | Calasiao | 2683488.56 | 2017-08-24 | 2017-10-09 | 100% | 2683488.56
Construction of Multi-Purpose Bldg. | Brgy. San Jose, Alaminos City | 1565814.05 | 2017-09-06 | 2017-10-23 | 100% | 1565814.05
Construction of Multi-Purpose Hall with covered pathway at NBI Office | Dagupan City | 1160303.46 | 2017-08-14 | 2017-11-03 | 100% | 1160303.46
Construction of Day Care Center with CR and Lavatory | Brgy. Cabarabuan, Mangatarem | 935577.99 | 2017-08-15 | Oct. 2017 | 100% | 935577.99
Construction of Multi-Purpose Bldg. | Brgy. Palma, Basista | 2163838.76 | 2017-05-25 | 2017-10-20 | 100% | 2163838.76
Construction of Tricycle Terminal | Poblacion, San Fabian | 1881919.64 | 2017-08-23 | 2017-11-02 | 100% | 2084491.45
Construction of Multi-Purpose Bldg., | Logolog, Baybay Sur, Sual | 466424.44 | 2017-10-18 | On-going | 50% | 466427.44
Preventive maintenance of Provicial Jail (Repair and repainting of Exterior Walls and Ceiling) | Lingayen | 234380.21 | 2017-08-30 | 2017-10-02 | 100% | 234380.21
Repair, repainting of Walling, Lavatory, and roofing at Dialysis Center, | PPH, San Carlos City | 188998.98 | 2017-09-20 | 2017-10-09 | 100% | 188998.98
Improvement (repainting of Perimeter Fence) at Lingayen District Hospital, | Lingayen | 256142.39 | 2017-09-20 | 2017-10-16 | 100% | 256142.39
Labor, materials, equipment and other incidentals for the repair/improvement of PAGO Bldg., at Nursery Tebag Sta. Barbara |  | 532343.28 | 2017-09-09 | 2017-10-19 | 100% | 532343.28
Construction of Waiting Area with Male and Female CR at Bolinao Community Hospital, | Bolinao | 523285.08 | 2017-09-20 | 2017-10-12 | 100% | 523285.08
Construction of Mini Chapel at Bayambang Dist. Hospital, | Bayambang | 544733.73 | 2017-09-25 | 2017-10-23 | 100% | 544733.73
Provision of pediment w/ extended roofing (covered court) & Hanging Basketball Board Framing | Poblacion, Basista | 646770.48 | 2017-09-20 | 2017-10-17 | 100% | 646770.48
Repair of stage at Dona Aurea E/S Sports Ground, | Poblacion, Sto. Tomas | 250959.41 | 2017-11-01 | 2017-11-06 | 100% | 250959.41
Construction of Guard Tower | Brgy. San Vicente, Burgos | 477287.88 | 2017-11-20 | On-going | 36.55%
Concreting/upgrading of flooring at Pang. Provincial Jail, | Lingayen | 168008.74 | 2017-11-14 | 2017-12-01 | 100% | 168008.74
Construction of Multi-Purpose Hall | San Juan, San Manuel | 545360.49 | 2017-09-11 | 2017-11-29 | 100% | 545360.49
Construction of 5 units dugwell | Brgy. San Roque, San Manuel | 407094.08 | 2017-11-08 | Dec. 2017 | 100% | 407094.08
Construction of 2 units deep well | Brgy. Dusoc, Bayambang | 60956 | 2017-08-07 | 2017-09-26 | 100% | 60956
Construction of 10 Artesian Wells w/ jetmatic Pumphead | Brgy. Binabalian, Bolinao | 132995 | 2017-07-04 | 2017-07-28 | 100% | 132995
Construction of 2 units deep well with jetmatic pumpheads | Brgy. Evangelista, Umingan | 200866.15 | 2017-08-10 | 2017-09-08 | 100% | 200866.15
Construction of 2 units Artesian Well | Brgy. Prado, Umingan | 91894 | 2017-10-24 | 2017-12-24 | 100% | 91894
Construction of water system (drilling of Point of Source w/ installation of Motorpump and PVC distribution Pipeline) at Garita Nat'l High Sch. | Bani | 233566.31 | 2017-11-02 | 2017-11-02 | 100% | 233566.31
Construction of two(2) units Artesian Well | Brgy. Lomboy, Binmaley | 454689.24 | 2017-11-20 | On-going | 70%
Construction of two(2) units Artesian Well | Brgy. San Juan, Umingan | 377655.8 | 2018-01-12 | On-going | 30%
Construction of 1 unit, 3 chamber laundry septic tank at EPDH, | Tayug | 166193 | Not yet started
Construction of Artesian Well Projects at Waterworks Section , Motorpool Cmpd., | Lingayen | 135246 | Not yet started
Construction of Drainage Canal (CHB) w/ RCCP | Brgy. Calit, Binmaley | 1718600.94 | 2017-09-26 | 2017-12-22 | 100% | 1718600.94
Labor, materials, equipment and other incidentals for the construction of Provincial Shuttle Bus Terminal, Motorpool Cmpd., Lingayen (Revised CP: P8390864.86, part charged to 2017-6911) |  | 8188336.39 | 2017-03-08 | 2017-10-30 | 100% | 8188336.39
Economic Development
Concreting of Farm to Market Road | Brgy. Calaocan, San Nicolas | 2527756.62 | 2017-05-04 | 2017-06-22 | 100% | 2527756.62
Concreting of Maligaya-Sitio Banaolan Rd. | Brgy. Palaming, San Carlos City | 2217194.75 | 2017-04-16 | 2017-07-03 | 100% | 2217194.75
5 drum E. Asphalt & 110 MT Asphalt Pre-mix for asphalting | Brgy. Sto. Tomas Road, San Jacinto | 676975 | 2017-09-14 | 2017-09-14 | 100% | 676975
Improvement (concreting) of road at Mendoza St. | Brgy. Libsong West, Lingayen | 1746347.74 | 2017-05-14 | 2017-10-20 | 100% | 1746347.74
Concreting of Carmay West Brgy. Road, | Rosales | 1075526.95 | 2017-06-05 | 2017-07-28 | 100% | 1075526.95
11 drums E. Asphalt and 253 Asphalt Pre-mix for the Asphalting | Brgy. Sumabnit, Binalonan | 1545830 | 2017-06-15 | 2017-06-21 | 100% | 1545830
Construction of drainage system | Don Canuto St., Brgy. Domalandan West, Lingayen | 1073486.6 | 2017-06-27 | 2017-07-20 | 100% | 1073486.6
Costruction of CHB Drainage | Brgy. Poblacion, Binmaley | 2355581.2 | 2017-06-27 | 2017-09-18 | 100% | 2355581.2
9 drums E. Asphalt and 207 MT of Asphalt Pre-mix for the Asphalting | Langka St., Brgy. San Jose, Alaminos City | 1263690 | 2017-11-22 | 2017-11-24 | 100% | 1263690
Concreting of Beleng Rd. | Brgy. Beleng, Bayambang | 1889440.89 | 2017-08-20 | 2017-10-02 | 100% | 1889440.89
Labor, materials, equipment and other incidentals for the concreting of Macayo-cayo | Bayambang | 1804422.59 | 2017-08-20 | 2017-09-26 | 100% | 1804422.59
9 drums E. Asphalt and 233 MT of Asphalt Pre-mix for the Asphalting/blocktopping | Brgy. Mancasuy Rd., Binalonan | 1407380 | 2017-10-27 | 2017-11-03 | 100% | 1407380
7 drums E. Asphalt and 152 MT Asphalt Pre-mix for the Asphalting | Brgy. Catalina Rd., Binalonan | 936695 | 2017-09-29 | 2017-10-02 | 100% | 936695
7 drums E. Asphalt and 221 MT Asphalt Pre-mix for the blocktopping | Brgy. Cili Rd., Binalonan | 1312810 | 2017-10-02 | 2017-11-11 | 100% | 1312810
150 MT of Asphalt Pre-mix and 7 drums of E. Asphalt for the asphalting of access road of Dasol Community Hospital and Dasol Breeding Station | Dasol | 925709 | 2017-10-30 | 2017-11-03 | 100% | 925709
299 MT Aspalt Pre-mix and 9 drums E. Asphalt use in blocktopping/patching | Brgy. Road, Brgy. Butao, Malasiqui | 1767850 | 2017-08-08 | 2017-08-10 | 100% | 1767850
Concreting of Sitio Bay-bay Rd. at | Brgy. Banaoang, Malasiqui | 2067818.84 | 2017-08-20 | 2017-10-02 | 100% | 2067818.84
310 MT Aspalt Pre-mix and 13 drums E. Asphalt use in blocktopping of Teofilo Visperas to Meliton Enriquez Rd. | Brgy. Banaoang, Mangaldan | 1887225 | 2017-07-11 | 2017-07-14 | 100% | 1887225
10 drums E. Asphalt and 322 MT Asphalt Pre-mix for blocktopping of Siti Ragas | Brgy. Andangin, Mangatarem | 1908260 | 2017-08-09 | 2017-08-15 | 100% | 1908260
11 drums E. Asphalt and 288 MT Asphalt Pre-mix for the blocktopping | Brgy. Magsaysay Rd., San Jacinto | 1737805 | 2017-09-05 | 2017-09-11 | 100% | 1737805
Concreting of Purok 1 Rd. | Brgy. Trenchera, Tayug | 484611.34 | 2017-08-02 | 2017-08-14 | 100% | 484611.34
Concreting of Purok 1 and 3 Road., | Brgy. Libertad, Tayug | 540799.61 | 2017-08-02 | 2017-08-11 | 100% | 540799.61
Concreting of Brgy. Amistad Rd., | Brgy. Amistad, Tayug | 665454.31 | 2017-08-02 | 2017-08-14 | 100% | 665454.31
Concreting of Brgy. Evangelista Rd., | Tayug | 475666.07 | 2017-08-02 | 2017-08-14 | 100% | 475666.07
160 MT Bituminous Concrete Surface Course and 20 drums Bituminous Prime Coat for the asphalting of Carosalesan-Aloo Road | Umingan | 2810600 | 2017-08-14 | 2017-08-29 | 100% | 2810600
Concreting of Sitio Valdez Rd., | Brgy. Dalanguiring, Urbiztondo | 2045910.65 | 2017-08-20 | 2017-09-30 | 100% | 2045910.65
Concreting of Sitio Pinac-Bato Rd., | Brgy. Baug, Urbiztondo | 1821522.69 | 2017-08-20 | 2017-09-23 | 100% | 1821522.69
12 drums E. Asphalt and 374 MT Asphalt Pre-mix for the Asphalting/blocktopping | Brgy. Dilan Paurino, Urdaneta City | 2223890 | 2017-11-07 | 2017-11-17 | 100% | 2223890
Concreting of Farm to Market Road Located at Purok 7 Brgy. Bactad East | Urdaneta City | 1997883 | 2017-08-24 | 2017-09-30 | 100% | 1997883
Construction of Sitio Don Juan Extension Farm to Market Road w/ RCCP | Brgy. Cabiocaan Calasiao | 1909356.02 | 2017-08-24 | 2017-10-10 | 100% | 1909356.02
466 MT of Asphalt Pre-mix and 17 drums of Emulsified Asphalt for the Asphalting of Rose Street and Caimito St., | Mapandan | 2802885 | 2017-10-12 | 2017-11-03 | 100% | 2802885
Labor, materials, equipment and other incidentals for the proposed concreting of Sitio Centro-Sitio Talsi Road, Brgy. Antipangol, San Carlos City |  | 2234255.07 | 2017-09-11 | 2017-12-19 | 100% | 2234255.07
13 drums E. Asphalt and 300 MT Asphalt Pre-mix for the patchin/blocktopping of Anda Tori-Tori Road, Anda |  | 1834005 | 2017-07-10 | 2017-08-29 | 100% | 1834005
44 MT Asphalt Pre-mix and 2 drums of E. Asphalt for the Asphalting of Access Road at NRSCC, | Lingayen | 270624 | 2017-09-14 | 2017-09-18 | 100% | 270624
Improvement (Raising and Concreting) of Brgy. Gayaman Road (L=200m;W=4.0) | Binmaley | 1964327.99 | 2017-09-26 | 2017-11-14 | 100% | 1964327.99
Rehabilitation of 1 unit box culvert (3x3x3x6m) at Castillo St., | Lingayen | 465699 | 2017-01-24 | On-going | 5% | 23284.95
322 MT Asphalt pre-mix and 10 drums E. Asphalt for the Asphalt/blocktopping of Canarem Road going to Barangobong and Burgos Rd, | Natividad | 1915000 | 2017-11-21 | 2017-11-28 | 100% | 1915000
Concreting of Sitio Ketegan Road | Brgy. Salud, Natividad | 2027531.21 | 2017-01-12 | 2017-12-11 | 100% | 2027531.21
Environmental Development
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA |  |  |  |  | HON. AMADO I. ESPINO, III
Provincial Accountant |  |  |  |  | Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of December 2017
Province of Pangasinan
LDRRMF
Particulars | Quick Response | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| Fund (QRF) | 70%
30%
A. Sources of Funds:
Current Appropriation | 52947060 | 123543140 |  |  |  | 176490200
Continuing Appropriation |  | 9512025 |  |  |  | 9512025
Previous Year's Appropriation transferred to the Special Trust Fund |  | 97152215.91 |  |  |  | 97152215.91
Transfers/Grants | [5 empty] | 0
Others Interest Income (Trust Fund) |  |  |  |  | 47401.69 | 47401.69
Total Funds Available | 52947060 | 230207380.91 | 0 | 0 | 47401.69 | 283201842.6
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies |  | 2673680 |  |  |  | 2673680
Office Supplies | [5 empty] | 0
Repair of Evacuation Center | [5 empty] | 0
Disaster Response & Rescue Equipment |  | 11389500 |  |  |  | 11389500
Institutional/Capacity Development (Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Capital Outlay - Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 7427325.95 |  |  |  | 7427325.95
Traveling Expense |  | 244884.5 |  |  |  | 244884.5
Training Expense |  | 163566.5 |  |  |  | 163566.5
IT Equipment & Software | [5 empty] | 0
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts |  | 8328643.5 |  |  |  | 8328643.5
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment |  | 20160985 |  |  |  | 20160985
Gasoline, Oil, Lubricants |  | 1065575.91 |  |  |  | 1065575.91
Drugs and Medicines |  | 5777480 |  |  |  | 5777480
Donations | [5 empty] | 0
Repair & Maintenance-Motor Vehicles |  | 651148.72 |  |  |  | 651148.72
Honorarium | [5 empty] | 0
Office Equipment |  | 168445 |  |  |  | 168445
Furnitures & Fixtures | [5 empty] | 0
Other Structures |  | 29457038 |  |  |  | 29457038
Other Transportation |  | 15978500 |  |  |  | 15978500
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. (Trust Fund) |  | 16596669.36 |  |  |  | 16596669.36
Repair & Maintenance - Building & Other Structures (Trust Fund) |  | 2169407.31 |  |  |  | 2169407.31
Bank Charges (Trust Fund) |  |  |  |  | 350 | 350
Total Utilization | 0 | 122252849.75 | 0 | 0 | 350 | 122253199.75
Unutilized Balance | 52947060 | 107954531.16 | 0 | 0 | 47051.69 | 160948642.85
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or
information contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending December 31, 2017
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 176333310.51
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
65580748.95
Capital Outlay
88479878.16
Financial Expenses
-0-
Sub-total |  |  |  | 154060627.11
Balance |  |  |  | 22272683.4
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO, III
Governor
Note on I11: Pangasinan Accounting:

## CASHFLOW
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the Fourth Quarter Ending December 31,2017
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 19739201.89
|  | Share from Internal Revenue Allotment |  | 740407315
|  | Receipts from business/service income |  | 142520964.92
|  | Interest Income |  | 1145951.89
|  | Other Receipts |  | 27450967.98
|  | Total Cash Inflow |  | 931264401.68
Cash Outflows:
|  | Payment of expenses |  | 321743837.83
|  | Payment to suppliers and creditors |  | 129494028.88
|  | Payment to employees |  | 238493816.49
|  | Interest Expenses |  | 11887055.63
|  | Other Expenses |  | 9579611.46
|  | Total Cash Outflow |  | 711198350.29
| Net Cas Flows from Operating Activities |  |  | 220066051.39
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
Proceeds from Sale of Biological Assets
|  | Collection of Principal on Loans to other Entities |  | 2340325
|  | Total Cash Inflow |  | 2340325
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 146868131.2
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 3100000
|  | Total Cash Outflow |  | 149968131.2
| Net Cash Flows from Investing Activities |  |  | -147627806.2
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 6846128.09
|  | Total Cash Inflow |  | 6846128.09
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 37869604.58
|  | Total Cash Outflow |  | 37869604.58
| Net Cash Flows from Financing Activities |  |  | -31023476.49
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 41414768.7
Add:Cash at Beginning of the Quarter |  |  |  | 1408039494.11
Cash at the End of the Quarter |  |  |  | 1449454262.81
Certified Correct:
ARTURO V. SORIANO,CPA
PROVINCIAL ACCOUNTANT

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE OCTOBER - DECEMBER QUARTER, CY 2017
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitation/Improvement/Upgrading of Burgos-Iliw-Iliw Road at Burgos, Pangasinan | Burgos, Pangasinan | 87957208.21 |  |  | 60% | 52774324.926 |  | fund from the Department of Interior and Local Government-CMGP; cost incurred in the quarter P18,839,831.17
Rehabilitation of Banaoang- Mapandan Road @ Sta. Barbara and Mapandan, Pangasinan | Sta. Barbara and Mapandan, Pangasinan | 45009579.52 |  |  | 70% | 31506705.664 |  | fund from the Department of Interior and Local Government-CMGP; cost incurred in the quarter P24,755,268.73
Hybrid Yellow Corn Seeds and Fertilizer Subsidy Project in support to the Agro-Industrial Enterprises Program | OPAg, Sta. Barbara, Pangasinan | 2999600 |  |  | 100% | 2999600 |  | fund from the Department of Agriculture - prize of Prov'l. Gov't. of Pangasinan as Outstanding Province to the CY 2016 National Quality Corn Achievers Awards
Certified Palay Seeds and Fertilizer Subsidy Project in support to the Agro-Industrial Enterprises Program | OPAg, Sta. Barbara, Pangasinan | 2497336 |  |  | 100% | 2497336 |  | fund from the Agricultural Training Institute Regional Training Center - prize of Prov'l. Gov't. of Pangasinan as Outstanding Province to the CY 2016 Rice Achievers Awards
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Centro Toma - Colayo Farmers Multi-Purpose Cooperative) | Centro Toma Bani, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Laguit Padilla Multi-Purpose Cooperative) | Laguit Padilla, Bugallon, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Saint Paschal Baylon Multi-Purpose Cooperative) | Poblacion, San Quintin, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Maresma Multi-Purpose Cooperative) | Balungao, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Tay-ak Marketing Cooperative) | Cabaruan, Umingan, Pangasinan | 962800 |  |  | 100% | 800000 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Mapolopolo Agrarian Reform Cooperative) | Mapolopolo, Basista, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP; cost incurred in the quarter P200,000.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Nayon Credit Cooperative) | Bantog, Umingan, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Bayanihan Hundred Islands ARC Cooperative) | Poblacion, Alaminos City, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Saranay Agrarian Reform Cooperative) | San Macario Sur, Natividad, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Capulaan Multi-Purpose Cooperative) | Capulaan, Villasis, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-GOP & LGU; cost incurred in the quarter P362,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Catuday AR Cooperative) | Catuday, Bolinao, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Southern Binmaley Multi-Purpose Cooperative) | Pallas, Binmaley, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Lambayan Multi-Purpose Cooperative) | Poblacion, Mapandan, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Catablan ARC Credit Cooperative) | Catablan, Urdaneta City, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Raniag Mantacdang Multi-Purpose Cooperative) | Mantacdang, San Quintin, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Atlas Mabuna Multi-Purpose Cooperative) | Lasip, Malasiqui, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Aramal Tococ FFF Multi-Purpose Cooperative) | Aramal, San Fabian, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
Implementation of the Farm Mechanization Service Facility under the PRDP - IREAP (1 unit Tractor with Cage Riller / Leveller, Rotary Tiller, and Trailer for Mapolopolo Agrarian Reform Cooperative) | Mapolopolo, Basista, Pangasinan | 962800 |  |  | 100% | 962800 |  | fund from the PRDP-IREAP-LGU; cost incurred in the quarter P162,800.00
TOTAL |  | 155794123.73 |  |  |  | 106945566.59
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## UNLIQUIDATED
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of December 31, 2017
Province, City or Municipality: | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 67600 |  |  | 0 | 0 | 0 |  |  | 67600
Advances to Special Disbursing
Rodolfo M. Cortez | 300000 | 1997-04-10 | [6 empty] | 300000
Rodolfo M. Cortez | 55800 | 1996-06-20 | [6 empty] | 55800
Sub-total | 355800 |  |  | 0 | 0 | 0 |  |  | 355800
GRAND TOTAL | 423400 | [7 empty] | 423400
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## ANNUAL DEBT SERVICE
LBP Form No.6
ANNEX "F"
Republic of the Phillippines
Province of Pangasinan
General Fund
For the Year 2018
| Date |  | Principal | Previous Payment |  |  | Amount Due |  |  | Balance of the
Creditor | Contracted | Term | Amount |  | Made |  | (Budget Year)* |  |  | Principal
|  |  |  | Principal | Interest | Total | Principal | Interest | Total
Land Bank of the | 2009-12-11 | 10 yrs | 149942779.08 | 115885692.22 | 40797639.95 | 156683332.17 | 17029043.4 | 2809737.16 | 19838780.56 | 34057086.86
Philippines | 2010-05-14 | 7 yrs | 97255640 | 97255640 | 24132252.31 | 121387892.31 | 6946831.44 | 187374.12 | 7134205.56 | 0
Dagupan Branch | 2009-12-17 | 10 yrs | 146278017.99 | 110571003.32 | 36930070.79 | 147501074.11 | 17878560.38 | 2949823.92 | 20828384.3 | 35707014.67
| 2012-11-29 | 10 yrs | 50228784.65 | 22323904.48 | 12264788.1 | 34588692.58 | 5580976.12 | 1841722.1 | 7422698.22 | 27904880.17
| 2012-11-29 | 10 yrs | 119020066.26 | 51667056.78 | 26960134.73 | 78627191.51 | 13470601.84 | 4445298.62 | 17915900.46 | 67353009.48
| 2014-03-28 | 10 yrs | 12300000 | 3758333.37 | 2476588.83 | 6234922.2 | 1366666.68 | 544958.33 | 1911625.01 | 8541666.63
| 2015-04-28 | 10 yrs | 6058050 | 6058050 | 415755.57 | 6473805.57 | 6165587.27 | 2882412.04 | 9047999.31 | 0
| 2015-04-28 | 10 yrs | 6657000 | 6657000 | 529545.94 | 7186545.94 | 5177666.68 | 2420559.17 | 7598225.85 | 0
| 2015-07-29 | 10 yrs | 349781754.22 | 47016300.73 | 26126899.02 | 73143199.75 | 41979605.08 | 20390505.61 | 62370110.69 | 302765453.49
| 10/21/2015 | 10 yrs | 85670199.47 | 6493861.94 | 8247591.24 | 14741453.18 | 10567405.56 | 5064929.26 | 15632334.82 | 79176337.53
| 12/21/2015 | 10 yrs | 77173324.25 | 7838833.51 | 5224643.27 | 13063476.78 | 9526424.56 | 4789655.84 | 14316080.4 | 69334490.74
| 2016-02-27 | 10 yrs | 95345424.1 | 7800186.08 | 6690121.78 | 14490307.86 | 7965682.8 | 5257350.63 | 13223033.43 | 87545238.02
| 1/29/2016 | 5 yrs | 50641600 | 17724560 | 3747045.34 | 21471605.34 | 10128320 | 2367494.8 | 12495814.8 | 32917040
| 9/27/2015 | 7 yrs | 36950000 | 11876785.74 | 3928088.67 | 15804874.41 | 5278571.44 | 1669348.21 | 6947919.65 | 25073214.26
| 2016-02-10 | 7 yrs | 91887000 | 22453673.06 | 7549340.98 | 30003014.04 | 13126714.26 | 4565225.89 | 17691940.15 | 69433326.94
[6 empty] | 0 | 0 | 0 | 0 | 0
| TOTAL |  | 1375189640.02 | 535380881.23 | 206020506.52 | 741401387.75 | 172188657.51 | 62186395.7 | 234375053.21 | 839808758.79
Certified Correct:
ARTURO V. SORIANO
Provincial Accountant