## 1QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2018
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | TOTAL COST | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[6 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Repair/improvement of Sison Auditorium | 2552943.75 | Lingayen, Pangasinan
Repainting works at NRSCC, Lingayen | 785197.88 | Lingayen, Pangasinan |  |  |  | 100% | 785197.88
Improvement of Sport Ground at Alaminos City National High School | 1702815 | Alaminos City
Replacement of roofing in rewiring of Main Bldg., Phase II, Mapandan Community Hospital | 6300682.88 | Mapandan, Pangasinan
Construction of perimeter fence at Dasol Community Hospital | 2147139 | Dasol, Pangasinan
Completion of Training Center II, Capitol Complex | 15979311 | Lingayen, Pangasinan
Renovation/improvement of Hazardous Waste Holding Facility | 1579067
Construction of 6 units PENRO Outpost within the Province | 2652208 | Within the Province
Proposed construction of Wharf | 2433133 | Brgy. Tori-Tori, Anda
Construction of drainage canal with concrete cover & CHB canal w/ stiffener | 5849415 | Arellano St., Bautista, Pangasinan
Construction of covered court (gymnasium | 3003950 | Brgy. San Felipe East, San Nicolas
Upgrading of Electrical System at PPH, Phase I | 15090761.88 | San Carlos City
Construction of 2-storey Bldg. for Health Center & Conference hall | 1775860 | Brgy. Cacandongan, Bautista, Pangasinan
Rehab of Upper Level Center Roof & Peeble Mesh out Flooring of Veteran's Park Museum Bldg., Veteran's Park | 536385 | Lingayen, Pangasinan
Upgrading/construction of Pedia Ward & Isolation Room Bldgs. At Lingayen Dist. Hospital | 1415632 | Lingayen, Pangasinan
Installation of Feederline for the New Medical Bldg. at Mangatarem Dist. Hospital | 979073 | Mangatarem, Pangasinan
Construction of OB-Gyne Bldg. at PPH | 3115000 | San Carlos City
Completion of municipal hall Bldg., | 7417774 | Bugallon, Pangasinan
Asphalt for PNHS, Lingayen Compound | 569100 | Lingayen, Pangasinan
Ground improvement of Reformation Center Compound (Landscaping) | 666878.66 | San Vicente, Burgos | 666878.66 |  |  | 100% | 666878.66
Construction of 3 units Guard Post and Installation of Lightings at Beachfront | 999732 | Lingayen, Pangasinan
Construction of Main Guard house and First Aide Post at the Beachfront, Capitol, Lingayen | 829448 | Lingayen, Pangasinan
Repair of old Isolation Room into CSSR, fabrication of tables and cabinets at Asingan Community Hospital | 261818.84 | Asingan, Pangasinan
Labor, materials and other incidentals for the improvement of Main Bldg. at Umingan Community Hospital | 732260.91 | Umingan, Pangasinan
Construction of Multi-Purpose Hall | 1824727 | Brgy. Bayoyong, Basista
Extension of concrete ditch at Motorpool Cmpd. | 961405 | Lingayen, Pangasinan
Rehabilitation of of Processing Bldg./Center at PAGO | 422618.98 | Sta. Barbara, Pangasinan
Construction of 2 units basketball board and flagpole at Pangasinan Reformation Center | 417990.83 | Burgos, Pangasinan
Renovation/improvement of various facilities at Pangasinan Reformation Center | 931556.94 | Brgy. San Vicente, Burgos, Pangasinan
Construction of covered court | 2284443.14 | Pogonsili, Aguilar
Completion of Pangasinan Corn Coordinating Center | 1392888 | San Gonzalo, San Quintin
Construction of Power House at Pangasinan Provincial Hospital | 924592 | San Carlos City
Electrical connection at Finance, Malong and ABC Bldgs., in the Province | 766576.75 | Lingayen, Pangasinan
Construction of 3-storey Multi-Purpose Bldg., (Phase 1) at Capitol Cmpd., Lingayen | 17000000 | Lingayen, Pangasinan
Construction of GSO Warehouse (Phase 1) at Capitol Cmpd., Lingayen | 23700000 | Lingayen, Pangasinan
Construction/Rehabilitation of various facilities at OPAG/OPVET | 6708120 | Brgy. Macabobo, Mangatarem
Construction of road at OPAG/OPVET at,(with Stone Masonry) | 3074849 | Brgy. Macabobo, Mangatarem
Construction of 3 units Artesian Well, | 195000 | San Vicente, San Manuel
Constrruction of 2 units Dug well | 339779.1 | Palapad, San Fabian
Constrruction of 2 units Dug well, | 310000 | Malokiat, Pozorrubio
Labor, materials, equipment for construction of breakwater | 5000000
Construction of 1 unit deep well | 491703.02 | Dulag, Binmaley
Construction of 2 units dug well | 303000 | Anda, Pangasinan
Various supplies/materials for the construction of 2 units Artesian Well | 56525 | Parac parac, San Fabian
Various supplies/materials for the construction of 2 units Artesian Well | 43052 | San Andres, Umingan
Various supplies/materials for the construction of 2 units Artesian Well | 56525 | Sagud Baley, San Fabian
Various materials for the construction of 2 units Artesian Well | 49371 | San Fabian
Construction of 2 units dug well | 224000 | Sitio San Pedro, San Macario, at Natividad
Construction of 2 units Artesian Well | 105354 | Brgy. San Pablo, Umingan
Installation of 2-units Point Sources Water System for Annual Youth Camp at Beachfront, Lagoon Area | 79754 | Lingayen
Economic Development
16 units, 8-horsepower, 4 diesel engine for irrigation projects | 688000 | Dist. III and V, Pangasinan
2 units water pump, to be awarded to the Brgy. Winners in the "Best in Community Garden" | 44000 | Bayambang, Pangasinan
Construction/installation of 40 units STWIP | 3166347.2 | various brgys and municipalities in the Province
Construction/installation of 40 units STWIP | 3166347.2 | Various brgys and municipalities in the Province
Livelihood Projects - Loans Granted to various Associations and MPC's | 2330000 | Pangasinan
Bamboos, fish, crablets and crab baskets for the grown-out culture of Mangrove crab as Aqua Culture Dishes Demo Project, Bolinao Fish Farm | 137787 | Bolinao, Pangasinan | 137787
Amortization of Principal and Interest on Loan to the LBP | 44833641.57 | Pangasinan
Repair/improvement of various roads | 2933500 | Within the Province of Pangasinan
Asphalting of Taketek and Panganiban Road | 5463075 | Tayug, Pangasinan | 5463075
Asphalt for Access Road, at Reformation Center | 1449180 | San Vicente, Burgos | 1449180
Asphalt for OPAG Main Entrance and Compound | 1316215 | Bolinao, Pangasinan | 1316215
Asphalt for the improvemet/blocktopping of municipal Roads sorrounding Auditorium | 2213300 | Poblacion, Burgos
Construction of 1 unit 2-barrel RCBC, Centro Pangapisan | 1171913 | Sual, Pangasinan
Concreting of Antipangal-Pangascasan Road | 1998000 | Bugallon, Pangasinan
Repair/Improvement of Balingasay Bridge | 2192575 | Bolinao, Pangasinan
Concreting of Fulgosimo Road | 2897840 | Umingan, Pangasinan
Improvement of Brgy. Road, Wawa | 2602800 | Lingayen, Pangasinan
Concreting of Brgy. Legaspi Road | 685708.41 |  | 685708.41
Asphalt for Blocktopping of Brgy. A. Alarcio Road | 1920890 | Laoac, Pangasinan | 1920890
Concreting of Villalon Rd., Zone 1 Flores | 2073074 | San Manuel, Pangasinan
Asphalt for blocktopping of Malilion, Sto. Tomas, Canangguan Road | 1898950 | San Nicolas, Pangasinan | 1898950
Construction of 1 unit 3-barrel RCBC, Brgy. Pangascasan | 1445335 | Sual, Pangasinan
Asphalt for the improvemet/blocktopping of Anambongan | 2600275 | Basista, Pangasinan | 2600275
Concreting of San Jacinto, Pozzorubio Road | 3769130 | Pozorrubio, Pangasinan
Concreting of Bantocaling w/ slope protection and RCCP | 4812365 | Mangatarem, Pangasinan
Concreting of Mabanang-Namalasan Road | 4901369.54 | Mangatarem, Pangasinan | 4901369.54
Asphalt for blocktopping of Ballay Bridge, | 195900 | Bani, Pangasinan
Asphalt for blocktopping of Pauline Bridge | 314800 | Sta. Barbara, Pangasinan
Asphalt for blocktopping along Sn. Fabian Camp One Rd., | 2497200 | San Fabian, Pangasinan
Asphalt for Sito Digup Rd., Fulgosino, | 1826890 | Umingan, Pangasinan | 1826890
Asphalt for blocktopping of Matic-matic Section, Naronong Road | 2497200 | Sta. Barbara, Pangasinan
Concreting of Austria St., Dorongan | 215081.49 | Lingayen, Pangasinan | 215081.49
Embarkment, backfilling of Access Road | 1319076 | Sitio Calay, Binmaley
Concreting Nalsian-Calasiao Road | 2891534 | Calasiao, Pangasinan
Construction of Balucay Brdg., | 6889938 | San Jacinto, Pangasinan
Concreting of Sitio Mogning at Brgy. San Felipe West | 3766246 | San Nicolas, Pangasinan
Improvement/blocktoping of Tayug-Natividad Road | 3079400 | Tayug, Pangasinan
Blocktopping of Laguit Centro Road | 2014000 | Brgy. Laguit Centro, Bugallon, Pangasinan
Construction of drainage Canal at Perez Blvd. | 802685 | Poblacion, San Carlos
Concreting of Salapingao Road | 3425300 | Binmaley, Pangasinan
Construction of 1 unit RCBC Castillo St. | 896451 | Lingayen, Pangasinan
Construction of Drainage Canal with cover | 1564609 | Hermoza, Dasol, Pangasinan
Concreting of Purok Agnanayon, Alolong, Agno | 2668917 | Agno, Pangasinan
Concreting of Brgy. Road | 2458718 | Bayambang, Pangasinan
Labor, materials, equipment and othe incidentals for the construction of Stone Masonry along Mapandan-Banaoang Road | 990491 | Sta. Barbara, Pangasinan
Labor, materials, and other incidentals for the rehab/concretin of Mabilao/Binday Road | 25000000 | San Fabian, Pangasinan
Asphalt for bloctopping of Balagan Rd. | 2014000 | Binmaley, Pangasinan
Asphalt for blocktopping of Dupo Road | 2693100 | Binmaley, Pangasinan
Asphalt for blocktopping of Pozorrubio- Sugcona Rd., (Imbalbalatong Section) | 1098400 | Pozorrubio, Pangasinan
Labor, materials, and other incidentals for the Rehabilitation of Urdaneta Community Bridge, Superstructure | 8728822 | Urdaneta City
Labor, materials, and other incidentals for the concreting of Sitio Centro, San Jose | 1260449 | Alaminos, Pangasinan
Labor, materials, and other incidentals for the rehab of Casabar Brdg., | 2532869 | San Manuel, Pangasinan
Environmental Development
10000 pcs. Coconut seedlings | 449700

## 2ndQtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2018
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | TOTAL COST | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[6 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Repair/improvement of Sison Auditorium | 2655056 | Lingayen | 2552943.75 |  |  | 100% | 2552943.75
Asphalt for the improvement of Sport Ground at Alaminos City National High School | 1707300 | Alaminos City | 1702815 |  |  | 100% | 1702815
Replacement of roofing in rewiring of Main Bldg., Phase II, Mapandan Community Hospital | 6303036 | Mapandan | 6300682.88 |  |  | 40% | 2520273.15
Completion of Training Center II, Capitol Complex | 15979311 | Lingayen | 15974887.74 |  |  | 80% | 11779910.19
Upgrading of Electrical System at PPH, Phase I | 15095413 | San Carlos City | 15090761.88 |  |  | 100% | 15090761.88
Extension of Drainage System at Capitol Cmpd., Lingayen | 1020828 | Lingayen
Construction of barbedwire Perimeter Fence and Guard House at Eco-Tourism Site, Sabangan, Lingayen | 1319394 | Lingayen
Improvement of Capitol Grounds (Additional Height/Soil Barrier) at Capitol Cmpd., Lingayen | 999956 | Lingayen
Construction of bleachers and concreting of floor slab at Municipal Plaza, Basista | 3759721 | Basista
Financial Assistance for the purchase of lot for the site of their Multi-Purpose Gymnasium, Anonas, Urdaneta | 3000000 | Urdaneta City | 3000000 |  |  | 100% | 3000000
Construction of Perimeter Fence (back) at OPAG, Tebag, Sta. Barbara | 3251797 | Sta. Barbara
Extension/Additional Height of Multi-Purpose Gym at Brgy. Gayaman, Binmaley | 1052466 | Binmaley
Construction of Covered Court (Gymnasium) at Brgy. Pantal, Bugallon | 2109028 | Bugallon
Construction of covered court (gymnasium) at Pangapisan North, Lingayen | 3097654 | Lingayen
13000 bags cement to be given to various barangays, associations and constituents in the province | 3510000 | Pangasinan
Construction of 3 units Guard Post and Installation of Lightings at Beachfront, Lingayen | 999732 | Lingayen | 994319.83 |  |  | 50% | 497159.92
Construction of Multi-Purpose Hall at Brgy. Bayoyong, Basista | 1824727 | Basista | 1817327.6 |  |  | 50% | 908663.8
Extension of concrete ditch at Motorpoo Cmpd., Lingayen | 961405 | Lingayen | 957103.74 |  |  | 100% | 957103.74
Rehabilitation of of Processing Bldg./Center at PAGO | 425436 | Pangasinan | 422618.98 |  |  | 100% | 422618.98
Construction of 2 units basketball board and flagpole at Pangasinan Reformation Center | 420449 | Burgos | 417990.83 |  |  | 100% | 417990.83
Renovation/improvement of various facilities at Pangasinan Reformation Center, Brgy. San Vicente, Burgos | 935578 | Burgos | 931556.94 |  |  | 100% | 931556.94
Construction of Storage, replacement , Sr. Citizens Bldg., Poblacion, San Vicente | 452098 |  | 449599.19 |  |  | 100% | 449599.19
Construction of covered court, Pogonsili, Aguilar | 2543445 | Aguilar | 2538270.15 |  |  | 100% | 2538270.15
Pest Control Treatment, Malong Bldg., Urdaneta District Hospital | 881139 | Urdaneta City | 878299.68 |  |  | 100% | 878299.68
Pest Control Treatment, WPDH, MDH, Bolinao CH | 861061 | Bolinao | 857598.26 |  |  | 100% | 857598.26
Pest Control Treatment, Pangasinan Skills Dev't. Center, BDH | 847378 | Bayambang | 844074.13 |  |  | 100% | 844074.13
Repainting of Capitol Resort Hotel | 1044578 | Lingayen | 1041013.53 |  |  | 100% | 1041013.53
Various supplies/materials for the installation of water source for swimming pool and repair of restrooms, quarters, movable shed/stand at NRSCC | 207443.5 | Lingayen
Upgrading of Systems and Preventive Maintenance of Dialysis Center at PPH, San Carlos City | 582000 | San Carlos City
Repair of perimeter fence leading to Baywalk, Capitol Cmpd., Lingayen | 118846 | Lingayen | 117730.19 |  |  | 100% | 117730.19
Extension of mess hall/Dining Area for Dirty Kitchen and storage area at Pangasinan Reformation Center, Burgos | 338814 | Burgos | 335862.24 |  |  | 100% | 335862.24
Additional works for pangasinan Reformation Center at San Vicente, Burgos | 614903 | Burgos | 611785.47 |  |  | 100% | 611785.47
Extension of 3-Phase Line & Installation of 3-75 KVA DX Transformer and Electrical Services at Mangatarem District Hospital, Mangatarem | 1988994 | Mangatarem
Extension of 3-Phase Line & Installation of 3-100KVA DX Transformer at Training Center 2 Capitol Compound, Lingayen | 2351565 | Lingayen
Improvement/rehabilitation of Main Ward Annex "B" at Urdaneta Dist. Hosp., Urdaneta City | 1222713 | Urdaneta City
Upgrading of Electrical System at Training Center 2 Capitol Compound, Lingayen | 4253811 | Lingayen
Pest Control Treatment of various Provincial Buildings at Capitol Compound, Lingayen | 765559 | Lingayen
Pest Control Treatment of various Hospitals, Umingan Com. Hosp., Lingayen Dist. Hosp. | 836610 | Lingayen
13000 bags cement to be given to various barangays, associations and constituents in the province | 3510000 | Pangasinan
Construction of 3 units Artesian Well, San Vicente, San Manuel | 195000 | San Manuel | 193067.8 |  |  | 100% | 193067.8
Constrruction of 2 units Dug well, Palapad, San Fabian | 342000 | San Fabian | 339779.1 |  |  | 100% | 339779.1
Constrruction of 2 units Dug well, Malokiat, Pozorrubio | 310000 | Pozorrubio | 306868.92 |  |  | 100% | 306868.92
Various materials for the conversion of deep well into Level II Water System at Brgy. Linoc, Binmaley | 98033 | Binmaley
50 units water pump, 7HP to be given to various farmer associations in the province | 1050000 | Pangasinan
Various spareparts for the various dredging machine at the PEO, Lingayen | 2062567 | Lingayen
Various spareparts for the various dredging machine at the PEO, Lingayen | 4363356 | Lingayen
Various materials in the construction 2 units Artesian Well at Brgy. San Vicente, Calasiao | 59376 | Calasiao
Construction of 1 unit deep well at Dulag, Binmaley | 494000 | Binmaley | 491703.02 |  |  | 100% | 491703.02
Construction of 2 units dug well, Anda | 303000 | Anda
Construction of 2 units dug well, Sitio San Pedro, San Macario, at Natividad | 224000 | Natividad | 221993.4 |  |  | 100% | 221993.4
Repair/improvement of various roads within the Province of Pangasinan | 2933500 | Pangasinan | 2925785 |  |  | 100% | 2925785
Economic Development
Livelihood Projects - Loans Granted to various Associations and MPC's | 2250000 | Pangasinan |  |  |  |  | 2250000
Amortization of Principal and Interest on Loan to the LBP | 107869345.12 | Pangasinan | 107869345.12 |  |  |  | 107869345.12
Bamboos, fish, crablets and crab baskets for the grown-out culture of Mangrove crab as Aqua Culture Dishes Demo Project, Bolinao Fish Farm, Bolinao | 137787 | Bolinao | 137787
77 Bags cement for the restoration and construction of damage protection wall at Coliaso Bridge along Mabilao-Binday Prov'l Road, San Fabian | 23100 | San Fabian | 23061.5 |  |  |  | 23061.5
Repair/blocktopping of Urbiztondo Div. Provl Road, Urbiztondo | 1664100 | Urbiztondo
Blocktopping of various Municipal Streets at Poblacion, Mapandan | 1578200 | Mapandan | 1574010 |  |  | 100% | 1574010
Asphalting/blocktopping of various Municipal Streets at San Quintin | 3308800 | San Quintin | 3300030 |  |  | 100% | 3300030
Rehabilitation of Urbiztondo-Basista Road, Urbiztondo and Basista, as per Extra Work Order No. 1 | 1712288.64
Asphalting of Brgy. Libson West Road, Lingayen | 221300
Improvement/rehabilitation (asphalting/blocktopping with patching) of Brgy. Cato to Patima Road, Infanta | 1973400
Improvement/construction of slope protection of RCBC along Lingayen Plaza Extension road, Brgy. Maniboc, Lingayen | 267297 |  | 265764.98 |  |  | 100% | 265764.98
Repair of Imelda Bridge (2 spans) at Mangatarem | 10895660
Blocktopping of Brgy. Tempra Guilig Rd., Brgy. Tempra Guilig, San Fabian | 1948000
Asphalting/blocktopping of Don Canuto Road at Domalandan West, Lingayen | 2222200
Asphalting/blocktopping of various FMR Brgy. Roads in Bani | 7618300
Rehabilitation of Lipit Bridge, Manaoag | 1640351
Repair and maintenance of various provincial roads | 3038000
Concreting of Sitio Mogning at Brgy. San Felipe West, San Nicolas | 3766246 |  | 3760876.61 |  |  | 100% | 3760876.61
Improvement/blocktoping of Tayug-Natividad Rd., Tayug | 3079400 |  | 3071230 |  |  | 100% | 3071230
Blocktopping of Laguit Centro Rd., Brgy. Laguit Centro, Bugallon | 2014000 |  | 2008650 |  |  | 100% | 2008650
Concreting of Salapingao Rd., Binmaley | 3425300 |  | 3418180.98 |  |  |  | 2563635.74
Construction of 1 unit RCBC Castillo St., Lingayen | 896451 |  | 893166.23 |  |  |  | 893166.23
Concreting of Purok Agnanayon, Alolong, Agno | 2668917 |  | 2663145.04 |  |  | 80% | 2130516.03
Concreting of Brgy. Road, Brgy. Salud at Natividad, Pangasinan | 1957928
Construction of River Bank Protection at Burgos Street (Area) Poblacion, Binmaley | 1220641
Improvement/Construction of Side Slope Protection at Brgy. Baňaga, Bugallon | 3021715
Concreting of Farm to Market Road and School Frontage of Quibaol Elem. Sch., Lingayen | 999660 |  | 997227.65 |  |  | 100% | 997227.65
Concreting of Brgy. Baluyot Road, Bautista | 5262139
Asphalting of Brgy. Hall Compound, Brgy. Tori-Tori, Anda | 303800
Asphalting of Taketek and Panganiban Road, Tayug | 5477600 |  | 5463075 |  |  | 100% | 5463075
Asphalt for Access Road, at Reformation Center, San Vicente, Burgos | 1453000 |  | 1449180 |  |  | 100% | 1449180
Concreting of Banaoang-Mapandan Road, Sta. Barbara as per Extra Work | 439738.78 |  | 439738.78 |  |  | 100% | 439738.78
Asphalt for OPAG Main Entrance and Compound at Bolinao | 1319700 |  | 1316215 |  |  | 100% | 1316215
Concreting of Antipangal-Pangascasan Road, Bugallon | 1998000 |  | 1992770.34 |  |  | 85% | 1693854.79
Repair/Improvement of Balingasay Bridge, Bolinao | 2192575 |  | 1313077.5 |  |  | 100% | 1313077.5
Concreting of Fulgosimo Road, Umingan | 2897840 |  | 2892949.27 |  |  | 100% | 2892949.27
Improvement of Brgy. Road, Wawa, Lingayen | 2602800 |  | 2597060.63 |  |  | 100% | 2597060.63
Concreting of Brgy. Legaspi Road | 689019 |  | 685708.41 |  |  | 100% | 685708.41
Asphalt for Blocktopping of Brgy. A. Alarcio Rd., Laoac | 1926000 |  | 1920890 |  |  | 100% | 1920890
Concreting of Villalon Rd., Zone 1 Flores, San Manuel | 2073074 |  | 2068038.19 |  |  | 100% | 2068038.19
Asphalt for blocktopping of Malilion, Sto. Tomas, Canangguan Rd., San Nicolas | 1904000 |  | 1898950 |  |  | 100% | 1898950
Asphalt for the improvemet/blocktopping of Anambongan, Basista | 2607200 |  | 2600275 |  |  | 100% | 2600275
Concreting of Bantocaling w/ slope protection and RCCP, Mangatarem | 4812365 |  | 4806167.84 |  |  | 100% | 2403083.92
Concreting of Mabanang-Namalasan Rd., Mangatarem | 4909300 |  | 4901369.54 |  |  | 40% | 1960547.82
Asphalt for blocktopping along Sn. Fabian Camp One Rd., San Fabian | 2497200 |  | 2490575 |  |  | 100% | 2490575
Asphalt for Sito Digup Rd., Fulgosino, Umingan | 1831700 |  | 1826890 |  |  | 100% | 1826890
Asphalt for blocktopping of Matic-matic Section, Naronong Rd., Sta. Barbara | 2497200 |  | 2490575 |  |  | 100% | 2490575
Concreting of Austria St., Dorongan, Lingayen | 218175 |  | 215081.49 |  |  | 100% | 215081.49
Embarkment, backfilling of Access Road, Sitio Calay, Binmaley | 1319076 |  | 1314919.31 |  |  | 75% | 1203443.97
Concreting of Brgy. Road, Brgy. Buayaen, Bayambang | 2458718 |  | 2453081.15 |  |  | 100% | 2453081.15
Labor, materials, equipment and othe incidentals for the construction of Stone Masonry along Mapandan-Banaoang Rd. , Sta. Barbara | 990491 |  | 987164.72 |  |  | 100% | 987164.72
Asphalt for bloctopping of Balagan Rd., Binamaley | 2014000 |  | 2008650 |  |  | 100% | 2008650
Asphalt for blocktopping of Dupo Rd., Binmaley | 2693100 |  | 2685955 |  |  | 100% | 2685955
Asphalt for blocktopping of Pozorrubio- Sugcona Rd., (Imbalbalatong Section), Pozorrubio | 1098400 |  | 1095490 |  |  | 100% | 1095490
Labor, materials, and other incidentals for the rehab of Casabar Brdg., San Manuel | 2532869 |  | 2527169.78 |  |  | 90% | 2274452.8
Blocktopping of various Provincial Bridges within the Province | 1526600
Blocktopping of Provincial Road Camaley Bo. Rd (Sta. Rosa Section) Binmaley | 1023500
Blocktopping of Brgy. Namalucan Rd., Agno | 1409000
Asphalting of San Jacinto-Pozorrubio Road, (Travo-Pugaro Section) Brgy. Dilan, Pozorrubio | 1066700
Labor, materials, and other incidentals for the improvement/concreting of Bued-Ambonao Rd, Calasiao | 5123204
11 drums E. Asphalt and 349 Asphalt Pre-mix for the blocktopping w/ patching of Farm to Market Road at Brgy. Inmalog Sur to Norte, San Fabian | 2077900
230 MT Asphalt Pre-mix and 10 drums of Emulsified Asphalt for use in the asphalting of Arzadon Rd., San Manuel | 1409000
79 MT of Asphalt Pre-mix and 3 drums of Emulsified Asphalt for use in the asphalting of Arzadon Brgy. Rd., San Manuel | 477700
Asphalting/blocktopping of Brgy. Malawa Rd., Lingayen | 1882000 |  | 1877010 |  |  |  | 1877010
Environmental Development
10000 pcs. Coconut seedlings | 450000 |  | 449700 |  |  | 100% | 449700
Various farm inputs to be used in the seedling propagation/production of various species at the Prov'l Agriculture Office Field Station of CY2018 | 491535

## 3rdQtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2018
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Extension of stage and concreting of pathway at PNHS | Lingayen | 408964.51 |  |  |  | 408964.51
Completion of 2-storey Brgy. Cabacaraan | San Manuel | 896912
Construction of Dirty Kitchen w/ storage at DILG Cmpd., | Lingayen | 707910
Construction of concrete pavement and drainage canal at School Division Office | Urdaneta City | 1076438
Construction of Day Care Center | Brgy. Ambalangan Dalin, San Fabian | 557256
FA, procurement of lot to be designated as Public Muslim Cemetery in, Pangasinan | Brgy. San Aurelio II, Balungao | 1500000 |  |  |  | 1500000
FA, procurement of lot for the proposed site of school building | Sitio Mangampag Brgy. Pogo, Bautista | 700000 |  |  |  | 700000
Construction of Well Source, installation of Motor Pump tank and Accessories, Mangatarem Breeding Station | Mangatarem | 299000
Labor, materials, equipment and other incidentals for the waterproofing of roofing/roof deck at Urduja House, Capitol Cmpd. | Lingayen | 1585000
Installation of additional ACU Panel Board at Pozorrubio Com. Hospital | Pozorrubio | 995593
Construnction of covered court (Gymnasium) at Brgy. Pogo (Area=16.9m x 30m) | Bayambang | 3088158
Construction of stage with comfort room | Brgy. Tamaro, Bayambang | 1102145
Improvement of Multi-Purpose hall (Brgy. Hall) | Brgy. Duera, Bayambang | 650000
Repair/improvement of roofing of Multi-Purpose Hall (Brgy. Hall) & Day Care Center | Brgy. Bical Norte, Bayambang | 527995
Repair/Improvement of Brgy. Hall and Brgy. Health Center | Brgy. Matalava, Lingayen | 1419593
Completion of Amphitheater Bldg. at Manaoag National High School | Manaoag | 2412679
Modification of Steel Column of covered court and construction of bleacher and renovation of Perimeter fence | Matalava, Lingayen | 1853734
Expansion of covered court at Tuliao Elem. Sch. | Tuliao, Sta. Barbara | 611159
Construction of Senior Citizen and Brgy. Health Worker Bldg., | Ventinilla, Sta. Barbara | 873854
Repair/improvement of various facilities at Ninoy E/S | Aguilar | 635071
Repair/improvement of various facilities at Buer-Bayaoas E/S, Aguilar | Aguilar | 613266
Repair/improvement of 1 unit 1 classroom at Enrico Prado NHS, Buer, Aguilar | Aguilar | 432259
Repair/improvement of 2 -1 unit classroom at Bocboc East E/S, Bocboc East, Aguilar | Aguilar | 681660
Repair/improvement of Brgy. Hall, Pogomboa, Aguilar | Aguilar | 370993
Construction of Slope Protection of Open Canal at Motorpool Compound, Capitol Complex | Lingayen | 424485.35
Construction of Service Bay Building, Motorpool Compound, Capitol Complex, Lingayen | Lingayen | 297642
Various construction materials for the construction of 6 classrooms in Multi-Purpose Gym at Pao Elem. Sch., Manaoag | Manaoag | 343260
Installation of Manual Transfer Switch (MTS) Panel at WPDH | Alaminos City | 457080
Conversion of Deep Well Source (Magsaysay Type) to Point Source Water Supply at Dona Catalina E/S, | Brgy. Laoag, Aguilar | 98731
13000 bags cement to be given to various barangays, associations and constituents in the province | Pangasinan | 3510000
13000 bags cement to be given to various barangays, associations and constituents in the province | Pangasinan | 3510000
Labor, materials, equipment and other incidentals for the Pest Control Treatment at CIDG, PIAS, and Gym Bldg. | Lingayen | 154938
13000 bags cement to be given to various barangays | Pangasinan | 3510000
Labor, materials, equiment and other incidentals for the construction of 2 units water Impounding at Dasol Breeding Station | Brgy. Bobonot, Dasol | 178722.84
1 unit outboard Motor mounting frame, steering control kit, installation of outboard motor frame kit and steering kit | PEO, Lingayen | 600000
Various materials for the construction of 2 units Artesian Well | Boundaries of Brgys. Rizal and Casanicolasan and boundaries of Brgys. Rizal and Carmay West, Rosales | 89930
Various materials for the construction of 1 unit Artesian Well at Brgy. Balincanaway, Rosales |  | 42192
Various materials for the construction of 1 unit Artesian Well | Brgy. Zone 1, Rosales | 16840
Various materials for the construction of 3 units deep well | Brgys. San Pedro East and Palakipak, Rosales | 40723
Construction of 1 unit new writer system at OPAG Mangatarem | Brgy. Malabobo,Mangatarem | 307000
Construction of drainage Canal | Brgy. San Gabriel 1st, Bayambang | 989770
Repair of Damaged Concrete pavement along Mabini Breeding Station Road | Poblacion, Mabini | 49445
Economic Development
Construction of 2 units wharf along Agno River | Poblacion, Lingayen | 4339209
Construction of 200 units STWIP of various brgys and municipalities in the Province | Pangasinan | 7000000
Concreting of Angayan Norte Brgy. Road, Balungao | Balungao | 2779445
Concreting of Capulaan Brgy. Road, | Balungao | 2779445
Concreting of Farm to Market Road, Zone IV at | Brgy. San Miguel, Balungao | 2779445
Rehabilitation of Box Culvert | Cabaritan-Binmeckeg Rd., Sison | 582570
Rehabilitation/upgrading of Pandel Bridge of Sitio Pannel Brdg., | Sitio Pandel Domalandan East, Lingayen | 2370728
5 drums E. Asphalt and 145 MT of Asphalt Pre-mix for the blocktopping | San Andres Brgy. Road,Umingan | 869500
120 MT Asphalt Pre-mix and 6 drums E. Asphalt for the Improvement/asphalt | Sitio Tangke Rd., at Brgy. Sumabnit, Binalonan | 746400
4 drums E. Asphalt and 82 MT of Asphalt Pre-mix for the asphalting of Access Road to Emergency Room at | PPH, Bolingit, San Carlos City | 508314
14 drums Emulsified Asphalt at 322 MT Asphalt Pre-mix for the proposed Asphalting | Brgy. Dulacac, Alaminos City | 1972600
Concreting of Alvear II Road, Poblacion | Lingayen | 3493305
11 drums E. Asphalt and 217 MT Asphalt mix for the blocktopping of Capitol Road Network, Capitol Cmpd. | Lingayen | 1351900
Concreting of Road | Brgy. Balangobong, Lingayen | 2570235
Concreting of Don Emilio Hilano St., Maniboc, Lingayen |  | 1556283
536 MT Asphalt Pre-mix 28 drums E. Asphalt for the repair/maintenance of various provincial roads in Pangasinan | Pangasinan | 3351200
437 MT Asphalt Pre-mix and 13 drums E. Asphalt for blocktopping | Palapar Norte, Lareg-lareg Road, Palapag Section, Malasiqui | 2590700
7 drums E. Asphalt and 224 MT Asphalt Pre-mix for blocktopping | Samat Bo. Provincial Road (Samat Section and Orduña St.), Bugallon | 1332800
Concreting of Pathwalk | Brgy. Tambac, Bayambang | 742500
Concreting of Pathwalk | Brgy. Bical Sur, Bayambang | 477547
Concreting of Brgy. Road | Brgy. Inanlorenza, Bayambang | 999965
Concreting of Pathwalk | Brgy. Maigpa, Bayambang | 999593
Concreting of Pathwalk | Brgy. Buayaen, Bayambang | 857023
Concreting of Brgy. Road | Brgy.San Gabriel 2nd, Bayambang | 999972
Concreting of Brgy. Road | Brgy. Nalsian Sur, Bayambang | 999565
Concreting of Pathwalk | Brgy. Sanlibo, Bayambang | 999965
Concreting of Brgy. Road | Brgy. Malioer, Bayambang | 999965
Concreting of Pathwalk | Brgy. Caturay, Bayambang | 999965
Concreting of Pathwalk | Brgy. Banaban, Bayambang | 999950
Concreting of Brgy. Road | Brgy. San Vicente, Bayambang | 990000
Materials for the improvement of Cabaritan-Binmeckeg Rd., | Sison | 69240
Improvement of Brgy. Mabini Road with RCCP and Slope Protection (Stone Masonry) | Balungao | 1840813
297 bags of Asphalt sealant for use in the rehabilitation/maintenance of various Provincial Roads withn the | Province of Pangasinan | 1039500
Various materials for the repair/improvement of damaged RCCP | Sablig, Anda | 51567
5 drums E. Asphalt and 166 MT of Asphalt Pre-mix for the blocktopping of Brgy. Road | Brgy. Road, Brgy. Darawey, Bayambang | 985000
5 drums E. Asphalt and 166 MT of Asphalt Pre-mix for the blocktopping of Brgy. Road, | Brgy. Tampog, Bayambang | 985000
5 drums E. Asphalt and 166 MT of Asphalt Pre-mix for the blocktopping of Brgy. Road, | Brgy. Pantol, Bayambang | 985000
Concreting of Brgy. Road | Brgy. Tanolong, Bayambang | 999965
Amortization of Principal and Interest on Loan to the LBP (as of June, 2018) |  | 0
Livelihood Projects - Loans Granted to various Associations and MPC's | Pangasinan | 3190000 |  |  |  | 3190000
2 booths fee of PGP to participate in 2018 Travel, Trade, Consumer Roadshows, | Carson, CA, USA | 126900 |  |  |  | 126900
Environmental Development

## 4thQtr (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2018
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Upgrading/construction of Pedia Ward & Isolation Room Bldgs. At Lingayen Dist. Hospital | Lingayen | 1410585.71 | 2018-07-19 | 2018-09-06 | 100% | 1410585.71 |  | completed
Concreting of Brgy. Road, Brgy. Salud at Natividad, Pangasinan | Natividad | 1953080 | 2018-07-09 | 2018-09-13 | 100% | 1953080 |  | completed
Improvement of Capitol Grounds (Additional Height/Soil Barrier) at Capitol Cmpd., Lingayen | Lingayen | 997058.33 | 2018-06-29 | 2018-10-04 | 100% | 997058.33 |  | completed
Construction of River Bank Protection at Burgos Street (Area) Poblacion, Binmaley | Binmaley | 1215537.84 | 2018-08-08 | 2018-11-05 | 100% | 1215537.84 |  | completed
Improvement/Construction of Side Slope Protection at Brgy. Baňaga, Bugallon | Bugallon | 3016901.86 | 2018-07-09 | 2018-09-24 | 100% | 3016901.86 |  | completed
Construction of bleachers and concreting of floor slab at Municipal Plaza, Basista | Basista | 3754403.45 | 2018-07-06 | On Going | 35% | 1314041.21 |  | on-going
Construction of Perimeter Fence (back) at OPAG, Tebag, Sta. Barbara | Sta. Barbara | 3245364.84 | 2018-07-18 | On Going | 50% | 1622682.42 |  | on-going
Extension/Additional Height of Multi-Purpose Gym at Brgy. Gayaman, Binmaley | Binmaley | 1048149.53 | 2018-07-09 | 2018-08-17 | 100% | 1048149.53 |  | completed
13000 bags cement to be given to various barangays, associations and constituents in the province | Pangasinan | 3506750 | Materials Only |  | 100% | 3506750 |  | completed
Completion of 2-storey Brgy. Cabacaraan, San Manuel | San Manuel | 892602.4 | 2018-08-14 | 2018-11-06 | 100% | 892602.4 |  | completed
Construction of Dirty Kitchen w/ storage at DILG Cmpd., Lingayen | Lingayen | 704996.97 | 2018-08-13 | 2018-09-17 | 100% | 704996.97 |  | completed
Installation of additional ACU Panel Board at Pozorrubio Com. Hospital, Pozorrubio | Pozorrubio | 989164.71 | 2018-09-23 | 2018-11-06 | 100% | 989164.71 |  | completed
Construction of stage with comfort room at Brgy. Tamaro, Bayambang | Bayambang | 1097506.18 | 2018-09-17 | Dec. 2018 | 100% | 987755.56 |  | completed
Repair/improvement of roofing of Multi-Purpose Hall (Brgy. Hall) & Day Care Center at Brgy. Bical Norte, Bayambang | Bayambang | 524077.24 | 2018-09-04 | 2018-10-01 | 100% | 524077.24 |  | completed
Repair/Improvement of Brgy. Hall and Brgy. Health Center at Brgy. Matalava, Lingayen | Lingayen | 1413145.49 | 2018-10-23 | 2018-11-29 | 100% | 1413145.49 |  | completed
Modification of Steel Column of covered court and construction of bleacher and renovation of Perimeter fence at Brgy. Matalava, Lingayen | Lingayen | 1848020.94 | 2018-10-23 | 2018-11-29 | 100% | 1848020.94 |  | completed
Repair/improvement of various facilities at Ninoy E/S, Aguilar | Aguilar | 632223.3 | 2018-10-10 | 2018-11-30 | 100% | 632223.3 |  | completed
Repair/improvement of 2 -1 unit classroom at Bocboc East E/S, Bocboc East, Aguilar | Aguilar | 678570.52 | 2018-10-18 | 2018-11-19 | 100% | 678570.52 |  | completed
Repair/improvement of Stage at Urdaneta City Nat'l HS, Urdaneta City | Urdaneta | 1468685 | On Going |  | 55% | 807776.75 |  | on-going
Upgrading of ATS Panel & Main Feederline at Umingan Community Hosp., Umingan | Umingan | 1526238 | On Going |  | 20% | 305247.6 |  | on-going
Construction of Multi-Purpose Gym Bleachers at Tonton Elem. Sch., Tonton, Lingayen | Lingayen | 1445618 | On Going |  | 13.85% | 200218.093 |  | on-going
Construction of stage at Brgy. Villanueva, Bautista | Bautista | 1375256.3 | On Going |  | 75% | 1031442.225 |  | on-going
Upgrading of Electrical System and Rewiring of OR/DR & Ward Bldg. at Asingan Community Hospital, Asingan | Asingan | 1103582 | 2018-12-17 | 2018-12-17 | 100% | 1097675.25 |  | completed
Construction of Multi-Purpose Hall at Brgy. Bayoyong, Basista | Basista | 1817327.6 | 2018-03-27 | 2018-10-25 | 100% | 1817327.6 |  | completed
Construction of 3-storey Multi-Purpose Bldg., (Phase 1) at Capitol Cmpd., Lingayen | Lingayen | 16980927 | 2018-05-14 | On Going | 15% | 2547139.05 |  | on-going
Extension of 3-Phase Line & Installation of 3-75 KVA DX Transformer and Electrical Services at Mangatarem District Hospital, Mangatarem | Mangatarem | 1983012.74 | 2018-07-18 | 2018-09-18 | 100% | 1983012.74 |  | completed
Extension of 3-Phase Line & Installation of 3-100KVA DX Transformer at Training Center 2 Capitol Compound, Lingayen | Lingayen | 2347800 | 2018-07-09 | 2018-08-28 | 100% | 2347800 |  | completed
Improvement/rehabilitation of Main Ward Annex "B" at Urdaneta Dist. Hosp., Urdaneta City | Urdaneta | 1217241.07 | 2018-07-09 | 2018-10-25 | 100% | 1217241.07 |  | completed
13000 bags cement to be given to various barangays, associations and constituents in the province | Pangasinan | 3506750 | Materials Only |  |  | 3506750 |  | completed
Construction of Slope Protection of Open Canal at Motorpool Compound, Capitol Complex, Lingayen | Lingayen | 424485.35 | 2018-08-14 | 2018-09-21 | 100% | 424485.35 |  | completed
Repair of various facilities at LDH, Lingayen | Lingayen | 588289 | Not Yet Started |  | n/a | n/a |  | nys
Preventive maintenance of Bayambang Dist. Hosp., Bayambang | Bayambang | 253756 | Not Yet Started |  | n/a | n/a |  | nys
Repair/improvement of various buildings at Dasol Community Hosp., Dasol | Dasol | 340816 | Not Yet Started |  | n/a | n/a |  | nys
Installation of 3P wiring for medical waste treatment machine at PPH, San Carlos City | San Carlos City | 349036.22 | On Going |  | 30% | 349036.22 |  | on-going
Repair of Various buildings at Mangatarem Dist. Hosp., Mangatarem | Mangatarem | 358333 | On Going |  | 28% | 100333.24 |  | on-going
Tiling works at 2nd floor of the 2-storey Training Center, Alcala | Alcala | 394400 | 2018-11-30 | 2018-12-21 | 100% | 394400 |  | completed
Repair/improvement of various buildings at Urdaneta Dist. Hosp., Urdaneta City | Urdaneta | 832464 | Not Yet Started |  | n/a | n/a |  | nys
Repainting of All Buildings at Asingan Com. Hosp. | Asingan | 479545 | 2018-12-02 | 2019-01-07 | 100% | 476561.99 |  | completed
Repair of various buildings at EPDH, Tayug | Tayug | 485600 | [5 empty] | nys
Construction of covered pathway at Dasol Com. Hosp. Brgy. Bobonot, Dasol | Dasol | 465847 | Nov. 2018 | 2018-12-28 | 100% | 462170.52 |  | completed
Labor, materials, equipment and other incidentals for the improvement/upgrading of various facilities (TB DOTS and Animal Bite Bldg.) at Dasol Com Hosp., Dasol | Dasol | 344172.69 | Not Yet Started |  | n/a | n/a |  | nys
Waterproofing of concrete cutter and canopies at Capitol Bldg. Roofdeck, Capitol Complex, Lingayen | Lingayen | 728191 | 2018-12-04 | 2019-01-07 | 100% | 725581.41 |  | completed
Construction of Gravity Wall at Waste Management Cmpd., Lingayen | Lingayen | 3656070 | 2019-01-21 |  | 21.55% |  |  | on-going
Construction of 2 units septic tank at Pago, Sta. Barbara | Sta. Barbara | 204943 | 2018-12-04 | 2018-12-28 | 100% | 202944.37 |  | completed
Construction of Elevated flatform for Bantayog ng Wika, Lingayen | Lingayen | 186946 | 2018-12-03 | 2018-12-12 | 100% | 183777.45 |  | completed
Construction of Bleachers w/ drainage canal at Brgy. Mapolo-polo, Basista | Basista | 762314 | 2018-12-04 | 2019-02-08 | 100% | 758890.2 |  | completed
Construction of Stage at Brgy. Paragos, Bayambang | Bayambang | 1091829 | 2019-01-21 |  | 1.73% |  |  | on-going
Rehabilitation of Amado T. Espino, Jr. covered court (Gym) at Poblacion, Aguilar | Aguilar | 685118 | 2018-12-03 | 2019-01-04 | 100% | 685118 |  | completed
Construction of Day Care Center at Zone 5, Bayambang | Bayambang | 999854 | Not Yet Started |  | n/a | n/a |  | nys
Construction of perimeter fence at Brgy. Duera, Bayambang | Bayambang | 346771 | Not Yet Started |  | n/a | n/a |  | nys
Construction of stage (additional works), at Brgy. Bical Norte, Bayambang | Bayambang | 609668 | Not Yet Started |  | n/a | n/a |  | nys
800 pcs. Jetmatic, 1600 pcs. GI Pipe | Pangasinan | 5959200 | Materials Only |  | 100% | 5959200 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
5,000 bags of cement | Pangasinan | 1500000 | Materials Only |  | 100% | 1500000 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
Gill nets, accessories and packing materials to be distributed to marginalized fisherfolk associations in the coastal municipalities | Pangasinan | 1025500 | Materials Only |  | 100% | 1025500 |  | completed
Rehabilitation of Sto. Domingo Bridge, San Manuel | San Manuel | 2216218 | 2018-11-22 | 2019-01-04 | 100% | 2210317.79 |  | completed
Repair/iprovement of covered court and with construction of 2-units stage at Brgy. Magtaking, Bugallon | Bugallon | 2639177 | Not Yet Started |  | n/a | n/a |  | nys
Constructuion of 2-storey Legislative Bldg., (Phase 1) at Capitol Cmpd., Lingayen, Pangasinan | Lingayen | 25000000 | Not Yet Started |  | n/a | n/a |  | nys
Improvement/reconstruction of Alvear (Lightings, sidewalk with Railings) and Artacho (Lightings) Provincial Rad at Lingayen | Lingayen | 10000000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of stage and covered court (Gymnasium) at Brgy. Salomague Norte, Bugallon | Bugallon | 4715000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court at Batancaoa South E/S, Urbiztondo | Urbiztondo | 2825703 | Not Yet Started |  | n/a | n/a |  | nys
Construction of 2-storey PEO (Phase 1) at Motorpool Cmpd, Capitol Complex, Lingayen | Lingayen | 15000000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of 3-units 2-storey cottages at Provincial Capitol Resort Hotel, Lingayen | Lingayen | 10000000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of PEO Warehouse Bldg. at Motorpool Cmpd, Lingayen | Lingayen | 11290429 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court (Gymnasium) at Brgy. Sabangan, Lingayen | Lingayen | 2240700 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court Gymnasium at Takipan, Mangatarem | Mangatarem | 2708097 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court (Gymnasium) Standard at Real National High School, Urbiztondo | Urbiztondo | 3334213 | Not Yet Started |  | n/a | n/a |  | nys
Economic Development
16 units, 8-horsepower, 4 diesel engine for irrigation projects in Dist. III and V | Pangasinan | 687760 | Materials Only |  | 100% | 687760 |  | completed
Construction/installation of 40 units STWIP of various brgys and municipalities in the Province | Pangasinan | 3165356.4 | Not Stated |  | 100% | 3165356.4 |  | completed
Construction/installation of 40 units STWIP of various brgys and municipalities in the Province | Pangasinan | 2295168.75 | On Going |  | 72.5% | 2295168.75 |  | on-going
Construction of 1 unit 3-barrel RCBC, Sito Panotnot, Brgy. Pangascasan, Sual | Sual | 1454085.22 | 2018-06-15 | 2018-11-07 | 100% | 1454085.22 |  | completed
Concreting of Maracang-Nancalasan Rd., Mangatarem | Mangatarem | 4901369.54 | 2018-03-19 | 2018-10-18 | 100% | 4901369.54 |  | completed
Asphalt for blocktopping of Ballag Bridge, Bani | Bani | 195735 | 2018-09-12 | 2018-09-12 | 100% | 195735 |  | completed
Asphalt for blocktopping of Pauline Bridge, Sta. Barbara | Sta. Barbara | 314540 | 2018-10-02 | 2018-10-02 | 100% | 314540 |  | completed
Concreting Nalsian-Bacayao Rd., Calasiao | Calasiao | 2885418.63 | 2018-03-27 | 2018-07-30 | 100% | 2885418.63 |  | completed
Concreting of Salapingao Rd., Binmaley (part) | Binmaley | 3418180.98 | 2018-04-10 | 2018-09-11 | 100% | 3418180.98 |  | completed
Rehabilitation of Urdaneta Community Bridge (Superstructure), Urdaneta City | Urdaneta | 8715685.32 | 2018-04-27 | On Going | 35% | 3051539.86 |  | on-going
Concreting of Sitio Centro, San Jose, Alaminos | Alaminos | 1255535.4 | 2018-04-29 | 2018-05-28 | 100% | 878874.78 |  | completed
Improvement/rehabilitation (asphalting/blocktopping with patching) of Brgy. Cato to Patima Road, Infanta | Infanta | 1968175 | 2018-09-27 | 2018-10-01 | 100% | 1968175 |  | completed
Repair of Imelda Bridge (2 spans) at Mangatarem | Mangatarem | 10889178.55 | 2018-07-19 |  | 40% | 4355671.42 |  | on-going
Rehabilitation of Lipit Bridge, Manaoag | Manaoag | 1634527.45 | 2018-07-18 | 2018-08-31 | 100% | 1634527.45 |  | completed
500 MT Asphalt Pre-mix and 20 drums Emulsified Asphalt , Repair and maintenance of various provincial roads | Pangasinan | 3030000 | Not Stated |  | 100% | 3030000 |  | completed
4 drums E. Asphalt and 82 MT of Asphalt Pre-mix for the asphalting of Access Road to Emergency Room at PPH, Bolingit, San Carlos City | San Carlos City | 508314 | 2018-09-22 | 2018-06-26 | 100% | 508314 |  | completed
Concreting of Road at Brgy. Balangobong, Lingayen | Lingayen | 2565178.6 | 2018-10-11 | 2018-11-28 | 100% | 2565178.6 |  | completed
Concreting of Brgy. Road, Brgy. Inanlorenza, Bayambang | Bayambang | 995679.38 | 2018-09-04 | 2018-09-28 | 100% | 995679.38 |  | completed
Concreting of Pathwalk at Brgy. Maigpa, Bayambang | Bayambang | 994616.44 | 2018-09-04 | 2018-09-28 | 100% | 994616.44 |  | completed
Concreting of Pathwalk at Brgy. Caturay, Bayambang | Bayambang | 996366.4 | 2018-09-04 | 2018-09-28 | 100% | 996366.4 |  | completed
Concreting of Brgy. Road, at Brgy. Tanolong, Bayambang | Bayambang | 995679.38 | 2018-09-04 | 2018-09-28 | 100% | 995679.38 |  | completed
Repair of Damaged Concrete pavement along Mabini Breeding Station Road, Poblacion, Mabini | Mabini | 49325 | Not Stated |  | 100% | 49325 |  | completed
Asphalt pre-mix and Emulsified Asphalt for blocktopping/patching of Brgy. Libson West, Lingayen | Lingayen | 565700 | 2018-04-13 | 2018-04-13 | 100% | 565700 |  | completed
1000 MT Asphalt Pre-mix and 32 drums Emulsified Asphalt for patching/asphalting/blocktopping of various Brgy. Roads at Urbiztondo | Urbiztondo | 5960800 | Oct. 2018 | Nov. 2018 | 100% | 5960800 |  | completed
Asphalting of Brgy. Doyong, Calasiao | Calasiao | 1229600 | 2018-11-20 | 2018-11-23 | 100% | 1229600 |  | completed
745 MT Asphalt Pre-mix (Special Mix) and 30 drums Emulsified Asphalt (SS-1) for use in the improvement (blocktopping with patching) of Palguyod-Manaol Prov'l Road (Palguyod Side), Pozorrubio | Pozorrubio | 4529500 | 2018-11-22 | 2018-12-01 | 100% | 4529500 |  | completed
Asphalts for the improvement (Patching/blocktopping) of Brgy. Road at Brgy. Hacienda, Bugallon | Bugallon | 2671100 | 2018-10-18 | 2018-10-22 | 100% | 2671100 |  | completed
Asphalts for the Asphalting of premises of the Brgy. Gym at Brgy. Villanueva, Bautista | Bautista | 1652300 | 2018-11-16 | 2018-11-19 | 100% | 1652300 |  | completed
280 MT Asphalt Pre-mix and 9 drums Emulsified Asphalt for the improvement or Asphalt Overlay at Brgy. Salasa, Bugallon | Bugallon | 1669600 | 2018-11-06 | 2018-11-08 | 100% | 1669600 |  | completed
Reconstruction of slope protection at San Antonio Brdg., Sta. Barbara | Sta. Barbara | 688397 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (raising/asphalting/blocktopping) of Amansabina Road 1 at Amansabina, Mangaldan | Mangaldan | 530100 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Brgy. Road at Brgy. Nalsian Norte, Bayambang | Bayambang | 997850 | Dec. 2018 | On Going | 45% | 449032.5 |  | on-going
Various materials for the reconstruction of Matic-matic Bridge (Flatslab) at Bgy. Matic-Matic, Sta. Barbara | Sta. Barbara | 5922593 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (Patching and Blocktopping) of Bantayan-Talogtog-Bateng Rd., Mangatarem | Mangatarem | 1823500 | 2018-11-19 | 2018-11-29 | 100% | 1823500 |  | completed
Improvement (Concreting and Raising with Stone Masonry) of Poblacion-Dalongue Road at Sta. Barbara | Sta. Barbara | 15000000 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Sabangan Brgy. Road at Brgy Sabangan, Binmaley | Binmaley | 1912331 | Not Yet Started |  | n/a | n/a |  | nys
Improvement of Existing Concrete Pavement at Brgy. Tombor, Binmaley | Binmaley | 2396947 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Farm to Market Road, at Brgy. Bogtong Silag, Mangatarem | Mangatarem | 2790371 | Not Yet Started |  | n/a | n/a |  | nys
79 MT Asphalt Pre-mix and 4 drums Emulsified Asphalt for use in the Proposed Access Road and Multi-Purpose Pavement at Eguia National High School Cmpd., Dasol | Dasol | 575500 | Not Yet Started |  | n/a | n/a |  | nys
230 MT Asphalt Pre-mix and 10 drums Emulsified Asphalt for use in the Asphalting of Brgy. Road at Brgy. Lelemaan, Manaoag | Manaoag | 1650000 | Not Yet Started |  | n/a | n/a |  | nys
Rehabilitation of Embarcadero Bridge at Malasiqui | Malasiqui | 14500000 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Sitio Boquig Road, Brgy. Paitan, San Carlos City | San Carlos City | 3321104 | Not Yet Started |  | n/a | n/a |  | nys
Rehabilitation/construction of Panganiban Bridge along Tayug-Sta. Maria Road at Tayug | Tayug | 21116947 | Not Yet Started |  | n/a | n/a |  | nys
Asphalt for the proposed blocktopping of Brgy. Anolid Rd., Malasiqui | Malasiqui | 1363000 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (bloctopping) of Alvear Road, Lingayen | Lingayen | 9999000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Artacho Street, Lingayen | Lingayen | 4996000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Farm to market Road at Brgy. Buenlag, Binmaley | Binmaley | 2728000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Lucban St., Brgy. Pias Road at Mapandan | Mapandan | 2728000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping along Sta. Maria-Sn Roque Rd. at San Roque Section, San Jacinto, Pangasinan | San Jacinto | 2090000 | Not Yet Started |  | n/a | n/a |  | nys
Asphalting of Brgy. Alitaya Road at Alitaya, Mangaldan | Mangaldan | 1606000 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (asphalting/blocktopping) of Brgy. Asin East Road at Malasiqui | Malasiqui | 3710000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Brgy. Road at Amancoro, Binmaley | Binmaley | 2097000 | Not Yet Started |  | n/a | n/a |  | nys
Livelihood Projects - Loans Granted to various Associations and MPC's | Pangasinan | 5065000 | Loan
Amortization of Principal and Interest on Loan to the LBP | Pangasinan | 63734370.91 |  |  | 100% | 63734370.91 |  | completed
Environmental Development
Various farm/nursery implements to be used fro various farm activities and project implementation at our field stations and provincial nurseries in Sta. Barbara, San Quintin, Dasol, Bolinao, Mangatarem and Lingayen | Pangasinan | 390075 |  |  | 100% | 390075 |  | completed
Various seedlings to be distributed in various rural-based organizations including school in support to the provincial reforestation project of the Provincial Gov't and also in support to the food production project | Pangasinan | 1530000 |  |  | 100% | 1530000 |  | completed

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2018
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Upgrading/construction of Pedia Ward & Isolation Room Bldgs. At Lingayen Dist. Hospital | Lingayen | 1410585.71 | 2018-07-19 | 2018-09-06 | 100% | 1410585.71 |  | completed
Concreting of Brgy. Road, Brgy. Salud at Natividad, Pangasinan | Natividad | 1953080 | 2018-07-09 | 2018-09-13 | 100% | 1953080 |  | completed
Improvement of Capitol Grounds (Additional Height/Soil Barrier) at Capitol Cmpd., Lingayen | Lingayen | 997058.33 | 2018-06-29 | 2018-10-04 | 100% | 997058.33 |  | completed
Construction of River Bank Protection at Burgos Street (Area) Poblacion, Binmaley | Binmaley | 1215537.84 | 2018-08-08 | 2018-11-05 | 100% | 1215537.84 |  | completed
Improvement/Construction of Side Slope Protection at Brgy. Baňaga, Bugallon | Bugallon | 3016901.86 | 2018-07-09 | 2018-09-24 | 100% | 3016901.86 |  | completed
Construction of bleachers and concreting of floor slab at Municipal Plaza, Basista | Basista | 3754403.45 | 2018-07-06 | On Going | 35% | 1314041.21 |  | on-going
Construction of Perimeter Fence (back) at OPAG, Tebag, Sta. Barbara | Sta. Barbara | 3245364.84 | 2018-07-18 | On Going | 50% | 1622682.42 |  | on-going
Extension/Additional Height of Multi-Purpose Gym at Brgy. Gayaman, Binmaley | Binmaley | 1048149.53 | 2018-07-09 | 2018-08-17 | 100% | 1048149.53 |  | completed
13000 bags cement to be given to various barangays, associations and constituents in the province | Pangasinan | 3506750 | Materials Only |  | 100% | 3506750 |  | completed
Completion of 2-storey Brgy. Cabacaraan, San Manuel | San Manuel | 892602.4 | 2018-08-14 | 2018-11-06 | 100% | 892602.4 |  | completed
Construction of Dirty Kitchen w/ storage at DILG Cmpd., Lingayen | Lingayen | 704996.97 | 2018-08-13 | 2018-09-17 | 100% | 704996.97 |  | completed
Installation of additional ACU Panel Board at Pozorrubio Com. Hospital, Pozorrubio | Pozorrubio | 989164.71 | 2018-09-23 | 2018-11-06 | 100% | 989164.71 |  | completed
Construction of stage with comfort room at Brgy. Tamaro, Bayambang | Bayambang | 1097506.18 | 2018-09-17 | Dec. 2018 | 100% | 987755.56 |  | completed
Repair/improvement of roofing of Multi-Purpose Hall (Brgy. Hall) & Day Care Center at Brgy. Bical Norte, Bayambang | Bayambang | 524077.24 | 2018-09-04 | 2018-10-01 | 100% | 524077.24 |  | completed
Repair/Improvement of Brgy. Hall and Brgy. Health Center at Brgy. Matalava, Lingayen | Lingayen | 1413145.49 | 2018-10-23 | 2018-11-29 | 100% | 1413145.49 |  | completed
Modification of Steel Column of covered court and construction of bleacher and renovation of Perimeter fence at Brgy. Matalava, Lingayen | Lingayen | 1848020.94 | 2018-10-23 | 2018-11-29 | 100% | 1848020.94 |  | completed
Repair/improvement of various facilities at Ninoy E/S, Aguilar | Aguilar | 632223.3 | 2018-10-10 | 2018-11-30 | 100% | 632223.3 |  | completed
Repair/improvement of 2 -1 unit classroom at Bocboc East E/S, Bocboc East, Aguilar | Aguilar | 678570.52 | 2018-10-18 | 2018-11-19 | 100% | 678570.52 |  | completed
Repair/improvement of Stage at Urdaneta City Nat'l HS, Urdaneta City | Urdaneta | 1468685 | On Going |  | 55% | 807776.75 |  | on-going
Upgrading of ATS Panel & Main Feederline at Umingan Community Hosp., Umingan | Umingan | 1526238 | On Going |  | 20% | 305247.6 |  | on-going
Construction of Multi-Purpose Gym Bleachers at Tonton Elem. Sch., Tonton, Lingayen | Lingayen | 1445618 | On Going |  | 13.85% | 200218.093 |  | on-going
Construction of stage at Brgy. Villanueva, Bautista | Bautista | 1375256.3 | On Going |  | 75% | 1031442.225 |  | on-going
Upgrading of Electrical System and Rewiring of OR/DR & Ward Bldg. at Asingan Community Hospital, Asingan | Asingan | 1103582 | 2018-12-17 | 2018-12-17 | 100% | 1097675.25 |  | completed
Construction of Multi-Purpose Hall at Brgy. Bayoyong, Basista | Basista | 1817327.6 | 2018-03-27 | 2018-10-25 | 100% | 1817327.6 |  | completed
Construction of 3-storey Multi-Purpose Bldg., (Phase 1) at Capitol Cmpd., Lingayen | Lingayen | 16980927 | 2018-05-14 | On Going | 15% | 2547139.05 |  | on-going
Extension of 3-Phase Line & Installation of 3-75 KVA DX Transformer and Electrical Services at Mangatarem District Hospital, Mangatarem | Mangatarem | 1983012.74 | 2018-07-18 | 2018-09-18 | 100% | 1983012.74 |  | completed
Extension of 3-Phase Line & Installation of 3-100KVA DX Transformer at Training Center 2 Capitol Compound, Lingayen | Lingayen | 2347800 | 2018-07-09 | 2018-08-28 | 100% | 2347800 |  | completed
Improvement/rehabilitation of Main Ward Annex "B" at Urdaneta Dist. Hosp., Urdaneta City | Urdaneta | 1217241.07 | 2018-07-09 | 2018-10-25 | 100% | 1217241.07 |  | completed
13000 bags cement to be given to various barangays, associations and constituents in the province | Pangasinan | 3506750 | Materials Only |  |  | 3506750 |  | completed
Construction of Slope Protection of Open Canal at Motorpool Compound, Capitol Complex, Lingayen | Lingayen | 424485.35 | 2018-08-14 | 2018-09-21 | 100% | 424485.35 |  | completed
Repair of various facilities at LDH, Lingayen | Lingayen | 588289 | Not Yet Started |  | n/a | n/a |  | nys
Preventive maintenance of Bayambang Dist. Hosp., Bayambang | Bayambang | 253756 | Not Yet Started |  | n/a | n/a |  | nys
Repair/improvement of various buildings at Dasol Community Hosp., Dasol | Dasol | 340816 | Not Yet Started |  | n/a | n/a |  | nys
Installation of 3P wiring for medical waste treatment machine at PPH, San Carlos City | San Carlos City | 349036.22 | On Going |  | 30% | 349036.22 |  | on-going
Repair of Various buildings at Mangatarem Dist. Hosp., Mangatarem | Mangatarem | 358333 | On Going |  | 28% | 100333.24 |  | on-going
Tiling works at 2nd floor of the 2-storey Training Center, Alcala | Alcala | 394400 | 2018-11-30 | 2018-12-21 | 100% | 394400 |  | completed
Repair/improvement of various buildings at Urdaneta Dist. Hosp., Urdaneta City | Urdaneta | 832464 | Not Yet Started |  | n/a | n/a |  | nys
Repainting of All Buildings at Asingan Com. Hosp. | Asingan | 479545 | 2018-12-02 | 2019-01-07 | 100% | 476561.99 |  | completed
Repair of various buildings at EPDH, Tayug | Tayug | 485600 | [5 empty] | nys
Construction of covered pathway at Dasol Com. Hosp. Brgy. Bobonot, Dasol | Dasol | 465847 | Nov. 2018 | 2018-12-28 | 100% | 462170.52 |  | completed
Labor, materials, equipment and other incidentals for the improvement/upgrading of various facilities (TB DOTS and Animal Bite Bldg.) at Dasol Com Hosp., Dasol | Dasol | 344172.69 | Not Yet Started |  | n/a | n/a |  | nys
Waterproofing of concrete cutter and canopies at Capitol Bldg. Roofdeck, Capitol Complex, Lingayen | Lingayen | 728191 | 2018-12-04 | 2019-01-07 | 100% | 725581.41 |  | completed
Construction of Gravity Wall at Waste Management Cmpd., Lingayen | Lingayen | 3656070 | 2019-01-21 |  | 21.55% |  |  | on-going
Construction of 2 units septic tank at Pago, Sta. Barbara | Sta. Barbara | 204943 | 2018-12-04 | 2018-12-28 | 100% | 202944.37 |  | completed
Construction of Elevated flatform for Bantayog ng Wika, Lingayen | Lingayen | 186946 | 2018-12-03 | 2018-12-12 | 100% | 183777.45 |  | completed
Construction of Bleachers w/ drainage canal at Brgy. Mapolo-polo, Basista | Basista | 762314 | 2018-12-04 | 2019-02-08 | 100% | 758890.2 |  | completed
Construction of Stage at Brgy. Paragos, Bayambang | Bayambang | 1091829 | 2019-01-21 |  | 1.73% |  |  | on-going
Rehabilitation of Amado T. Espino, Jr. covered court (Gym) at Poblacion, Aguilar | Aguilar | 685118 | 2018-12-03 | 2019-01-04 | 100% | 685118 |  | completed
Construction of Day Care Center at Zone 5, Bayambang | Bayambang | 999854 | Not Yet Started |  | n/a | n/a |  | nys
Construction of perimeter fence at Brgy. Duera, Bayambang | Bayambang | 346771 | Not Yet Started |  | n/a | n/a |  | nys
Construction of stage (additional works), at Brgy. Bical Norte, Bayambang | Bayambang | 609668 | Not Yet Started |  | n/a | n/a |  | nys
800 pcs. Jetmatic, 1600 pcs. GI Pipe | Pangasinan | 5959200 | Materials Only |  | 100% | 5959200 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
5,000 bags of cement | Pangasinan | 1500000 | Materials Only |  | 100% | 1500000 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
15,000 bags of cement | Pangasinan | 4500000 | Materials Only |  | 100% | 4500000 |  | completed
Gill nets, accessories and packing materials to be distributed to marginalized fisherfolk associations in the coastal municipalities | Pangasinan | 1025500 | Materials Only |  | 100% | 1025500 |  | completed
Rehabilitation of Sto. Domingo Bridge, San Manuel | San Manuel | 2216218 | 2018-11-22 | 2019-01-04 | 100% | 2210317.79 |  | completed
Repair/iprovement of covered court and with construction of 2-units stage at Brgy. Magtaking, Bugallon | Bugallon | 2639177 | Not Yet Started |  | n/a | n/a |  | nys
Constructuion of 2-storey Legislative Bldg., (Phase 1) at Capitol Cmpd., Lingayen, Pangasinan | Lingayen | 25000000 | Not Yet Started |  | n/a | n/a |  | nys
Improvement/reconstruction of Alvear (Lightings, sidewalk with Railings) and Artacho (Lightings) Provincial Rad at Lingayen | Lingayen | 10000000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of stage and covered court (Gymnasium) at Brgy. Salomague Norte, Bugallon | Bugallon | 4715000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court at Batancaoa South E/S, Urbiztondo | Urbiztondo | 2825703 | Not Yet Started |  | n/a | n/a |  | nys
Construction of 2-storey PEO (Phase 1) at Motorpool Cmpd, Capitol Complex, Lingayen | Lingayen | 15000000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of 3-units 2-storey cottages at Provincial Capitol Resort Hotel, Lingayen | Lingayen | 10000000 | Not Yet Started |  | n/a | n/a |  | nys
Construction of PEO Warehouse Bldg. at Motorpool Cmpd, Lingayen | Lingayen | 11290429 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court (Gymnasium) at Brgy. Sabangan, Lingayen | Lingayen | 2240700 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court Gymnasium at Takipan, Mangatarem | Mangatarem | 2708097 | Not Yet Started |  | n/a | n/a |  | nys
Construction of covered court (Gymnasium) Standard at Real National High School, Urbiztondo | Urbiztondo | 3334213 | Not Yet Started |  | n/a | n/a |  | nys
Economic Development
16 units, 8-horsepower, 4 diesel engine for irrigation projects in Dist. III and V | Pangasinan | 687760 | Materials Only |  | 100% | 687760 |  | completed
Construction/installation of 40 units STWIP of various brgys and municipalities in the Province | Pangasinan | 3165356.4 | Not Stated |  | 100% | 3165356.4 |  | completed
Construction/installation of 40 units STWIP of various brgys and municipalities in the Province | Pangasinan | 2295168.75 | On Going |  | 72.5% | 2295168.75 |  | on-going
Construction of 1 unit 3-barrel RCBC, Sito Panotnot, Brgy. Pangascasan, Sual | Sual | 1454085.22 | 2018-06-15 | 2018-11-07 | 100% | 1454085.22 |  | completed
Concreting of Maracang-Nancalasan Rd., Mangatarem | Mangatarem | 4901369.54 | 2018-03-19 | 2018-10-18 | 100% | 4901369.54 |  | completed
Asphalt for blocktopping of Ballag Bridge, Bani | Bani | 195735 | 2018-09-12 | 2018-09-12 | 100% | 195735 |  | completed
Asphalt for blocktopping of Pauline Bridge, Sta. Barbara | Sta. Barbara | 314540 | 2018-10-02 | 2018-10-02 | 100% | 314540 |  | completed
Concreting Nalsian-Bacayao Rd., Calasiao | Calasiao | 2885418.63 | 2018-03-27 | 2018-07-30 | 100% | 2885418.63 |  | completed
Concreting of Salapingao Rd., Binmaley (part) | Binmaley | 3418180.98 | 2018-04-10 | 2018-09-11 | 100% | 3418180.98 |  | completed
Rehabilitation of Urdaneta Community Bridge (Superstructure), Urdaneta City | Urdaneta | 8715685.32 | 2018-04-27 | On Going | 35% | 3051539.86 |  | on-going
Concreting of Sitio Centro, San Jose, Alaminos | Alaminos | 1255535.4 | 2018-04-29 | 2018-05-28 | 100% | 878874.78 |  | completed
Improvement/rehabilitation (asphalting/blocktopping with patching) of Brgy. Cato to Patima Road, Infanta | Infanta | 1968175 | 2018-09-27 | 2018-10-01 | 100% | 1968175 |  | completed
Repair of Imelda Bridge (2 spans) at Mangatarem | Mangatarem | 10889178.55 | 2018-07-19 |  | 40% | 4355671.42 |  | on-going
Rehabilitation of Lipit Bridge, Manaoag | Manaoag | 1634527.45 | 2018-07-18 | 2018-08-31 | 100% | 1634527.45 |  | completed
500 MT Asphalt Pre-mix and 20 drums Emulsified Asphalt , Repair and maintenance of various provincial roads | Pangasinan | 3030000 | Not Stated |  | 100% | 3030000 |  | completed
4 drums E. Asphalt and 82 MT of Asphalt Pre-mix for the asphalting of Access Road to Emergency Room at PPH, Bolingit, San Carlos City | San Carlos City | 508314 | 2018-09-22 | 2018-06-26 | 100% | 508314 |  | completed
Concreting of Road at Brgy. Balangobong, Lingayen | Lingayen | 2565178.6 | 2018-10-11 | 2018-11-28 | 100% | 2565178.6 |  | completed
Concreting of Brgy. Road, Brgy. Inanlorenza, Bayambang | Bayambang | 995679.38 | 2018-09-04 | 2018-09-28 | 100% | 995679.38 |  | completed
Concreting of Pathwalk at Brgy. Maigpa, Bayambang | Bayambang | 994616.44 | 2018-09-04 | 2018-09-28 | 100% | 994616.44 |  | completed
Concreting of Pathwalk at Brgy. Caturay, Bayambang | Bayambang | 996366.4 | 2018-09-04 | 2018-09-28 | 100% | 996366.4 |  | completed
Concreting of Brgy. Road, at Brgy. Tanolong, Bayambang | Bayambang | 995679.38 | 2018-09-04 | 2018-09-28 | 100% | 995679.38 |  | completed
Repair of Damaged Concrete pavement along Mabini Breeding Station Road, Poblacion, Mabini | Mabini | 49325 | Not Stated |  | 100% | 49325 |  | completed
Asphalt pre-mix and Emulsified Asphalt for blocktopping/patching of Brgy. Libson West, Lingayen | Lingayen | 565700 | 2018-04-13 | 2018-04-13 | 100% | 565700 |  | completed
1000 MT Asphalt Pre-mix and 32 drums Emulsified Asphalt for patching/asphalting/blocktopping of various Brgy. Roads at Urbiztondo | Urbiztondo | 5960800 | Oct. 2018 | Nov. 2018 | 100% | 5960800 |  | completed
Asphalting of Brgy. Doyong, Calasiao | Calasiao | 1229600 | 2018-11-20 | 2018-11-23 | 100% | 1229600 |  | completed
745 MT Asphalt Pre-mix (Special Mix) and 30 drums Emulsified Asphalt (SS-1) for use in the improvement (blocktopping with patching) of Palguyod-Manaol Prov'l Road (Palguyod Side), Pozorrubio | Pozorrubio | 4529500 | 2018-11-22 | 2018-12-01 | 100% | 4529500 |  | completed
Asphalts for the improvement (Patching/blocktopping) of Brgy. Road at Brgy. Hacienda, Bugallon | Bugallon | 2671100 | 2018-10-18 | 2018-10-22 | 100% | 2671100 |  | completed
Asphalts for the Asphalting of premises of the Brgy. Gym at Brgy. Villanueva, Bautista | Bautista | 1652300 | 2018-11-16 | 2018-11-19 | 100% | 1652300 |  | completed
280 MT Asphalt Pre-mix and 9 drums Emulsified Asphalt for the improvement or Asphalt Overlay at Brgy. Salasa, Bugallon | Bugallon | 1669600 | 2018-11-06 | 2018-11-08 | 100% | 1669600 |  | completed
Reconstruction of slope protection at San Antonio Brdg., Sta. Barbara | Sta. Barbara | 688397 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (raising/asphalting/blocktopping) of Amansabina Road 1 at Amansabina, Mangaldan | Mangaldan | 530100 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Brgy. Road at Brgy. Nalsian Norte, Bayambang | Bayambang | 997850 | Dec. 2018 | On Going | 45% | 449032.5 |  | on-going
Various materials for the reconstruction of Matic-matic Bridge (Flatslab) at Bgy. Matic-Matic, Sta. Barbara | Sta. Barbara | 5922593 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (Patching and Blocktopping) of Bantayan-Talogtog-Bateng Rd., Mangatarem | Mangatarem | 1823500 | 2018-11-19 | 2018-11-29 | 100% | 1823500 |  | completed
Improvement (Concreting and Raising with Stone Masonry) of Poblacion-Dalongue Road at Sta. Barbara | Sta. Barbara | 15000000 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Sabangan Brgy. Road at Brgy Sabangan, Binmaley | Binmaley | 1912331 | Not Yet Started |  | n/a | n/a |  | nys
Improvement of Existing Concrete Pavement at Brgy. Tombor, Binmaley | Binmaley | 2396947 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Farm to Market Road, at Brgy. Bogtong Silag, Mangatarem | Mangatarem | 2790371 | Not Yet Started |  | n/a | n/a |  | nys
79 MT Asphalt Pre-mix and 4 drums Emulsified Asphalt for use in the Proposed Access Road and Multi-Purpose Pavement at Eguia National High School Cmpd., Dasol | Dasol | 575500 | Not Yet Started |  | n/a | n/a |  | nys
230 MT Asphalt Pre-mix and 10 drums Emulsified Asphalt for use in the Asphalting of Brgy. Road at Brgy. Lelemaan, Manaoag | Manaoag | 1650000 | Not Yet Started |  | n/a | n/a |  | nys
Rehabilitation of Embarcadero Bridge at Malasiqui | Malasiqui | 14500000 | Not Yet Started |  | n/a | n/a |  | nys
Concreting of Sitio Boquig Road, Brgy. Paitan, San Carlos City | San Carlos City | 3321104 | Not Yet Started |  | n/a | n/a |  | nys
Rehabilitation/construction of Panganiban Bridge along Tayug-Sta. Maria Road at Tayug | Tayug | 21116947 | Not Yet Started |  | n/a | n/a |  | nys
Asphalt for the proposed blocktopping of Brgy. Anolid Rd., Malasiqui | Malasiqui | 1363000 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (bloctopping) of Alvear Road, Lingayen | Lingayen | 9999000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Artacho Street, Lingayen | Lingayen | 4996000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Farm to market Road at Brgy. Buenlag, Binmaley | Binmaley | 2728000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Lucban St., Brgy. Pias Road at Mapandan | Mapandan | 2728000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping along Sta. Maria-Sn Roque Rd. at San Roque Section, San Jacinto, Pangasinan | San Jacinto | 2090000 | Not Yet Started |  | n/a | n/a |  | nys
Asphalting of Brgy. Alitaya Road at Alitaya, Mangaldan | Mangaldan | 1606000 | Not Yet Started |  | n/a | n/a |  | nys
Improvement (asphalting/blocktopping) of Brgy. Asin East Road at Malasiqui | Malasiqui | 3710000 | Not Yet Started |  | n/a | n/a |  | nys
Blocktopping of Brgy. Road at Amancoro, Binmaley | Binmaley | 2097000 | Not Yet Started |  | n/a | n/a |  | nys
Livelihood Projects - Loans Granted to various Associations and MPC's | Pangasinan | 5065000 | Loan
Amortization of Principal and Interest on Loan to the LBP | Pangasinan | 63734370.91 |  |  | 100% | 63734370.91 |  | completed
Environmental Development
Various farm/nursery implements to be used fro various farm activities and project implementation at our field stations and provincial nurseries in Sta. Barbara, San Quintin, Dasol, Bolinao, Mangatarem and Lingayen | Pangasinan | 390075 |  |  | 100% | 390075 |  | completed
Various seedlings to be distributed in various rural-based organizations including school in support to the provincial reforestation project of the Provincial Gov't and also in support to the food production project | Pangasinan | 1530000 |  |  | 100% | 1530000 |  | completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Provincial Governor

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of December 2018
Province of Pangasinan
LDRRMF
Particulars | Quick Response Fund (QRF) | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| 30% | 70%
A. Sources of Funds:
Current Appropriation | 59072134.3 | 137834980.06 |  |  |  | 196907114.36
Continuing Appropriation |  | 9997030.52 |  |  |  | 9997030.52
Previous Year's Appropriation transferred to the Special Trust Fund |  | 152629229.35 |  |  |  | 152629229.35
Others Interest Income(Trust Fund) |  |  |  |  | 90195.18 | 90195.18
Transfers/Grants | [5 empty] | 0
Others Interest Income (Trust Fund) | [5 empty] | 0
Total Funds Available | 59072134.3 | 300461239.93 | 0 | 0 | 90195.18 | 359623569.41
B. Utilization
Medicines | [5 empty] | 0
Medical Supplies | [5 empty] | 0
Food Supplies |  | 22480232.4 |  |  |  | 22480232.4
Office Supplies |  | 272745 |  |  |  | 272745
Repair of Evacuation Center | [5 empty] | 0
Disaster Response & Rescue Equipment |  | 19812975 |  |  |  | 19812975
Institutional/Capacity Development (Ex. Trainings, environmental assessment & other related activities) | [5 empty] | 0
Construction of Evacuation Center | [5 empty] | 0
Capital Outlay - Equipment | [5 empty] | 0
Transfer to other LGUs | [5 empty] | 0
Other Maintenance and Operating Expenses |  | 116037290.33 |  |  |  | 116037290.33
Traveling Expense | [5 empty] | 0
Training Expense |  | 541455.2 |  |  |  | 541455.2
IT Equipment & Software |  | 1894240 |  |  |  | 1894240
Motor Vehicles | [5 empty] | 0
Other Machineries and Equipment | [5 empty] | 0
Watercrafts | [5 empty] | 0
Other Property, Plant and Equipment | [5 empty] | 0
Roads, Highways and Bridges | [5 empty] | 0
Communication Equipment |  | 3511924 |  |  |  | 3511924
Gasoline, Oil, Lubricants |  | 1856023.96 |  |  |  | 1856023.96
Drugs and Medicines |  | 350000 |  |  |  | 350000
Repair & Maintenance-Machinery & Equipment |  | 527965.37 |  |  |  | 527965.37
Repair & Maintenance-Motor Vehicles |  | 1593959.4 |  |  |  | 1593959.4
Honorarium | [5 empty] | 0
Office Equipment |  | 653390 |  |  |  | 653390
Furnitures & Fixtures | [5 empty] | 0
Other Structures |  | 18449853.98 |  |  |  | 18449853.98
Other Transportation | [5 empty] | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. (Trust Fund) | [5 empty] | 0
Repair & Maintenance - Building & Other Structures (Trust Fund) | [5 empty] | 0
Bank Charges (Trust Fund) | [5 empty] | 0
Total Utilization (Current Appropriation) | 0 | 187982054.64 | 0 | 0 | 0 | 187982054.64
Reversion to General Fund of the Unutilized LDRRMF - TRUST FUND CY 2012 |  | 3963903.78 |  |  |  | 3963903.78
Reversion to General Fund of the Unutilized LDRRMF - TRUST FUND CY 2011 |  | 2286348.08 |  |  |  | 2286348.08
Reversion to General Fund of the Unutilized LDRRMF - TRUST FUND CY 2013 |  | 906831.08 |  |  |  | 906831.08
Total Utilization (Trust Fund) (Current Appropriation & Trust Fund) | 0 | 195139137.58 | 0 | 0 | 0 | 195139137.58
Unutilized Balance | 59072134.3 | 105322102.35 | 0 | 0 | 90195.18 | 164484431.83
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO,CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending December 31, 2018
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 213455745.85
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
119772242.79
Capital Outlay
38101787.1
Financial Expenses
-0-
Sub-total |  |  |  | 157874029.89
Balance |  |  |  | 55581715.96
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO, III
Governor
Note on I11: Pangasinan Accounting:

## CASHFLOW
FDP Form 9 - Statement of Cash Flow
(COA Form)
PROVINCE OF PANGASINAN
Statement of Condensed Cash Flows
GENERAL FUND
For the Fourth Quarter Ending December 31,2018
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 32626666.19
|  | Share from Internal Revenue Allotment |  | 794203249
|  | Receipts from business/service income |  | 96651559.08
|  | Interest Income |  | 1111473.8
|  | Other Receipts |  | 23922389.21
|  | Total Cash Inflow |  | 948515337.28
Cash Outflows:
|  | Payment of expenses |  | 337339978.45
|  | Payment to suppliers and creditors |  | 130057299.26
|  | Payment to employees |  | 315756065.75
|  | Interest Expenses |  | 14169934.95
|  | Other Expenses |  | 7116979.39
|  | Total Cash Outflow |  | 804440257.8
| Net Cas Flows from Operating Activities |  |  | 144075079.48
Cash Flows from Investing Activities:
Cash Inflows:
Proceeds from Sale of Investment Property
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 2161350
|  | Collection of Principal on Loans to other Entities |  | 5596925
|  | Total Cash Inflow |  | 7758275
Cash Outflows:
Purchase / Construction of Investment Property
|  | Purchase / Construction of Property, Plant and Equipment |  | 89716702.3
Purchase of Bearer Biological Assets
|  | Grant of Loans |  | 1800000
|  | Total Cash Outflow |  | 91516702.3
| Net Cash Flows from Investing Activities |  |  | -83758427.3
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 11459947.87
|  | Total Cash Inflow |  | 11459947.87
Cash Outflows:
Payment of Long-Term Liabilities
|  | Payment of Loan Amortization |  | 52043471.33
|  | Total Cash Outflow |  | 52043471.33
| Net Cash Flows from Financing Activities |  |  | -40583523.46
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 19733128.72
Add:Cash at Beginning of the Quarter |  |  |  | 1857998041.89
Cash at the End of the Quarter |  |  |  | 1877731170.61
Certified Correct:
ARTURO V. SORIANO,CPA
Provincial Accountant

## TRUSTFUND
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE OCTOBER - DECEMBER QUARTER, CY 2018
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
1 unit Tractor with Cage Roller / Leveler, Rotary Tiller and Trailer delivered to Imbalbalatong Multi-Purpose Cooperattive, Pozorrubio, Pangasinan | Pozorrubio, Pangasinan | 199600 |  |  | 100% | 199600 |  | fund from the Department of Agriculture
Rehabilitation of Gonzales-San Juan Farm to Market Road | Umingan, Pangasinan | 111846972.7 |  |  | 10.43% | 2625811.77 |  | fund from the Department of Agriculture
Medical Assistance for Indigent Patients of Lingayen District Hospital | Lingayen, Pangasinan | 1000000 |  |  | 36% | 363998.68 |  | fund from the Department of Health (MAIP)
Medical Assistance for Indigent Patients of Bolinao Community Hospital | Bolinao, Pangasinan | 500000 |  |  | 95% | 477289 |  | fund from the Department of Health (MAIP)
Medical Assistance for Indigent Patients of Urdaneta District Hospital | Urdaneta, Pangasisnan | 4000000 |  |  | 81.68% | 3267399.12 |  | fund from the Department of Health (MAIP)
Rehabilitation/improvement/upgrading of Burgos-liw-liw Road @ Burgos Pangasinan | Burgos, Pangasinan | 87957208.21 |  |  | 100% | 8795720.82 |  | fund from the Department of Interior and Local Government-CMGP
2 Units Vehicle (Passenger Van) for Tourism and Investment promotion and other related activities |  | 3000000 |  |  | 100% | 3000000 |  | funds from Department of Local and Interior Government - Performance Challenge Fund (PCF) CY 2017
Expenses for the Pangasinan Provincial Tourism Development Planning Seminar Workshop on Sept. 12-14, 2018 at View Park, Tagaytay, Calamba Road, Tagaytay City |  | 500000 |  |  | 100% | 500000 |  | funds from Department of Tourism (financial assistance for the provincial tourism master plan formulation - first tranche)
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO,CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor

## UNLIQUIDATED CASH ADV
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of December 31, 2018
Province, City or Municipality: |  | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Rowena Brenda O. Guiang | 56047 | 2018-12-27 | - pymt of cash advance for per diems, travelling expenses and miscellanoeus expenses for the CapabilityBuilding Tour of GSO personnel Area supervisors, electricians at Bonifacio Global City, Ayala Avenue, Makati City and Pampanga |  | 56047
Melody Claire D. Sison | 3600 | 2018-12-27 | - pymt of cash advance for per diems and travelling expenses for Observation Tour on Alternative Technologies Solid Waste Management of GSO |  | 3600
Louie F. Ocampo | 7680 | 2018-12-12 | - cash advance to defray expenses to conduct their Team Building of Pangasinan Dangoan Dance Group Dec. 17-18, 2018 |  | 7680
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 134927 |  |  | 0 | 67327 | 0 | 0 | 0 | 67600
Advances to Special Disbursing
Rodolfo M. Cortez | 30000 | 1997-04-10 | [6 empty] | 30000
Rodolfo M. Cortez | 20000 | 1996-06-20 | [6 empty] | 20000
Sub-total | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 50000
GRAND TOTAL | 184927 |  |  |  | 67327 |  |  |  | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO, III
Provincial Accountant | [5 empty] | Governor