## 1QTR (hidden)
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2020
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | TOTAL COST | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[6 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Re-painting of outside fence steel Barnicade, Cyclone Partition, Canal Oval Line and Carbs/painting of Basketball court, volleyball & Sipak Takraw |  |  | 2770257
Improvement/repair of NRSCC Tennis Court at NRSCC Cmpd., Lingayen |  | Lingayen | 2589931
Perimeter fencing with barbed wire of DRRM Learning Center at Brgy. San Vicente, Burgos |  | Burgos | 1127449
Installation of feederline ATS Panel Line Side Wiring & Electrical wiring for generator house at 3-storey Multi-Purpose Bldg., Lingayen |  | Lingayen | 1441595
Concreting of floor of playing area infront of grandstand & Lawn Tennis court at NRSCC, Lingayen |  | Lingayen | 8381580
Installation of main feederline & main distribution Panel on Public Health Bldg. at WPDH, Alaminos City |  | Alaminos City | 2025314
Asphalting of hospital grounds for parking and waiting area @ Bayambang District Hospital |  | Bayambang | 918500
Construction of PNP Crime Laboratory Bldg. at PPO, Lingayen |  | Lingayen | 3193050
Construction of public toilet@ Pasalubong Center, Capitol Cmpd., Lingayen |  | Lingayen | 1615914
Construction of covered court w/ bleachers at Eastern Pangasinan District Hospital, Tayug |  | Tayug | 6216225
Construction of additional 1-chamber septi tanks @ Capitol Complex, Lingayen |  | Lingayen | 880181
Improvement/asphalting of periphery of the Brgy. Auditorium and portions of Salomague Norte Road @ Brgy. Salomague Norte, Bugallon |  | Bugallon | 719750
Asphalting of Peripheral area of 3-storey multi-purpose Bldg., Capitol Cmpd., Lingayen |  | Lingayen | 890000
Repainting of NRSCC Grandstand façade , Lingayen |  | Lingayen | 777041
Completion of Ceiling of Multi-purpose Bldg., Poblacion, Bani |  | Bani | 173993
Payment of lot w/ an area of 3242 sq.m. at Bolingit, San Carlos City |  | San Carlos City | 1945200
Improvement of PDRRMO (construction of Canopy ground floor back of main bldg & concreting of basketball half court flooring & public CR Pathway @ LDH Cmpd., Lingayen |  | Lingayen | 864248
Upgrading of electrical main feederline of Admin Bldg. @ NRSCC, Lingayen |  | Lingayen | 849700
Replacement of Basketball & Rings & Volleyball Sepak Takraw Nets @ NRSCC, Lingayen |  | Lingayen | 151055
Construction of 1 unit Guard house, Steel gate @ PDRRMO, Lingayen |  | Lingayen | 1028262
Construction of covered court (gymnasium) @ Brgy. Calomboyan |  |  | 499710
Construction of Multi-Purpose Shed @ San Felipe West, San Nicolas |  | San Nicolas | 494420
Repair/improvement of multi-purpose hall @ Brgy. Salpad, San Nicolas |  | San Nicolas | 499574
Construction of covered court (gymnasium) @ Brgy. Annam (Phase 1), Umingan |  | Umingan | 497323
Landscaping of the Peripheral Area of the Multi-purpose Bldg., @ Brgy. Malabobo, Mangatarem |  | Mangatarem | 500000
Construction of elevated Stainless Tank @ Dasol Breeding Station, Dasol |  | Dasol | 807000
Construction of comfort room (male/female) at Dasol OPAG Breeding Station, Dasol |  | Dasol | 799504
Rooftop development of San Carlos City Jail @ Brgy. Bliss, Pagal, San Carlos City |  | San Carlos City | 891366
Construction of MP Building at Sobol, San Nicolas |  | San Nicolas | 857745
Construction of MP Building at Sinabaan, Umingan |  | Umingan | 529490
Improvement of Brgy. Hall, with CR, Barongobong, Natividad |  | Natividad | 44194
Concreting of Brgy. Hall, Peripheral Area, Dalangiring, Urbiztondo |  | Urbiztondo | 220206
Construction of MP Bldg., Cabuan, Umingan |  | Umingan | 514797
Repair/Improvement of MP Brgy. Bldg. at Carosalesan, Umingan |  | Umingan | 398369
Construction of MP Hall (Phase 1) at Canangaon, San Nicolas |  | San Nicolas | 499800
Construction/Installation of 5 units Solar St. lights at San Andrea, Umingan |  | Umingan | 455703
Construction of MP Bldg., Esperanza, Umingan |  | Umingan | 514797
Construction of Multi-Purpose Shed @ San Felipe West, San Nicolas |  | San Nicolas | 494420
Repair/improvement of multi-purpose hall @ Brgy. Salpad, San Nicolas |  | San Nicolas | 499574
Construction of covered court (gymnasium) @ Brgy. Annam (Phase 1), Umingan |  | Umingan | 497323
Landscaping of the Peripheral Area of the Multi-purpose Bldg., @ Brgy. Malabobo, Mangatarem |  | Mangatarem | 500000
Construction of elevated Stainless Tank @ Dasol Breeding Station, Dasol |  | Dasol | 807000
Construction of comfort room (male/female) at Dasol OPAG Breeding Station, Dasol |  | Dasol | 799504
Rooftop development of San Carlos City Jail @ Brgy. Bliss, Pagal, San Carlos City |  | San Carlos City | 891366
Construction of 3 units Artesian Well @ Brgy. Labney, San Jacinto |  | San Jacinto | 132945
Construction of 2 units Artesian Well @ Brgy. Cabangaran, Umingan |  | Umingan | 95124
Construction of 3 units Dug Well w/ jetmatic Pump head @ Brgy. San Bonifacio, San Manuel |  | San Manuel | 96933
Construction of 3 units Artesian Well @ Brgy. Alo-O, Umingan |  | Umingan | 117864
Construction of 5 units Artesian Well @ Brgy. Malimpuec, Basista |  | Basista | 121523
Construction of 3 units Artesian Well @ Brgy.Bantog, Umingan |  | Umingan | 117759
Construction of 3 units Artesian Well @ Brgy. Carosalesan, Umingan |  | Umingan | 116859
Construction of 3 units Artesian Well @ Brgy. Palospos, San Carlos City |  | San Carlos City | 112923
Construction of 3 units Artesian Well @ Brgy. San Roque, San Jacinto |  | San Jacinto | 122484
Extension of drainage canal @ Carusocan Norte, Asingan |  | Asingan | 497117
Construction of concrete drainage canal with fixed and removable cover, Nibaliw Norte, Bautista |  | Bautista | 1003963
Construction, declogging of drainage canal along San Miguel Road, Calasiao |  | Calasiao | 2891760
Proposed permanent marking at Binalonan at Binalonan-San Manuel Rd. Binalonan & San Manuel |  | Binalonan & San Manuel | 1982973
Construction & repair of concrete drainage canal w/ fixed and removable cover and cross drain (infront of Juan C. Laya NHS) @ San Manuel |  | San Manuel | 10164063
Economic Development
Amortization of Principal and Interest on Loan to the LBP |  |  | 49630158.58
Various farm inputs implementation of the aquaculture Technology demonstration projects @ OPAG Bolinao Fish Farm in Arnedo, Bolinao |  |  | 402561
Livelihood Projects - Loans Granted to various Associations and MPC's |  |  | 5640000
Emulsified asphalt for the repair & maintenance of provincial roads within the province |  |  | 3497500
Concreting of Brgy. Pantol-Poponto Rd., (Brgy. Pantol Side) @ Bayambang |  |  | 1136643
Asphalting/blocktopping of Cacayasen Brgy. Road, @ Burgos |  |  | 1433000
Reconstruction of foot bridge |  |  | 6635427
Improvement/blocktopping of Brgy. Road & Brgy. Pantal, Bugallon |  |  | 495000
Concreting of Mapolopolo Bayoyong Rd., @ Basista |  |  | 10000000
Concreting of Road Shoulder @ Brg. San Felipe East, San Nicolas |  |  | 499325
272 MT Pre-mix and 13 drums Emulsified asphalt |  |  | 1969500
Concreting of Brgy. Road, Brgy. Aserda, Mapandan |  |  | 497204
Concreting of Lobong-Labney Rd., @ San Jacinto |  |  | 5456675
Construction of drainage Canal @ Brgy. Poblacion Sur Road, Sta. Barbara |  |  | 526815
Asphalt/pre-mix for use in the repair/maintenance of various roads and bridges w/in the province |  |  | 3750500
Improvement of slope protection along Maticmatic Manomong Rd., Sta. Barbara |  |  | 1924574
Improvement/rehab of Kinabalutan Bridge (flat slab) Matulong, Manaoag |  |  | 1695993
Asphalt for blocktopping of Brgy. Road, Dulay |  |  | 857500
Asphalt for blocktopping of Peripheral Area of Public Market, Poblacion, Balungao |  |  | 1255000
Environmental Development

## UNLIQUIDATED CA
FDP Form 12- Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
As of September 30, 2020
Province, City or Municipality: |  | PANGASINAN
Name of Debtor (in alphabetical order) | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Advances for Officers and Employees
Christine Ann Margret Z. Calimlim | 4500 | 2020-08-10 | cash advance registration fee to attend webinar on values restoration officers (VROs) training the trainers August 11-14, 2020 via zoom videoconferencing | 4500
Henry E. Cruz | 4500 | 2020-08-10 | cash advance registration fee to attend webinar on Values Restoration officers August 11-14, 2020 | 4500
Mr. Tyrone R. Pagsolingan | 11300 | 2020-02-05 | cash advance the Reg. Fee, Traveling expenses, hotel accomodation and per diems attending the Montoring and Coaching for leaders training in Civil Service Commission |  |  | 11300
Salvador Vedaña | 10000 | 2003-10-08 | Traveling Expenses | [5 empty] | 10000
Judge Dionisio C. Sison | 7000 | 2001-07-16 | [6 empty] | 7000
Eugenio G. Ramos | 2500 | 1999-04-14 | [6 empty] | 2500
BM Eduardo Perez, Sr. | 5000 | 1999-02-03 | Traveling Expenses | [5 empty] | 5000
BM Rogelio Law | 5000 | 1997-09-22 | Traveling Expenses | [5 empty] | 5000
Atty. Feliciano M. Bautista | 1200 | 1997-07-22 | Traveling Expenses | [5 empty] | 1200
Roderick Mina | 3600 | 1997-06-22 | Traveling Expenses | [5 empty] | 3600
BM Leonardo Caranto | 20000 | 1997-02-27 | Traveling Expenses | [5 empty] | 20000
Maximu Dulay | 5000 | 1989-06-16 | [6 empty] | 5000
Federico Victorio | 1500 | 1985-04-30 | Traveling Expenses | [5 empty] | 1500
Rodolfo Rivera | 1300 | 1983-06-04 | Traveling Expenses | [5 empty] | 1300
Rodolfo Itchon | 1500 | 1982-05-07 | Traveling Expenses | [5 empty] | 1500
Rodolfo Itchon | 1000 | 1981-03-19 | Traveling Expenses | [5 empty] | 1000
Rodolfo Rodrigo | 500 | 1978-11-23 | Traveling Expenses | [5 empty] | 500
Narciso Ramos | 1250 | 1978-08-28 | Traveling Expenses | [5 empty] | 1250
Felipe Santillan | 1250 | 1978-02-28 | Traveling Expenses | [5 empty] | 1250
Sub-total | 87900 |  |  | 9000 | 0 | 11300 | 0 | 0 | 67600
Advances to Special Disbursing
Irmina B. Francisco | 50000 | 9/9/2020 | cash advance to defray misc expenses for use in the Pgo | 50000
IRMINA B. FRANCISCO | 200000 | 2020-09-24 | To cash advance of financial assistance for medication given to different constituents of the province of pangasinan | 200000
Cristina J. Bumiltac | 750000.08 | 2020-09-30 | to replenishment of cash advance in pymt of various operational use at Capitol Resort Hotel | 750000.08
Irmina B. Francisco | 100000 | 2020-08-24 | cash advance financial assistance for cultural presentation given to diff constituents of the Province of Pangasinan |  | 100000
Edwin B. Sison | 200000 | 2020-07-27 | cash advance to be used of annual registration fees of various motor vehicles with plate fees of various motor vehicles with plate numbers ending in 7 and 8 |  | 200000
Irmina B. Francisco | 50000 | 2020-06-15 | cash advance for defray misc expenses for use in the Pgo |  | 50000
Irmina B. Francisco | 200000 | 2020-03-26 | cash advance of financial assistance for medication given to diff constituents of the Province of Pangasinan |  |  | 200000
Irmina B. Francisco | 100000 | 2020-02-19 | cash advance of financial assistance for medication given to diff constituents of the Province of Pangasinan |  |  | 100000
Irmina B. Francisco | 100000 | 2020-02-19 | cash advance of FA for cultural presentation given to diff constituents of the Province of pangasinan |  |  | 100000
Rodolfo M. Cortez | 30000 | 1996-06-20 | [6 empty] | 30000
Rodolfo M. Cortez | 20000 | 1997-04-10 | [6 empty] | 20000
Sub-total | 1800000.08 |  |  | 1000000.08 | 350000 | 400000 | 0 | 0 | 50000
GRAND TOTAL | 1887900.08 |  |  | 1009000.08 | 350000 | 411300 | 0 | 0 | 117600
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor

## TRUST FUND UTILIZATION
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE JULY - SEPTEMBER QUARTER, CY 2020
Province : PANGASINAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Medical Assistance for Indigent Patients of Various Hospitals | [5 empty] | 8092186.4 |  | funds from Department of Health (MAIP)
Rehalbilitation of Balungao Sta. Maria Road | Balungao, Pangasinan | 47343826.99 |  |  | 100% | 47343826.99 |  | funds from Department of Interior and Local Government (CMGP)
Various Programs / Activities for Covid - 19 | [5 empty] | 27724113 |  | Trust Liabilities (Calamity Fund)
Special Risk Allowance for COVID - 19 Frontliners | [5 empty] | 12222813.21 |  | funds from Sual Corporation (RWMHEEF)
Contruction of Bangus Processing Facility for Integrated Small Fishpond Owners and Lesses (ISFOl) MPC | Brgy. BIEC, Binmaley, Pangasinan | 3070403.04 |  |  | 50.35% | 1545947.93 |  | funds from Department of Agriculture (PRDP-IREAP-GOP)
RehabiLitation of Gonzales-San Juan Farm to market road | Umingan, Pangasinan | 119270614.79 |  |  | 94.35% | 112531825.05 |  | funds from Department of Agriculture (PRDP-IBUILD)
Various expenses for early childhood care and development in the first 1000 days (ECCD-FIK) Program (NNC) | [5 empty] | 22508018.44 |  | funds from National Nutrition Council
Construction of two storey halfway house building | Burgos, Pangasinan | 4814424.71 |  |  | 80% | 3851539.77 |  | funds from Department of Interior and Local Government
Rehabilitation of Basista-Urbiztondo Road Phase II | Basista Pangasinan | 86266272.5 |  |  | 50% | 43133136.25 |  | funds from Department of Interior and Local Government (CMGP)
Construction of two storey multi-purpose building for basic sector | PSWDO Compound, Lingayen, Pangasinan | 17230406.1 |  |  | 30% | 5169121.83 |  | funds from Sual Corporation (DLF)
Construction of Tomato Trading Post Facility for Tugui Grande Fresh Produce Farme's Association, Inc. | Brgy. Tugui Grande | 2885843.5 |  |  | 16% | 461734.96 |  | funds from Department of Agriculture (PRDP-IREAP-GOP)
TOTAL | [5 empty] | 284584263.83
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO,CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor

## CASH FLOW
PROVINCE OF PANGASINAN
Statement of Cash Flows
GENERAL FUND
For the Month Ended September 30, 2020
Cash Flows from Operating Activities:
Cash Inflows:
|  | Collection from Taxpayers |  | 10970993.39
|  | Share from Internal Revenue Allotment |  | 324467852
|  | Receipts from business/service income |  | 32775118.54
|  | Interest Income |  | 196367.14
|  | Other Receipts |  | 15165743.24
|  | Total Cash Inflow |  | 383576074.31
Cash Outflows:
|  | Payment of expenses |  | 90847156.94
|  | Payment to suppliers and creditors |  | 45659290.81
|  | Payment to employees |  | 108470398.16
|  | Interest Expenses |  | 2644095.39
|  | Other Expenses |  | 4446247.15
|  | Total Cash Outflow |  | 252067188.45
| Net Cas Flows from Operating Activities |  |  | 131508885.86
Cash Flows from Investing Activities:
Cash Inflows:
|  | Proceeds from Sale of Investment Property |  | 0
|  | Proceeds from Sale/Disposal of Property, Plant and Equipment |  | 0
Proceeds from Insurance Claim
|  | Proceeds from Sale of Biological Assets |  | 0
|  | Collection of Principal on Loans to other Entities |  | 7450000
|  | Total Cash Inflow |  | 7450000
Cash Outflows:
|  | Purchase / Construction of Investment Property |  | 0
|  | Purchase / Construction of Property, Plant and Equipment |  | 75509168.06
|  | Purchase of Bearer Biological Assets |  | 0
Grant of Loans
|  | Total Cash Outflow |  | 75509168.06
| Net Cash Flows from Investing Activities |  |  | -68059168.06
Cash Flows from Financing Activities:
Cash Inflows:
|  | Proceeds from Loans |  | 1692767.49
|  | Total Cash Inflow |  | 1692767.49
Cash Outflows:
|  | Payment of Long-Term Liabilities |  | 0
|  | Payment of Loan Amortization |  | 12392000.94
|  | Total Cash Outflow |  | 12392000.94
| Net Cash Flows from Financing Activities |  |  | -10699233.45
Total Cash Provided by Operating,Investing and
|  | Financing Activities |  | 52750484.35
Add:Cash at Beginning of the Month |  |  |  | 2229564069.21
Cash at the End of the Month |  |  |  | 2282314553.56 | 0
Certified Correct:
ARTURO V. SORIANO, CPA
Provincial Accountant

## SEF
FDP Form 11 - SEF Utilization
(SEF Budget Accountability Form No. 1)
REPORT OF SEF UTILIZATION
For the Quarter Ending September 30, 2020
Province/City Municipality |  | Pangasinan
Receipt from SEF |  |  |  | 165000000
Less: | DISBURSEMENTS (broken down by expense class and by object of expenditure)
Personal Services
-0-
Maintenance and Other Operating Expenses
42449274.64
Capital Outlay
49018263
Financial Expenses
-0-
Sub-total |  |  |  | 91467537.64
Balance |  |  |  | 73532462.36
We hereby certify that we have reviewed the
contents and hereby attest to the veracity and
correctness of the data or information
contained in this document.
ARTURO V. SORIANO, CPA
Provincial Accountant
HON. AMADO I. ESPINO III
Governor
Note on I11: Pangasinan Accounting:

## LDRRM
FDP Form 8 - Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
As of September 2020
Province of Pangasinan
LDRRMF
Particulars | Quick Response Fund (QRF) | Mitigation Fund | NDRRMF | From Other LGUs | From Other Sources | Total
| 30% | 70%
A. Sources of Funds:
Current Appropriation | 68346214.5 | 159474500.5 |  |  |  | 227820715
Continuing Appropriation |  | 24174415.6 |  |  |  | 24174415.6
Previous Year's Appropriation transferred to the Special Trust Fund |  | 121266731.76 |  |  |  | 121266731.76
Others Interest Income(Trust Fund) |  | 0 |  |  | 0 | 0
Transfers/Grants |  | 0 |  |  | 0 | 0
Others Interest Income (Trust Fund) | [5 empty] | 0
Total Funds Available | 68346214.5 | 304915647.86 | 0 | 0 | 0 | 373261862.36
B. Utilization
Medicines |  | 0 |  |  |  | 0
Medical Supplies |  | 0 |  |  |  | 0
Food Supplies | 59237500 | 0 |  |  |  | 59237500
Office Supplies |  | 0 |  |  |  | 0
Repair of Evacuation Center |  | 0 |  |  |  | 0
Disaster Response & Rescue Equipment |  | 0 |  |  |  | 0
Institutional/Capacity Development (Ex. Trainings, environmental assessment & other related activities) |  | 0 |  |  |  | 0
Construction of Evacuation Center |  | 0 |  |  |  | 0
Capital Outlay - Equipment |  | 0 |  |  |  | 0
Transfer to other LGUs |  | 0 |  |  |  | 0
Flood Control Systems |  | 2000000 |  |  |  | 2000000
Other Maintenance and Operating Expenses | 255300 | 1751916.7 |  |  |  | 2007216.7
Traveling Expense |  | 293083 |  |  |  | 293083
Training Expense |  | 71087 |  |  |  | 71087
IT Equipment & Software |  | 966500 |  |  |  | 966500
Motor Vehicles |  | 6000000 |  |  |  | 6000000
Other Machinery and Equipment |  | 1893900 |  |  |  | 1893900
Watercrafts |  | 0 |  |  |  | 0
Other Property, Plant and Equipment |  | 0 |  |  |  | 0
Roads, Highways and Bridges |  | 0 |  |  |  | 0
Communication Equipment |  | 338300 |  |  |  | 338300
Gasoline, Oil, Lubricants |  | 913007.01 |  |  |  | 913007.01
Drugs and Medicines |  | 6470500 |  |  |  | 6470500
Repair & Maintenance-Machinery & Equipment |  | 326704.54 |  |  |  | 326704.54
Repair & Maintenance-Motor Vehicles |  | 40798 |  |  |  | 40798
Construction & Heavy Equipment |  | 0 |  |  |  | 0
Office Equipment |  | 0 |  |  |  | 0
Furnitures & Fixtures |  | 0 |  |  |  | 0
Other Structures |  | 373931 |  |  |  | 373931
Other Transportation Equipment |  | 0 |  |  |  | 0
Repair/Rehabilitation of Public Infrastructures, Roads, Highways and Bridges, etc. (Trust Fund) | [5 empty] | 0
Repair & Maintenance - Building & Other Structures (Trust Fund) | [5 empty] | 0
Bank Charges (Trust Fund) | [5 empty] | 0
Total Utilization (Current Appropriation) | 59492800 | 21439727.25 | 0 | 0 | 0 | 80932527.25
0
0
COVID-19 Related Expenses |  | 94277763.01 | 0 | 0 | 0 | 94277763.01
Total Utilization (Trust Fund) (Current Appropriation & Trust Fund) | 59492800 | 115717490.26 | 0 | 0 | 0 | 175210290.26
Unutilized Balance | 8853414.5 | 189198157.6 | 0 | 0 | 0 | 198051572.1
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. |  |  |  |  | Noted by:
ARTURO V. SORIANO, CPA |  |  |  |  | HON. AMADO I. ESPINO III
Provincial Accountant |  |  |  |  | Governor

## 20%IRA
FDP Form 7- 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2020
Province, City or Municipality: PANGASINAN
PROGRAM OR PROJECT | LOCATION | TOTAL COST | DATE STARTED | TARGET COMPLETION DATE | PROJECT STATUS |  | No. of Extensions, if any | Remarks
[5 empty] | % OF COMPLETION | TOTAL COST INCURRED TO DATE
Social Development
Relocation of lines and replacement of wires at Capitol Compound, Lingayen | Lingayen | 1415895 | 2020-08-17 |  | 100% | 1415895 |  | completed
Installation of 13 units Solar Stree Lights, San Roque, San Manuel | San Manuel | 941071 | [5 empty] | nys
Construction of Perimeter Fence w/ steel Gate at Capitol Compound, Lingayen | Lingayen | 1719577 | 2020-08-26 | On-going |  |  |  | on-going
Construction of stage at Camp Abat, Manaoag | Manaoag | 1465389 | 2020-08-17 | On-going | 47.73% | 699430.1697 |  | on-going
Installation of Transformer and Electrical Services at the 3-storey MP Building at Capitol, Bugallon | Bugallon | 1656588.13 | [5 empty] | nys
Installation of electrical main feederline for 3 units 2-storey cottages at CRH, Lingayen | Lingayen | 1727261 | 2020-08-24 |  | 100% | 1727261 |  | completed
Rehabilitation of drainage system w/ catch basin at Bayambang District Hospital | Bayambang | 1150000 | [5 empty] | nys
2-storey MP Building, Asingan | Asingan | 987795
Construction/installation of 10 units Solar Street light at Brgy. Caoayan Kiling, Urbiztondo | San Carlos City | 1000000 | [5 empty] | nys
Asphalting of Parking Area at Training Center 1 & 2, Capitol Cmpd., Lingayen | Lingayen | 2944000 | [5 empty] | nys
Construction of Additonal 16 units Chamber for the Existing Septic Tanks at NRSCC, Lingayen | Lingayen | 1428657 | [5 empty] | nys
Construction of Senior Citizen Bldg., Brgy. Baluyot, Bautista | Bautista | 1217073 | [5 empty] | nys
Improvement of PDRRMO (construction of Canopy ground floor back of main bldg & concreting of basketball half court flooring & public CR Pathway @ LDH Cmpd., Lingayen | Lingayen | 861560.04 | 2020-01-30 | 2020-03-13 | 100% | 861560.04 |  | completed
Upgrading of electrical main feederline of Admin Bldg. @ NRSCC, Lingayen | Lingayen | 837890.12 | 2020-02-18 | 2020-05-10 | 100% | 837890.12 |  | completed
Concreting of Brgy. Hall, Peripheral Area, Dalangiring, Urbiztondo | Urbiztondo | 218240.1 |  |  | 100% | 218240.1 |  | completed
Construction of MP Hall (Phase 1) at Canangaon, San Nicolas | San Nicolas | 497381.25 | 2020-02-26 | 2020-07-10 | 100% | 497381.25 |  | completed
Improvement of Pasalubong Center into PGEMPCOP at Beachfront Capitol Complex, Lingayen | Lingayen | 769731 | 2020-08-19 | Sept. 2020 | 100% | 769731 |  | completed
Construction of covered walkway at Bolinao Community Hospital | Bolinao | 804733 | 2020-08-17 | on-going | 53.76% | 432624.4608 |  | on-going
Extension/improvement of Dietary Bldg., at PPH, Bolingit, San Carlos City | San Carlos City | 999921 | 2020-08-13 | on-going | 25% | 249980.25 |  | on-going
Improvement of laboratory Room at Mangatarem Dist. Hopital, Mangatarem | Mangatarem | 380718 | 2020-08-19 | on-going | 75% | 285538.5 |  | on-going
Improvement of Dietary & Laundry Room at Umingan Community Hospital | Umingan | 859081 |  |  |  | 0 |  | nys
Provision of Roof Deck Roofing for X-Ray/Ultrasound Bldg. at Mapandan Com. Hospital | Mapandan | 1322693 | 2020-08-26 | on-going | 62% | 820069.66 |  | on-going
Repair of PDRRMO (former PSWDO) Bldg. at PDRRMO Compound, Lingayen | Lingayen | 797828 |  | nys |  | 0 |  | nys
Replacement of floor tiles at Provincial Veterinary Clinic, Brgy. Bliss Libson East., Lingayen | Lingayen | 309972 | 2020-09-25 | on-going | 90% | 278974.8 |  | on-going
Preventive maintenance/pallative repair at Brgy. Arnedo, PAgO, Bolinao | Bolinao | 189388 |  |  |  | 0 |  | nys
Replacement of stainless steel watertank and repair of its structural frame & PPH, Brgy. Bolingit, San Carlos City | San Carlos City | 387000 |  |  |  | 0 |  | nys
Preventive maintenance of Western Pangasinan District Hospital at Alaminos City | Alaminos City | 108881 |  |  |  | 0
Upgrading of electrical system at Pangasinan Reformation Center, Brgy. San Vicente, Burgos | Burgos | 2684354 | 2020-10-19 | on-going | 20% | 536870.8 |  | on-going
Improvement of Dialysis Bldg., at Urdaneta District Hospital, Urdaneta City | Urdaneta City | 917981 | 2020-10-06 | on-going | 90% | 826182.9 |  | on-going
Construction of 2 units Artesian Well @ Brgy. Cabangaran, Umingan | Umingan | 95024 | 2020-03-02 | 2020-06-26 | 100% | 95024 |  | completed
Construction of 3 units Artesian Well @ Brgy. Alo-O, Umingan | Umingan | 117744 | 2020-03-02 |  | 100% | 117744 |  | completed
Construction of 3 units Artesian Well @ Brgy.Bantog, Umingan | Umingan | 117639 | Not Stated |  | 100% | 117639 |  | completed
Construction of 3 units Artesian Well @ Brgy. Labney, San Jacinto |  | 132783 | 2020-09-07 |  | 100% | 132783 |  | completed
Construction of 3 units Artesian Well @ Brgy. Palospos, San Carlos City | San Carlos City | 112739 | 2020-09-07 |  | 100% | 112739 |  | completed
Construction of 2 units artesian well at Brgy. Cabalitian, Umingan | Umingan | 288000 | [5 empty] | nys
Construction of 2 units Dug well with jetmatic pump head at Brgy. Maseil-seil, Umingan | Umingan | 237300 | [5 empty] | nys
Construction of 2 units artesian well at Brgy. Macayug, San Jacinto | San Jacinto | 307000 | [5 empty] | nys
Construction of 1 unit artesian well at Brgy. Gamata, San Carlos City | San Carlos City | 339000 | [5 empty] | nys
Construction of 2 deep well at Brgy. Olo, Cagarlitan, Mangatarem | Mangatarem | 1177000 | [5 empty] | nys
Construction of 1 unit Level II Water System at Brgy. Buenlag, Binmaley | Binmaley | 474000 | [5 empty] | nys
Construction of 1 unit Point Source system (Deep well) at Brgy. San Roque, Bolinao | Bolinao | 224000 | [5 empty] | nys
Construction of Well source (6" dia. Casing, 54' m depth) at Brgy. San Miguel, Bani | Bani | 117000 | [5 empty] | nys
Construction of 2 units dug well at Brgy. Don Montano, Umingan | Umingan | 190000 | [5 empty] | nys
Emulsified asphalt for the repair & maintenance of provincial roads within the province | Pangasinan | 3489865 | Not Stated |  | 100% | 3489865 |  | completed
Concreting of Brgy. Pantol-Poponto Rd., (Brgy. Pantol Side) @ Bayambang | Bayambang | 1131315.45 | 2020-05-25 | 2020-06-11 | 100% | 1131315.45 |  | completed
Asphalting/blocktopping of Cacayasen Brgy. Road, @ Burgos | Burgos | 1429880 | 2020-07-20 | 2020-07-24 | 100% | 1429880 |  | completed
Reconstruction of foot bridge | Pangasinan | 6318692.84 | 2020-03-25 | on-going | 50% | 3159346.42 |  | on-going
TOTAL Social Development |  | 46899640.93 |  |  |  | 20243965.9205
Economic Development
Amortization of Principal and Interest on Loan to the LBP | Pangasinan | 76111535.42
Various farm inputs implementation of the aquaculture Technology demonstration projects @ OPAG Bolinao Fish Farm in Arnedo, Bolinao | Bolinao | 402431 | Not Stated |  | 100% | 402431
Fish gears, gill nets, fish trap, fish pot & other accessories | Pangasinan | 3006500
Assorted fruit trees and coconut seedlings | Pangasinan | 1755000
297 Pre-mix and 13 drums asphalt at San Vicente, Burgos | Burgos | 2132000
Concreting of Mapolopolo Bayoyong Rd., @ Basista | Basista | 10000000 | 2020-03-19 | on-going | 15% | 1495548 |  | on-going
69 MT Pre-mix and 3 drums Emulsified Asphalt for the blocktopping of Zone III Road, Rosales | Rosales | 495000 | [5 empty] | nys
Concreting of FMR (farm to market Road) at Brgy. Rizal, Rosales | Rosales | 769502 | 2020-08-17 | 2020-08-26 | 100% | 769502 |  | completed
155 MT Pre-mix and 7 drums E. Asphalt for Asphalting/blocktopping along Tebag-Butao Rd. (Tebag Section) at Sta. Barbara | Sta. Barbara | 1116000 | 2020-09-02 | 2020-09-15 | 100% | 1116000 |  | completed
690 MT Pre-mix and 30 drums E. Asphalt for the blocktopping of Arnedo- Balingasay Provincial Road at Bolinao | Bolinao | 4950000 | 2020-08-12 | 2020-09-16 | 100% | 4950000 |  | completed
Repair and maintenance of various Provincial roads w/in the province | Pangasinan | 7678000
Concreting of farm to Market Road at Brgy. Cabilacaan, Calasiao | Calasiao | 2180782 | 2020-08-23 | on-going | 34% | 741465.88 |  | on-going
Concreting of Brgy. Nagpalangan Road, Binmaley | Binmaley | 1221817 | 2020-08-26 | on-going | 5% | 61090.85 |  | on-going
Blocktopping of Brgy. Pallas Road, Binmaley | Binmaley | 2310000 | 2020-07-07 | 2020-07-16 | 100% | 2310000 |  | completed
Blocktopping of Mapandan-Urdaneta Road, Urdaneta City | Urdaneta City | 4950000 | 2020-08-12 | 2020-08-28 | 100% | 4950000 |  | completed
Asphalting of Mabini Road at Balungao | Balungao | 2054000 | 2020-09-25 | 2020-10-01 | 100% | 2054000 |  | completed
Blocktopping of Brgy. Road., at Brgy. Bila, Sison | Sison | 1022500 | on-going |  | 60% | 613500 |  | on-going
Concreting of Farm to Market Road at Brgy. Payar, Malasiqui | Malasiqui | 1249901 | 2020-09-29 |  | 97% | 1212403.97 |  | on-going
Asphalting of Brgy. Road at Brgy. Ballag, Bani | Bani | 1650000 | [5 empty] | nys
Construction of box culvert at Tubuan, Labrador | Labrador | 1199747 | [5 empty] | nys
Construction of Concrete Bridge at Brgy., San Juan, Agno | Agno | 8818028 | [5 empty] | nys
Concreting of Road/Pathwalk at Brgy. Flores, San Manuel | San Manuel | 5100000 | 2020-09-29 | on-going | 3% | 153000 |  | on-going
Concreting of Litac-Namacalan Road, at Brgy. Boboy, Agno | Agno | 2596032 |  | on-going |  |  |  | nys
Reconstruction 3-barrel Reinforced Concret box Culvert at Brgy. Cacayasen, Burgos | Burgos | 2129432 |  | on-going |  |  |  | nys
Concreting of Brgy. Babuyan Road, Infanta | Infanta | 2523495 |  | on-going |  |  |  | nys
Concreting of pathwalk at Cabaoangan Farm to market Road, Brgy. Siblot, San Nicolas | San Nicolas | 3580995 |  | on-going |  |  |  | nys
Concreting of Quiray Road in Sitio Kadampat at Brgy. Bolo, Labrador | Labrador | 3556991 |  | on-going |  |  |  | nys
Blocktopping of San Carlos-Sta. Barbara via Macabito at San Carlos City | San Carlos City | 4950000 |  | on-going |  |  |  | nys
Blocktopping of Brgy. Songkoy Road, Calasiao | Calasiao | 1980000 | on-going |  | 78.26% | 1549548 |  | on-going
Asphalting of San Isidro Norte Road, Binmaley | Binmaley | 2410000 | [5 empty] | nys
Blocktopping of FMR AT Brgy. Aliaga, Malasiqui | Malasiqui | 2970000 | [5 empty] | nys
Reconstruction of Lipit Bridge (Prestressed) at Manaoag | Manaoag | 20756920 | [5 empty] | nys
TOTAL Economic Development |  | 85378153 |  |  |  | 22378489.7
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ARTURO V. SORIANO, CPA | [5 empty] | HON. AMADO I. ESPINO III
Provincial Accountant | [5 empty] | Governor